## Sheet1
Task Name | Baseline Start | Baseline Finish | Baseline Duration | Actual Start | Actual Finish | Start | Finish | Duration | % Complete | Predecessors | Successors
Naidupeta_TopCon-Cell_7.1GW | Tue 01-10-24 | Tue 30-06-26 | 615 days | Tue 01-10-24 | NA | Tue 01-10-24 | Tue 30-06-26 | 614.88 days | 22%
Pre Project Approval | Tue 01-10-24 | Tue 07-01-25 | 95 days | Tue 01-10-24 | Mon 31-03-25 | Tue 01-10-24 | Mon 31-03-25 | 175.38 days | 100%
DPR / Financial / Land details | Tue 01-10-24 | Fri 13-12-24 | 72 days | Tue 01-10-24 | Mon 31-03-25 | Tue 01-10-24 | Mon 31-03-25 | 175.38 days | 100%
Project Requisition | Tue 01-10-24 | Tue 08-10-24 | 7 days | Tue 01-10-24 | Tue 08-10-24 | Tue 01-10-24 | Tue 08-10-24 | 7.75 days | 100% |  | 5
Process Flow Diagram | Tue 08-10-24 | Tue 15-10-24 | 7 days | Tue 08-10-24 | Tue 15-10-24 | Tue 08-10-24 | Tue 15-10-24 | 7.75 days | 100% | 4 | 6,8
Capacity Finalisation | Tue 15-10-24 | Tue 22-10-24 | 7 days | Tue 15-10-24 | Tue 22-10-24 | Tue 15-10-24 | Tue 22-10-24 | 7.75 days | 100% | 5 | 50,56,7
Tentative Budget | Tue 22-10-24 | Tue 29-10-24 | 7 days | Tue 22-10-24 | Tue 29-10-24 | Tue 22-10-24 | Tue 29-10-24 | 7.75 days | 100% | 6 | 9
Environment Impact Assessment (EIA) | Tue 15-10-24 | Tue 22-10-24 | 7 days | Tue 15-10-24 | Tue 22-10-24 | Tue 15-10-24 | Tue 22-10-24 | 7.75 days | 100% | 5 | 9
Preparation of Detailed Project Report | Tue 29-10-24 | Wed 06-11-24 | 7 days | Tue 29-10-24 | Wed 06-11-24 | Tue 29-10-24 | Wed 06-11-24 | 8.88 days | 100% | 7,8 | 10,13
CAPEX Committee/ Board Approval | Wed 06-11-24 | Wed 13-11-24 | 7 days | Wed 06-11-24 | Wed 13-11-24 | Wed 06-11-24 | Wed 13-11-24 | 7.75 days | 100% | 9 | 11
Project Code / IO Code creation in SAP | Wed 13-11-24 | Wed 20-11-24 | 7 days | Wed 13-11-24 | Wed 20-11-24 | Wed 13-11-24 | Wed 20-11-24 | 7.75 days | 100% | 10 | 12
PE Internal Funding | Wed 20-11-24 | Wed 27-11-24 | 7 days | Wed 20-11-24 | Wed 27-11-24 | Wed 20-11-24 | Wed 27-11-24 | 7.75 days | 100% | 11 | 15
Identification of Land | Wed 06-11-24 | Thu 21-11-24 | 15 days | Wed 06-11-24 | Thu 21-11-24 | Wed 06-11-24 | Thu 21-11-24 | 15.63 days | 100% | 9 | 14,17,18,19
Land Settlement Payout/Final land payment | Thu 21-11-24 | Fri 06-12-24 | 15 days | Thu 21-11-24 | Fri 06-12-24 | Thu 21-11-24 | Fri 06-12-24 | 15.63 days | 100% | 13 | 15,22,23,24
Final Sale Agreement/Lease Deed | Fri 06-12-24 | Fri 13-12-24 | 7 days | Sat 01-03-25 | Mon 31-03-25 | Sat 01-03-25 | Mon 31-03-25 | 29.13 days | 100% | 12,14 | 26
Feasibility Study | Thu 21-11-24 | Tue 07-01-25 | 45 days | Sat 01-03-25 | Thu 20-03-25 | Sat 01-03-25 | Thu 20-03-25 | 19 days | 100%
Topography Study | Thu 21-11-24 | Fri 06-12-24 | 15 days | Sat 01-03-25 | Thu 20-03-25 | Sat 01-03-25 | Thu 20-03-25 | 19 days | 100% | 13
Geotechnical Investigation | Fri 06-12-24 | Mon 23-12-24 | 15 days | Sat 01-03-25 | Thu 20-03-25 | Sat 01-03-25 | Thu 20-03-25 | 0 days | 100% | 13
Drain Study | Mon 23-12-24 | Tue 07-01-25 | 15 days | Sat 01-03-25 | Thu 20-03-25 | Sat 01-03-25 | Thu 20-03-25 | 0 days | 100% | 13 | 56,60
Licensing & Approvals | Fri 06-12-24 | Tue 30-06-26 | 550 days | Fri 06-12-24 | NA | Fri 06-12-24 | Tue 30-06-26 | 549.75 days | 23%
License & Drawing - Pre - approvals | Fri 06-12-24 | Mon 12-05-25 | 150 days | Fri 06-12-24 | NA | Fri 06-12-24 | Mon 02-02-26 | 407.38 days | 32%
Environmental Clearance | Fri 06-12-24 | Tue 07-01-25 | 30 days | Fri 06-12-24 | Tue 07-01-25 | Fri 06-12-24 | Tue 07-01-25 | 30 days | 100% | 14 | 38
NOC from AAI | Fri 06-12-24 | Tue 07-01-25 | 30 days | Fri 06-12-24 | Tue 07-01-25 | Fri 06-12-24 | Tue 07-01-25 | 30 days | 100% | 14 | 38
Construction Power approval 33kVA/11kVA | Fri 06-12-24 | Tue 07-01-25 | 30 days | Fri 20-06-25 | Fri 24-10-25 | Fri 20-06-25 | Fri 24-10-25 | 122.63 days | 100% | 14 | 38
HARA Study | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 16-06-25 | Tue 15-07-25 | Mon 16-06-25 | Tue 15-07-25 | 29.13 days | 100% | 57 | 38
Building Permit (SMP, Building Layouts, Section& Elevation View) | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 02-06-25 | NA | Mon 02-06-25 | Wed 02-07-25 | 30 days | 0% | 57,15 | 38
BOCW Registeration ( Building and Other Construction Workers ) | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 02-06-25 | NA | Mon 02-06-25 | Wed 02-07-25 | 30 days | 0% | 57 | 38
Consent for Establishment (CFE) - Pollution Control Board (PCB) - Ammendement | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 31-03-25 | Wed 30-04-25 | Mon 31-03-25 | Wed 30-04-25 | 30 days | 100% | 57 | 38
HAZOP Study | Fri 07-02-25 | Mon 10-03-25 | 30 days | Fri 20-06-25 | Tue 15-07-25 | Fri 20-06-25 | Tue 15-07-25 | 24.63 days | 100% | 57 | 38
Fire Plan approval | Fri 07-02-25 | Mon 12-05-25 | 90 days | Tue 07-10-25 | NA | Tue 07-10-25 | Wed 07-01-26 | 90 days | 0% | 57 | 38
Factory Plan Approval | Fri 07-02-25 | Mon 12-05-25 | 90 days | Mon 02-06-25 | NA | Mon 02-06-25 | Tue 02-09-25 | 90 days | 0% | 57 | 38
Electricity Load Sanction Approval | Fri 07-02-25 | Mon 10-03-25 | 30 days | Thu 01-05-25 | Mon 30-06-25 | Thu 01-05-25 | Mon 30-06-25 | 58.38 days | 100% | 57 | 38
CEIG Drawing approval | Fri 07-02-25 | Mon 12-05-25 | 90 days | Tue 07-10-25 | NA | Tue 07-10-25 | Wed 07-01-26 | 90 days | 0% | 57 | 38
Ground water Department Approval ( Borewell) | Fri 07-02-25 | Mon 12-05-25 | 90 days | Thu 15-05-25 | NA | Thu 15-05-25 | Fri 15-08-25 | 90 days | 0% | 57 | 38
New Water connection& approval | Fri 07-02-25 | Mon 12-05-25 | 90 days | Mon 06-10-25 | NA | Mon 06-10-25 | Tue 06-01-26 | 90 days | 0% | 57 | 38
PESO Drawing Approval | Fri 07-02-25 | Mon 12-05-25 | 90 days | Mon 06-10-25 | NA | Mon 06-10-25 | Tue 06-01-26 | 90 days | 0% | 57 | 38
MOOWRS Drawings Approval | Fri 07-02-25 | Mon 12-05-25 | 90 days | Sat 01-11-25 | NA | Sat 01-11-25 | Mon 02-02-26 | 90 days | 0% | 57 | 13821389
License & Drawing Completion - Milestone | Mon 12-05-25 | Mon 12-05-25 | 0 days | NA | NA | Wed 07-01-26 | Wed 07-01-26 | 0 days | 0% | 22,23,24,25,26,27,28,29,30,31,32,33,34,35,36
License - Post-Construction approvals | Wed 29-04-26 | Tue 30-06-26 | 60 days | NA | NA | Wed 29-04-26 | Tue 30-06-26 | 60 days | 0%
Fire Approval License | Wed 29-04-26 | Tue 30-06-26 | 60 days | NA | NA | Wed 29-04-26 | Tue 30-06-26 | 60 days | 0% | 1662FF | 47
Factory License | Wed 29-04-26 | Tue 30-06-26 | 60 days | NA | NA | Wed 29-04-26 | Tue 30-06-26 | 60 days | 0% | 1662FF | 47
CEIG Approval License | Wed 29-04-26 | Tue 30-06-26 | 60 days | NA | NA | Wed 29-04-26 | Tue 30-06-26 | 60 days | 0% | 1662FF | 47
Water release Approval License | Wed 29-04-26 | Tue 30-06-26 | 60 days | NA | NA | Wed 29-04-26 | Tue 30-06-26 | 60 days | 0% | 1662FF | 47
PESO Licence | Wed 29-04-26 | Tue 30-06-26 | 60 days | NA | NA | Wed 29-04-26 | Tue 30-06-26 | 60 days | 0% | 1662FF | 47
MOOWRS License | Wed 29-04-26 | Tue 30-06-26 | 60 days | NA | NA | Wed 29-04-26 | Tue 30-06-26 | 60 days | 0% | 1662FF | 47
Consent for Operation License | Wed 29-04-26 | Tue 30-06-26 | 60 days | NA | NA | Wed 29-04-26 | Tue 30-06-26 | 60 days | 0% | 1662FF | 47
Post Construction Approval & Licenses - Milestone | Tue 30-06-26 | Tue 30-06-26 | 0 days | NA | NA | Tue 30-06-26 | Tue 30-06-26 | 0 days | 0% | 40,41,42,43,44,45,46
Basic Engineering | Tue 22-10-24 | Sat 22-02-25 | 119 days | Sun 02-02-25 | Mon 04-08-25 | Sun 02-02-25 | Mon 04-08-25 | 176.5 days | 100%
Process Tool | Tue 22-10-24 | Wed 08-01-25 | 75 days | Sun 02-02-25 | Mon 04-08-25 | Sun 02-02-25 | Mon 04-08-25 | 176.5 days | 100%
Receipt of Offers | Tue 22-10-24 | Wed 06-11-24 | 15 days | Sun 02-02-25 | Mon 10-02-25 | Sun 02-02-25 | Mon 10-02-25 | 7.75 days | 100% | 6 | 51
Technical Evaluation | Thu 07-11-24 | Fri 22-11-24 | 15 days | Mon 10-02-25 | Sun 16-02-25 | Mon 10-02-25 | Sun 16-02-25 | 5.75 days | 100% | 50 | 5213781385
Process Flow Diagram Based on Equipment Selection | Fri 22-11-24 | Sat 07-12-24 | 15 days | Mon 17-02-25 | Tue 18-02-25 | Mon 17-02-25 | Tue 18-02-25 | 2.13 days | 100% | 51 | 5313791386
Equipment Selection& List | Sat 07-12-24 | Mon 23-12-24 | 15 days | Thu 20-02-25 | Mon 24-02-25 | Thu 20-02-25 | Mon 24-02-25 | 4.38 days | 100% | 52 | 54
Field Utility Matrix (FUM) | Tue 24-12-24 | Wed 08-01-25 | 15 days | Tue 25-02-25 | Thu 27-02-25 | Tue 25-02-25 | Thu 27-02-25 | 3.25 days | 100% | 53 | 57,721,709,733,745,754,766,778,791,815,827,840,864,877,889,901,913,925,938,950,962,975,987,999,1011,1024,1036,1048,1060,1073,1085,1097,1109,1121,1133,55
FUM Revision | NA | NA | 0 days? | Sun 01-06-25 | Mon 04-08-25 | Sun 01-06-25 | Mon 04-08-25 | 61.75 days | 100% | 54 | 2.8333e+174
Site Master Plan Finalization (SMP) | Tue 07-01-25 | Wed 22-01-25 | 15 days | Sat 01-03-25 | Mon 10-03-25 | Sat 01-03-25 | Mon 10-03-25 | 0 days | 100% | 19,6 | 5.7638e+50
Factory Architectural Buildings Layout | Wed 22-01-25 | Fri 07-02-25 | 15 days | Tue 11-03-25 | Sun 30-03-25 | Tue 11-03-25 | Sun 30-03-25 | 19.13 days | 100% | 54,56 | 5.8784e+96
Single Line Drawing (SLD Electrical - HV System) | Fri 07-02-25 | Sat 22-02-25 | 15 days | Sun 01-06-25 | Mon 30-06-25 | Sun 01-06-25 | Mon 30-06-25 | 28 days | 100% | 57 | 1.1421e+82
Site Readiness Activity / Mobilization | Tue 07-01-25 | Wed 26-03-25 | 75 days | Thu 01-05-25 | Mon 10-11-25 | Thu 01-05-25 | Mon 10-11-25 | 186.63 days | 100%
Jungle / Bush Clearance | Tue 07-01-25 | Wed 22-01-25 | 15 days | Thu 01-05-25 | Sat 10-05-25 | Thu 01-05-25 | Sat 10-05-25 | 10 days | 100% | 19 | 61,62
Land Leveling & Grading | Wed 22-01-25 | Wed 26-03-25 | 60 days | Wed 07-05-25 | Fri 30-05-25 | Wed 07-05-25 | Fri 30-05-25 | 19.13 days | 100% | 60 | 64SS+15 days,65SS+15 days,67SS+15 days,68SS+15 days,69SS+15 days,70SS+15 days,72SS+15 days,73SS+15 days,66SS+15 days,71SS+15 days,74SS+15 days
Signages | Wed 22-01-25 | Sat 22-02-25 | 30 days | Mon 02-06-25 | Mon 30-06-25 | Mon 02-06-25 | Mon 30-06-25 | 28 days | 100% | 60 | 75
Temporary Power Connection | Wed 22-01-25 | Sat 22-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 56 | 64SS+7 days,65SS+7 days,67SS+7 days,68SS+7 days,69SS+7 days,70SS+7 days,72SS+7 days,73SS+7 days,66SS+7 days,71SS+7 days,74SS+7 days
Temporary Area Lighting | Fri 07-02-25 | Wed 26-03-25 | 45 days | Fri 30-05-25 | Sat 30-08-25 | Fri 30-05-25 | Sat 30-08-25 | 89.88 days | 100% | 63SS+7 days,61SS+15 days | 75
Temporary CCTV | Fri 07-02-25 | Wed 26-03-25 | 45 days | Fri 30-05-25 | Sat 30-08-25 | Fri 30-05-25 | Sat 30-08-25 | 89.88 days | 100% | 63SS+7 days,61SS+15 days | 75
Temporary RO & Softner Plant | Fri 07-02-25 | Wed 26-03-25 | 45 days | Thu 07-08-25 | Sat 30-08-25 | Thu 07-08-25 | Sat 30-08-25 | 23.5 days | 100% | 63SS+7 days,61SS+15 days | 75
Project Team - Guest House & Accomodation | Fri 07-02-25 | Wed 26-03-25 | 45 days | Fri 30-05-25 | Mon 30-06-25 | Fri 30-05-25 | Mon 30-06-25 | 30.25 days | 100% | 63SS+7 days,61SS+15 days | 75
Project Team - Site Transportation | Fri 07-02-25 | Mon 10-03-25 | 30 days | Fri 30-05-25 | Mon 30-06-25 | Fri 30-05-25 | Mon 30-06-25 | 30.25 days | 100% | 63SS+7 days,61SS+15 days | 75
Project Team - PPE Kit | Fri 07-02-25 | Wed 26-03-25 | 45 days | Fri 30-05-25 | Thu 05-06-25 | Fri 30-05-25 | Thu 05-06-25 | 6.63 days | 100% | 63SS+7 days,61SS+15 days | 75
Project Team - Internet & Communication Setup | Fri 07-02-25 | Wed 26-03-25 | 45 days | Fri 30-05-25 | Mon 30-06-25 | Fri 30-05-25 | Mon 30-06-25 | 30.25 days | 100% | 63SS+7 days,61SS+15 days | 75
Site Office Porta Cabins, Security Cabins | Fri 07-02-25 | Wed 26-03-25 | 45 days | Fri 30-05-25 | Sun 15-06-25 | Fri 30-05-25 | Sun 15-06-25 | 15.75 days | 100% | 63SS+7 days,61SS+15 days | 75
Quality Control Lab | Fri 07-02-25 | Wed 26-03-25 | 45 days | Fri 30-05-25 | Thu 05-06-25 | Fri 30-05-25 | Thu 05-06-25 | 6.63 days | 100% | 63SS+7 days,61SS+15 days | 75
Environmental Social & Goveranace | Fri 07-02-25 | Thu 20-03-25 | 2 mons | Thu 07-08-25 | Mon 10-11-25 | Thu 07-08-25 | Mon 10-11-25 | 4.61 mons | 100% | 63SS+7 days,61SS+15 days | 75
Borwell Installation | Fri 07-02-25 | Thu 20-03-25 | 2 mons | Thu 05-06-25 | Tue 30-09-25 | Thu 05-06-25 | Tue 30-09-25 | 5.68 mons | 100% | 63SS+7 days,61SS+15 days | 75
Site Readiness Completion - Milestone | NA | NA | 0 days | Mon 10-11-25 | Mon 10-11-25 | Mon 10-11-25 | Mon 10-11-25 | 0 days | 100% | 64,65,66,67,68,69,70,71,72,73,74,62
Building | Fri 07-02-25 | Fri 19-12-25 | 304 days | Thu 17-10-24 | NA | Thu 17-10-24 | Fri 05-06-26 | 575.38 days | 23%
Main Building - Phase 1 | Fri 07-02-25 | Tue 18-11-25 | 274 days | Thu 17-10-24 | NA | Thu 17-10-24 | Mon 29-12-25 | 422.88 days | 69%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 31-03-25 | Tue 15-04-25 | Mon 31-03-25 | Tue 15-04-25 | 15.63 days | 100% | 57 | 80,86
Order for PEB | Mon 10-03-25 | Fri 09-05-25 | 58 days | Thu 01-05-25 | Mon 16-06-25 | Thu 01-05-25 | Mon 16-06-25 | 44.88 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Thu 01-05-25 | Sat 03-05-25 | Thu 01-05-25 | Sat 03-05-25 | 3.25 days | 100% | 78 | 81
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Sat 03-05-25 | Sat 10-05-25 | Sat 03-05-25 | Sat 10-05-25 | 6.75 days | 100% | 80 | 82
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Mon 12-05-25 | Fri 16-05-25 | Mon 12-05-25 | Fri 16-05-25 | 5.5 days | 100% | 81 | 83
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Mon 19-05-25 | Sat 24-05-25 | Mon 19-05-25 | Sat 24-05-25 | 6.63 days | 100% | 82 | 84
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | Mon 26-05-25 | Mon 16-06-25 | Mon 26-05-25 | Mon 16-06-25 | 21.25 days | 100% | 83 | 94103110117124
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | Thu 01-05-25 | Mon 16-06-25 | Thu 01-05-25 | Mon 16-06-25 | 44.88 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Thu 01-05-25 | Sat 03-05-25 | Thu 01-05-25 | Sat 03-05-25 | 3.25 days | 100% | 78 | 87
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Sat 03-05-25 | Sat 10-05-25 | Sat 03-05-25 | Sat 10-05-25 | 7.75 days | 100% | 86 | 88
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Mon 12-05-25 | Fri 16-05-25 | Mon 12-05-25 | Fri 16-05-25 | 5.5 days | 100% | 87 | 89
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Mon 19-05-25 | Sat 24-05-25 | Mon 19-05-25 | Sat 24-05-25 | 6.63 days | 100% | 88 | 90
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Mon 26-05-25 | Mon 16-06-25 | Mon 26-05-25 | Mon 16-06-25 | 21.25 days | 100% | 89 | 91SS+7 days
Transporation in Multiple Lot for Civil | Tue 15-04-25 | Thu 18-09-25 | 150 days | Sun 01-06-25 | NA | Sun 01-06-25 | Tue 04-11-25 | 150 days | 90% | 90SS+7 days | 92SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Tue 24-06-25 | 60 days | Thu 05-06-25 | Sat 26-07-25 | Thu 05-06-25 | Sat 26-07-25 | 46.88 days | 100% | 91SS+7 days | 95,93
Brick block work ( side walls) | Tue 24-06-25 | Fri 25-07-25 | 30 days | Fri 27-06-25 | NA | Fri 27-06-25 | Wed 27-08-25 | 30 days | 80% | 92 | 97SS+15 days
Transporation in Multiple Lot for PEB | Fri 09-05-25 | Mon 11-08-25 | 90 days | Fri 04-07-25 | Thu 20-11-25 | Fri 04-07-25 | Thu 20-11-25 | 134.88 days | 100% | 84 | 95SS+7 days
Installation/Erection of Structures on the pedastal | Tue 24-06-25 | Mon 25-08-25 | 60 days | Sun 06-07-25 | Sat 27-09-25 | Sun 06-07-25 | Sat 27-09-25 | 60 days | 100% | 94SS+7 days,92 | 96SS+30 days
Roof sheeting & Wall Clading | Fri 25-07-25 | Thu 25-09-25 | 60 days | Sat 23-08-25 | NA | Sat 23-08-25 | Fri 24-10-25 | 60 days | 85% | 95SS+30 days | 97SS+30 days,99
PCC / Grade slab / Flooring work | Mon 25-08-25 | Mon 27-10-25 | 60 days | Mon 06-10-25 | NA | Mon 06-10-25 | Sat 06-12-25 | 60 days | 60% | 96SS+30 days,93SS+15 days | 98SS+7 days
VDF Flooring | Tue 02-09-25 | Mon 03-11-25 | 60 days | Thu 17-10-24 | NA | Thu 17-10-24 | Sat 13-12-25 | 60 days | 40% | 97SS+7 days | 1.0014e+166
PEB Finishing | Thu 25-09-25 | Fri 10-10-25 | 15 days | NA | NA | Fri 24-10-25 | Sat 08-11-25 | 15 days | 0% | 96 | 101
Painting | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Sat 13-12-25 | Mon 29-12-25 | 15 days | 0% | 98 | 101
Handover - Main Building - Phase 1 | Tue 18-11-25 | Tue 18-11-25 | 0 days | NA | NA | Mon 29-12-25 | Mon 29-12-25 | 0 days | 0% | 100,99
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | Wed 10-09-25 | NA | Wed 10-09-25 | Mon 22-12-25 | 99.38 days | 46%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | Wed 10-09-25 | Thu 25-09-25 | Wed 10-09-25 | Thu 25-09-25 | 15.63 days | 100% | 84 | 104
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | Tue 30-09-25 | Mon 13-10-25 | Tue 30-09-25 | Mon 13-10-25 | 13.38 days | 100% | 103 | 105
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | Thu 06-11-25 | Mon 10-11-25 | Thu 06-11-25 | Mon 10-11-25 | 4.38 days | 100% | 104 | 106
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Mon 10-11-25 | Sat 15-11-25 | 5.5 days | 0% | 105 | 107
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Sat 15-11-25 | Wed 17-12-25 | 30 days | 0% | 106 | 108
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Wed 17-12-25 | Mon 22-12-25 | 4.38 days | 0% | 107 | 1413
Rolling Shutter | Fri 09-05-25 | Thu 24-07-25 | 73 days | Wed 10-09-25 | NA | Wed 10-09-25 | Thu 11-12-25 | 89.88 days | 46%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | Wed 10-09-25 | Thu 25-09-25 | Wed 10-09-25 | Thu 25-09-25 | 15.63 days | 100% | 84 | 111
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | Tue 30-09-25 | Mon 13-10-25 | Tue 30-09-25 | Mon 13-10-25 | 13.38 days | 100% | 110 | 112
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | Wed 15-10-25 | Sat 18-10-25 | Wed 15-10-25 | Sat 18-10-25 | 4.38 days | 100% | 111 | 113
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | Tue 21-10-25 | Sat 25-10-25 | Tue 21-10-25 | Sat 25-10-25 | 5.5 days | 100% | 112 | 114
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | Sat 25-10-25 | NA | Sat 25-10-25 | Wed 26-11-25 | 30 days | 0% | 113 | 115
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Wed 26-11-25 | Thu 11-12-25 | 15 days | 0% | 114 | 1414
Docklever | Fri 09-05-25 | Thu 24-07-25 | 73 days | Tue 15-07-25 | NA | Tue 15-07-25 | Thu 25-09-25 | 70.88 days | 32%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | Tue 15-07-25 | Fri 18-07-25 | Tue 15-07-25 | Fri 18-07-25 | 4.38 days | 100% | 84 | 118
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | Fri 18-07-25 | Sun 20-07-25 | Fri 18-07-25 | Sun 20-07-25 | 2.25 days | 100% | 117 | 119
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | Mon 21-07-25 | Wed 23-07-25 | Mon 21-07-25 | Wed 23-07-25 | 3.25 days | 100% | 118 | 120
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | Wed 30-07-25 | Sat 09-08-25 | Wed 30-07-25 | Sat 09-08-25 | 11.13 days | 100% | 119 | 121
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | Mon 11-08-25 | NA | Mon 11-08-25 | Wed 10-09-25 | 30 days | 0% | 120 | 122
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Wed 10-09-25 | Thu 25-09-25 | 15 days | 0% | 121 | 1415
Lift Material | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Mon 16-06-25 | Sat 30-08-25 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 16-06-25 | Tue 24-06-25 | 7 days | 0% | 84 | 125
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 24-06-25 | Tue 01-07-25 | 7 days | 0% | 124 | 126
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 01-07-25 | Tue 08-07-25 | 7 days | 0% | 125 | 127
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 08-07-25 | Tue 15-07-25 | 7 days | 0% | 126 | 128
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Tue 15-07-25 | Fri 15-08-25 | 30 days | 0% | 127 | 129
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Fri 15-08-25 | Sat 30-08-25 | 15 days | 0% | 128 | 1416
ETP Shed | Fri 07-02-25 | Tue 18-11-25 | 274 days | Mon 31-03-25 | NA | Mon 31-03-25 | Tue 10-03-26 | 332.5 days | 30%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 31-03-25 | Tue 15-04-25 | Mon 31-03-25 | Tue 15-04-25 | 15.63 days | 100% | 57 | 133139
Order for PEB | Mon 10-03-25 | Fri 09-05-25 | 58 days | Sun 01-06-25 | Sat 16-08-25 | Sun 01-06-25 | Sat 16-08-25 | 74.13 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Sun 01-06-25 | Wed 04-06-25 | Sun 01-06-25 | Wed 04-06-25 | 3.25 days | 100% | 131 | 134
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Tue 03-06-25 | Tue 10-06-25 | Tue 03-06-25 | Tue 10-06-25 | 7.75 days | 100% | 133 | 135
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Thu 12-06-25 | Tue 17-06-25 | Thu 12-06-25 | Tue 17-06-25 | 5.5 days | 100% | 134 | 136
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Thu 19-06-25 | Wed 25-06-25 | Thu 19-06-25 | Wed 25-06-25 | 6.63 days | 100% | 135 | 137
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | Sat 26-07-25 | Sat 16-08-25 | Sat 26-07-25 | Sat 16-08-25 | 21.25 days | 100% | 136 | 147156163170177
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | Sun 01-06-25 | Sat 16-08-25 | Sun 01-06-25 | Sat 16-08-25 | 74.13 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Sun 01-06-25 | Wed 04-06-25 | Sun 01-06-25 | Wed 04-06-25 | 3.25 days | 100% | 131 | 140
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Tue 03-06-25 | Tue 10-06-25 | Tue 03-06-25 | Tue 10-06-25 | 7.75 days | 100% | 139 | 141
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Thu 12-06-25 | Tue 17-06-25 | Thu 12-06-25 | Tue 17-06-25 | 5.5 days | 100% | 140 | 142
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Thu 19-06-25 | Wed 25-06-25 | Thu 19-06-25 | Wed 25-06-25 | 6.63 days | 100% | 141 | 143
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Sat 26-07-25 | Sat 16-08-25 | Sat 26-07-25 | Sat 16-08-25 | 21.25 days | 100% | 142 | 144SS+7 days
Transporation in Multiple Lot for Civil | Tue 15-04-25 | Thu 18-09-25 | 150 days | Thu 17-07-25 | NA | Thu 17-07-25 | Mon 05-01-26 | 150 days | 60% | 143SS+7 days | 145SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Tue 24-06-25 | 60 days | Thu 17-07-25 | NA | Thu 17-07-25 | Wed 24-09-25 | 60 days | 60% | 144SS+7 days | 148146
Brick block work ( side walls) | Tue 24-06-25 | Fri 25-07-25 | 30 days | NA | NA | Wed 24-09-25 | Sat 25-10-25 | 30 days | 0% | 145 | 150SS+15 days
Transporation in Multiple Lot for PEB | Fri 09-05-25 | Mon 11-08-25 | 90 days | Thu 16-10-25 | NA | Thu 16-10-25 | Sat 15-11-25 | 30 days | 60% | 137 | 148SS+7 days
Installation/Erection of Structures on the pedastal | Tue 24-06-25 | Mon 25-08-25 | 60 days | Fri 14-11-25 | NA | Fri 14-11-25 | Mon 15-12-25 | 30 days | 5% | 145,147SS+7 days | 149SS+30 days
Roof sheeting & Wall Clading | Fri 25-07-25 | Thu 25-09-25 | 60 days | NA | NA | Mon 15-12-25 | Thu 15-01-26 | 30 days | 0% | 148SS+30 days | 150SS+30 days,152
PCC / Grade slab / Flooring work | Mon 25-08-25 | Mon 27-10-25 | 60 days | NA | NA | Thu 15-01-26 | Sat 14-02-26 | 30 days | 0% | 146SS+15 days,149SS+30 days | 151SS+7 days
VDF Flooring | Tue 02-09-25 | Mon 03-11-25 | 60 days | NA | NA | Thu 22-01-26 | Mon 23-02-26 | 30 days | 0% | 150SS+7 days | 1.5315e+82
PEB Finishing | Thu 25-09-25 | Fri 10-10-25 | 15 days | NA | NA | Thu 15-01-26 | Fri 30-01-26 | 15 days | 0% | 149 | 154
Painting | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Mon 23-02-26 | Tue 10-03-26 | 15 days | 0% | 151 | 154
Handover - ETP Shed | Tue 18-11-25 | Tue 18-11-25 | 0 days | NA | NA | Tue 10-03-26 | Tue 10-03-26 | 0 days | 0% | 152153
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Sat 16-08-25 | Wed 12-11-25 | 83.88 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Sat 16-08-25 | Tue 02-09-25 | 15.63 days | 0% | 137 | 157
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 02-09-25 | Tue 16-09-25 | 13.38 days | 0% | 156 | 158
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 16-09-25 | Sat 20-09-25 | 4.38 days | 0% | 157 | 159
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Sat 20-09-25 | Fri 26-09-25 | 5.5 days | 0% | 158 | 160
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Fri 26-09-25 | Tue 28-10-25 | 30 days | 0% | 159 | 161
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Tue 28-10-25 | Wed 12-11-25 | 15 days | 0% | 160 | 1470
Rolling Shutter | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Sat 16-08-25 | Fri 31-10-25 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Sat 16-08-25 | Mon 25-08-25 | 7 days | 0% | 137 | 164
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Mon 25-08-25 | Mon 01-09-25 | 7 days | 0% | 163 | 165
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Mon 01-09-25 | Mon 08-09-25 | 7 days | 0% | 164 | 166
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Mon 08-09-25 | Mon 15-09-25 | 7 days | 0% | 165 | 167
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Mon 15-09-25 | Thu 16-10-25 | 30 days | 0% | 166 | 168
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Thu 16-10-25 | Fri 31-10-25 | 15 days | 0% | 167 | 1471
Docklever | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Sat 16-08-25 | Fri 31-10-25 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Sat 16-08-25 | Mon 25-08-25 | 7 days | 0% | 137 | 171
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Mon 25-08-25 | Mon 01-09-25 | 7 days | 0% | 170 | 172
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Mon 01-09-25 | Mon 08-09-25 | 7 days | 0% | 171 | 173
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Mon 08-09-25 | Mon 15-09-25 | 7 days | 0% | 172 | 174
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Mon 15-09-25 | Thu 16-10-25 | 30 days | 0% | 173 | 175
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Thu 16-10-25 | Fri 31-10-25 | 15 days | 0% | 174 | 1472
EOT Crane | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Sat 16-08-25 | Fri 31-10-25 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Sat 16-08-25 | Mon 25-08-25 | 7 days | 0% | 137 | 178
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Mon 25-08-25 | Mon 01-09-25 | 7 days | 0% | 177 | 179
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Mon 01-09-25 | Mon 08-09-25 | 7 days | 0% | 178 | 180
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Mon 08-09-25 | Mon 15-09-25 | 7 days | 0% | 179 | 181
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Mon 15-09-25 | Thu 16-10-25 | 30 days | 0% | 180 | 182
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Thu 16-10-25 | Fri 31-10-25 | 15 days | 0% | 181 | 1473
FG/ RM Shed | Fri 07-02-25 | Tue 18-11-25 | 274 days | Mon 02-06-25 | NA | Mon 02-06-25 | Fri 16-01-26 | 221.25 days | 64%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 02-06-25 | Mon 30-06-25 | Mon 02-06-25 | Mon 30-06-25 | 28 days | 100% | 57 | 186192
Order for PEB | Mon 10-03-25 | Fri 09-05-25 | 58 days | Tue 01-07-25 | Wed 20-08-25 | Tue 01-07-25 | Wed 20-08-25 | 49.38 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Tue 01-07-25 | Thu 03-07-25 | Tue 01-07-25 | Thu 03-07-25 | 3.25 days | 100% | 184 | 187
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Fri 04-07-25 | Sat 05-07-25 | Fri 04-07-25 | Sat 05-07-25 | 2.13 days | 100% | 186 | 188
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Sat 05-07-25 | Tue 08-07-25 | Sat 05-07-25 | Tue 08-07-25 | 2.25 days | 100% | 187 | 189
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Thu 10-07-25 | Fri 18-07-25 | Thu 10-07-25 | Fri 18-07-25 | 8.88 days | 100% | 188 | 190
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | Fri 18-07-25 | Wed 20-08-25 | Fri 18-07-25 | Wed 20-08-25 | 31.5 days | 100% | 189 | 200209216223230
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | Tue 01-07-25 | Wed 20-08-25 | Tue 01-07-25 | Wed 20-08-25 | 49.38 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Tue 01-07-25 | Thu 03-07-25 | Tue 01-07-25 | Thu 03-07-25 | 3.25 days | 100% | 184 | 193
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Fri 04-07-25 | Sat 05-07-25 | Fri 04-07-25 | Sat 05-07-25 | 2.13 days | 100% | 192 | 194
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Sat 05-07-25 | Tue 08-07-25 | Sat 05-07-25 | Tue 08-07-25 | 3.25 days | 100% | 193 | 195
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Thu 10-07-25 | Fri 18-07-25 | Thu 10-07-25 | Fri 18-07-25 | 8.88 days | 100% | 194 | 196
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Fri 18-07-25 | Wed 20-08-25 | Fri 18-07-25 | Wed 20-08-25 | 32.5 days | 100% | 195 | 197SS+7 days
Transporation in Multiple Lot for Civil | Tue 15-04-25 | Thu 18-09-25 | 150 days | Fri 18-07-25 | NA | Fri 18-07-25 | Sat 27-12-25 | 150 days | 80% | 196SS+7 days | 198SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Tue 24-06-25 | 60 days | Sun 20-07-25 | Mon 13-10-25 | Sun 20-07-25 | Mon 13-10-25 | 77.25 days | 100% | 197SS+7 days | 201199
Brick block work ( side walls) | Tue 24-06-25 | Fri 25-07-25 | 30 days | Sat 20-09-25 | Thu 13-11-25 | Sat 20-09-25 | Thu 13-11-25 | 30 days | 100% | 198 | 203SS+15 days
Transporation in Multiple Lot for PEB | Fri 09-05-25 | Mon 11-08-25 | 90 days | Sat 04-10-25 | Thu 20-11-25 | Sat 04-10-25 | Thu 20-11-25 | 46 days | 100% | 190 | 201SS+7 days
Installation/Erection of Structures on the pedastal | Tue 24-06-25 | Mon 25-08-25 | 60 days | Mon 13-10-25 | Thu 06-11-25 | Mon 13-10-25 | Thu 06-11-25 | 23.63 days | 100% | 198,200SS+7 days | 202SS+30 days
Roof sheeting & Wall Clading | Fri 25-07-25 | Thu 25-09-25 | 60 days | Sun 23-11-25 | NA | Sun 23-11-25 | Tue 09-12-25 | 15 days | 5% | 201SS+30 days | 203SS+30 days,205
PCC / Grade slab / Flooring work | Mon 25-08-25 | Mon 27-10-25 | 60 days | Fri 21-11-25 | NA | Fri 21-11-25 | Thu 08-01-26 | 15 days | 30% | 199SS+15 days,202SS+30 days | 204SS+7 days
VDF Flooring | Tue 02-09-25 | Mon 03-11-25 | 60 days | NA | NA | Fri 28-11-25 | Sat 13-12-25 | 15 days | 0% | 203SS+7 days | 2.0616e+54
PEB Finishing | Thu 25-09-25 | Fri 10-10-25 | 15 days | NA | NA | Tue 09-12-25 | Wed 24-12-25 | 15 days | 0% | 202 | 207
Painting | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Sat 13-12-25 | Sat 20-12-25 | 7 days | 0% | 204 | 207
Handover - FG/ RM Shed | Tue 18-11-25 | Tue 18-11-25 | 0 days | NA | NA | Wed 24-12-25 | Wed 24-12-25 | 0 days | 0% | 205206
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | Wed 10-09-25 | NA | Wed 10-09-25 | Sat 03-01-26 | 111.5 days | 39%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | Wed 10-09-25 | Thu 25-09-25 | Wed 10-09-25 | Thu 25-09-25 | 15.63 days | 100% | 190 | 210
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | Tue 30-09-25 | Mon 13-10-25 | Tue 30-09-25 | Mon 13-10-25 | 13.38 days | 100% | 209 | 211
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | Thu 06-11-25 | Mon 10-11-25 | Thu 06-11-25 | Mon 10-11-25 | 4.38 days | 100% | 210 | 212
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Mon 10-11-25 | Tue 18-11-25 | 7 days | 0% | 211 | 213
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Tue 18-11-25 | Thu 18-12-25 | 30 days | 0% | 212 | 214
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Thu 18-12-25 | Sat 03-01-26 | 15 days | 0% | 213 | 1585
Rolling Shutter | Fri 09-05-25 | Thu 24-07-25 | 73 days | Wed 10-09-25 | NA | Wed 10-09-25 | Thu 11-12-25 | 89.88 days | 46%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | Wed 10-09-25 | Thu 25-09-25 | Wed 10-09-25 | Thu 25-09-25 | 15.63 days | 100% | 190 | 217
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | Tue 30-09-25 | Mon 13-10-25 | Tue 30-09-25 | Mon 13-10-25 | 13.38 days | 100% | 216 | 218
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | Wed 15-10-25 | Sat 18-10-25 | Wed 15-10-25 | Sat 18-10-25 | 4.38 days | 100% | 217 | 219
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | Tue 21-10-25 | Sat 25-10-25 | Tue 21-10-25 | Sat 25-10-25 | 5.5 days | 100% | 218 | 220
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | Sat 25-10-25 | NA | Sat 25-10-25 | Wed 26-11-25 | 30 days | 0% | 219 | 221
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Wed 26-11-25 | Thu 11-12-25 | 15 days | 0% | 220 | 1586
Docklever | Fri 09-05-25 | Thu 24-07-25 | 73 days | Tue 15-07-25 | NA | Tue 15-07-25 | Thu 25-09-25 | 70.88 days | 32%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | Tue 15-07-25 | Fri 18-07-25 | Tue 15-07-25 | Fri 18-07-25 | 4.38 days | 100% | 190 | 224
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | Fri 18-07-25 | Sun 20-07-25 | Fri 18-07-25 | Sun 20-07-25 | 2.25 days | 100% | 223 | 225
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | Mon 21-07-25 | Wed 23-07-25 | Mon 21-07-25 | Wed 23-07-25 | 3.25 days | 100% | 224 | 226
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | Wed 30-07-25 | Sat 09-08-25 | Wed 30-07-25 | Sat 09-08-25 | 11.13 days | 100% | 225 | 227
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | Mon 11-08-25 | NA | Mon 11-08-25 | Wed 10-09-25 | 30 days | 0% | 226 | 228
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Wed 10-09-25 | Thu 25-09-25 | 15 days | 0% | 227 | 1587
Rack | Fri 09-05-25 | Thu 24-07-25 | 73 days | Tue 04-11-25 | NA | Tue 04-11-25 | Fri 16-01-26 | 71.63 days | 8%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | Tue 04-11-25 | Sat 08-11-25 | Tue 04-11-25 | Sat 08-11-25 | 5.5 days | 100% | 190 | 231
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | Mon 10-11-25 | NA | Mon 10-11-25 | Mon 17-11-25 | 7 days | 0% | 230 | 232
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Mon 17-11-25 | Mon 24-11-25 | 7 days | 0% | 231 | 233
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Mon 24-11-25 | Mon 01-12-25 | 7 days | 0% | 232 | 234
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Mon 01-12-25 | Thu 01-01-26 | 30 days | 0% | 233 | 235
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Thu 01-01-26 | Fri 16-01-26 | 15 days | 0% | 234 | 1588
Scrap Yard | Fri 07-02-25 | Tue 21-10-25 | 247 days | Fri 01-08-25 | NA | Fri 01-08-25 | Thu 12-02-26 | 188.38 days | 28%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Fri 01-08-25 | Thu 21-08-25 | Fri 01-08-25 | Thu 21-08-25 | 20.13 days | 100% | 57 | 239
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | Sun 24-08-25 | Mon 20-10-25 | Sun 24-08-25 | Mon 20-10-25 | 55 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Sun 24-08-25 | Sat 30-08-25 | Sun 24-08-25 | Sat 30-08-25 | 6.63 days | 100% | 237 | 240
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Sat 30-08-25 | Mon 01-09-25 | Sat 30-08-25 | Mon 01-09-25 | 2.13 days | 100% | 239 | 241
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Tue 02-09-25 | Wed 03-09-25 | Tue 02-09-25 | Wed 03-09-25 | 0 days | 100% | 240 | 242
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Fri 05-09-25 | Wed 10-09-25 | Fri 05-09-25 | Wed 10-09-25 | 5.5 days | 100% | 241 | 243
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Sat 30-08-25 | Mon 20-10-25 | Sat 30-08-25 | Mon 20-10-25 | 38.25 days | 100% | 242 | 244SS+7 days,255,262,269,276
Transportation in Multiple Lot for Civil | Tue 15-04-25 | Mon 18-08-25 | 120 days | Wed 10-09-25 | NA | Wed 10-09-25 | Tue 11-11-25 | 60 days | 60% | 243SS+7 days | 245SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Tue 24-06-25 | 60 days | Wed 10-09-25 | Sat 15-11-25 | Wed 10-09-25 | Sat 15-11-25 | 58.13 days | 100% | 244SS+7 days | 246
Slab 1 ( RCC) | Tue 24-06-25 | Tue 15-07-25 | 20 days | Sat 15-11-25 | NA | Sat 15-11-25 | Sat 06-12-25 | 20 days | 10% | 245 | 247248
Slab 2 (RCC) | Tue 15-07-25 | Mon 04-08-25 | 20 days | NA | NA | Sat 06-12-25 | Sat 27-12-25 | 20 days | 0% | 246 | 249
Brick block work ( side walls) - Level 1 | Tue 15-07-25 | Wed 30-07-25 | 15 days | NA | NA | Sat 06-12-25 | Mon 22-12-25 | 15 days | 0% | 246 | 250SS+15 days
Brick block work ( side walls) - Level 2 | Tue 05-08-25 | Wed 20-08-25 | 15 days | NA | NA | Sat 27-12-25 | Mon 12-01-26 | 15 days | 0% | 247 | 250SS
PCC / Grade slab / Flooring work | Tue 05-08-25 | Thu 04-09-25 | 30 days | NA | NA | Sat 27-12-25 | Mon 12-01-26 | 15 days | 0% | 248SS+15 days,249SS | 251SS+15 days
Flooring | Wed 20-08-25 | Fri 19-09-25 | 30 days | NA | NA | Mon 12-01-26 | Wed 28-01-26 | 15 days | 0% | 250SS+15 days | 2.5216e+46
Painting | Sat 20-09-25 | Tue 21-10-25 | 30 days | NA | NA | Wed 28-01-26 | Thu 12-02-26 | 15 days | 0% | 251 | 253
Handover - Scrap Yard - (Admin Building) | Tue 21-10-25 | Tue 21-10-25 | 0 days | NA | NA | Thu 12-02-26 | Thu 12-02-26 | 0 days | 0% | 252
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Mon 20-10-25 | Sat 03-01-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 20-10-25 | Tue 28-10-25 | 7 days | 0% | 243 | 256
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 255 | 257
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 256 | 258
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 11-11-25 | Tue 18-11-25 | 7 days | 0% | 257 | 259
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Tue 18-11-25 | Fri 19-12-25 | 30 days | 0% | 258 | 260
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Fri 19-12-25 | Sat 03-01-26 | 15 days | 0% | 259 | 1599
Rolling Shutter | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Mon 20-10-25 | Sat 03-01-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 20-10-25 | Tue 28-10-25 | 7 days | 0% | 243 | 263
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 262 | 264
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 263 | 265
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 11-11-25 | Tue 18-11-25 | 7 days | 0% | 264 | 266
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Tue 18-11-25 | Fri 19-12-25 | 30 days | 0% | 265 | 267
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Fri 19-12-25 | Sat 03-01-26 | 15 days | 0% | 266 | 1600
Elevator - Human | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Mon 20-10-25 | Sat 03-01-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 20-10-25 | Tue 28-10-25 | 7 days | 0% | 243 | 270
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 269 | 271
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 270 | 272
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 11-11-25 | Tue 18-11-25 | 7 days | 0% | 271 | 273
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Tue 18-11-25 | Fri 19-12-25 | 30 days | 0% | 272 | 274
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Fri 19-12-25 | Sat 03-01-26 | 15 days | 0% | 273 | 1601
Interior | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Mon 20-10-25 | Sat 03-01-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 20-10-25 | Tue 28-10-25 | 7 days | 0% | 243 | 277
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 276 | 278
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 277 | 279
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 11-11-25 | Tue 18-11-25 | 7 days | 0% | 278 | 280
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Tue 18-11-25 | Fri 19-12-25 | 30 days | 0% | 279 | 281
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Fri 19-12-25 | Sat 03-01-26 | 15 days | 0% | 280 | 1602160316041600
Chemical Yard | Fri 07-02-25 | Thu 31-07-25 | 168 days | Mon 04-08-25 | NA | Mon 04-08-25 | Fri 16-01-26 | 160.88 days | 30%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 04-08-25 | Thu 04-09-25 | Mon 04-08-25 | Thu 04-09-25 | 30.38 days | 100% | 57,55 | 285291
Order for PEB | Mon 10-03-25 | Fri 09-05-25 | 58 days | Thu 04-09-25 | Mon 13-10-25 | Thu 04-09-25 | Mon 13-10-25 | 38.13 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Thu 04-09-25 | Tue 09-09-25 | Thu 04-09-25 | Tue 09-09-25 | 5.5 days | 100% | 283 | 286
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Wed 10-09-25 | Mon 15-09-25 | Wed 10-09-25 | Mon 15-09-25 | 5.5 days | 100% | 285 | 287
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Tue 16-09-25 | Thu 25-09-25 | Tue 16-09-25 | Thu 25-09-25 | 10 days | 100% | 286 | 288
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Sat 27-09-25 | Sat 04-10-25 | Sat 27-09-25 | Sat 04-10-25 | 0 days | 100% | 287 | 289
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | Thu 25-09-25 | Mon 13-10-25 | Thu 25-09-25 | Mon 13-10-25 | 7.88 days | 100% | 288 | 299308315322
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | Thu 04-09-25 | Tue 18-11-25 | Thu 04-09-25 | Tue 18-11-25 | 73 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Thu 04-09-25 | Tue 09-09-25 | Thu 04-09-25 | Tue 09-09-25 | 5.5 days | 100% | 283 | 292
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Wed 10-09-25 | Mon 15-09-25 | Wed 10-09-25 | Mon 15-09-25 | 5.5 days | 100% | 291 | 293
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Tue 16-09-25 | Thu 25-09-25 | Tue 16-09-25 | Thu 25-09-25 | 10 days | 100% | 292 | 294
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Sat 27-09-25 | Sat 04-10-25 | Sat 27-09-25 | Sat 04-10-25 | 7.75 days | 100% | 293 | 295
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Thu 25-09-25 | Tue 18-11-25 | Thu 25-09-25 | Tue 18-11-25 | 42.75 days | 100% | 294 | 296SS+7 days
Transportation in Multiple Lot for Civil | Tue 15-04-25 | Thu 17-07-25 | 90 days | Thu 25-09-25 | NA | Thu 25-09-25 | Wed 03-12-25 | 60 days | 30% | 295SS+7 days | 297SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Mon 09-06-25 | 45 days | Sat 25-10-25 | NA | Sat 25-10-25 | Tue 25-11-25 | 30 days | 30% | 296SS+7 days | 300298
Brick block work ( side walls) | Mon 09-06-25 | Wed 09-07-25 | 30 days | NA | NA | Tue 25-11-25 | Wed 10-12-25 | 15 days | 0% | 297 | 302
Transportation in Multiple Lot for PEB | Fri 09-05-25 | Mon 09-06-25 | 30 days | NA | NA | Mon 13-10-25 | Wed 29-10-25 | 15 days | 0% | 289 | 300SS+7 days
Installation/Erection of Structures on the pedastal | Mon 09-06-25 | Tue 24-06-25 | 15 days | NA | NA | Tue 25-11-25 | Wed 10-12-25 | 15 days | 0% | 297,299SS+7 days | 301
Roof sheeting & Wall Clading | Tue 24-06-25 | Wed 09-07-25 | 15 days | NA | NA | Thu 11-12-25 | Fri 26-12-25 | 15 days | 0% | 300 | 302304
PCC / Grade slab / Flooring work | Wed 09-07-25 | Wed 16-07-25 | 7 days | NA | NA | Fri 26-12-25 | Fri 02-01-26 | 7 days | 0% | 298301 | 303SS+7 days
VDF Flooring | Thu 17-07-25 | Thu 24-07-25 | 7 days | NA | NA | Fri 02-01-26 | Fri 09-01-26 | 7 days | 0% | 302SS+7 days | 3.0515e+58
PEB Finishing | Wed 09-07-25 | Wed 16-07-25 | 7 days | NA | NA | Fri 26-12-25 | Fri 02-01-26 | 7 days | 0% | 301 | 306
Painting | Thu 24-07-25 | Thu 31-07-25 | 7 days | NA | NA | Fri 09-01-26 | Fri 16-01-26 | 7 days | 0% | 303 | 306
Handover - Chemical Yard | Thu 31-07-25 | Thu 31-07-25 | 0 days | NA | NA | Fri 16-01-26 | Fri 16-01-26 | 0 days | 0% | 304305
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Mon 13-10-25 | Sat 27-12-25 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 13-10-25 | Tue 21-10-25 | 7 days | 0% | 289 | 309
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 21-10-25 | Tue 28-10-25 | 7 days | 0% | 308 | 310
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 309 | 311
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 310 | 312
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Tue 11-11-25 | Fri 12-12-25 | 30 days | 0% | 311 | 313
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Fri 12-12-25 | Sat 27-12-25 | 15 days | 0% | 312 | 1492
Rolling Shutter | Fri 09-05-25 | Fri 25-07-25 | 74 days | NA | NA | Mon 13-10-25 | Mon 29-12-25 | 74 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 13-10-25 | Tue 21-10-25 | 7 days | 0% | 289 | 316
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 21-10-25 | Tue 28-10-25 | 7 days | 0% | 315 | 317
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 316 | 318
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 317 | 319
Manufacturing Duration | Sat 07-06-25 | Mon 09-06-25 | 1 day | NA | NA | Tue 11-11-25 | Wed 12-11-25 | 1 day | 0% | 318 | 320
Transporation in Multiple Lot | Mon 09-06-25 | Fri 25-07-25 | 45 days | NA | NA | Wed 12-11-25 | Mon 29-12-25 | 45 days | 0% | 319 | 1493
Docklever | Fri 09-05-25 | Fri 25-07-25 | 74 days | NA | NA | Mon 13-10-25 | Mon 29-12-25 | 74 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 13-10-25 | Tue 21-10-25 | 7 days | 0% | 289 | 323
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 21-10-25 | Tue 28-10-25 | 7 days | 0% | 322 | 324
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 323 | 325
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 324 | 326
Manufacturing Duration | Sat 07-06-25 | Mon 09-06-25 | 1 day | NA | NA | Tue 11-11-25 | Wed 12-11-25 | 1 day | 0% | 325 | 327
Transporation in Multiple Lot | Mon 09-06-25 | Fri 25-07-25 | 45 days | NA | NA | Wed 12-11-25 | Mon 29-12-25 | 45 days | 0% | 326 | 1494
Gas Yard | Fri 07-02-25 | Thu 31-07-25 | 168 days | Mon 04-08-25 | NA | Mon 04-08-25 | Thu 22-01-26 | 165.75 days | 30%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 04-08-25 | Thu 04-09-25 | Mon 04-08-25 | Thu 04-09-25 | 31.38 days | 100% | 57,55 | 331337
Order for PEB | Mon 10-03-25 | Fri 09-05-25 | 58 days | Thu 04-09-25 | Mon 13-10-25 | Thu 04-09-25 | Mon 13-10-25 | 38.13 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Thu 04-09-25 | Tue 09-09-25 | Thu 04-09-25 | Tue 09-09-25 | 5.5 days | 100% | 329 | 332
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Wed 10-09-25 | Mon 15-09-25 | Wed 10-09-25 | Mon 15-09-25 | 5.5 days | 100% | 331 | 333
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Tue 16-09-25 | Thu 25-09-25 | Tue 16-09-25 | Thu 25-09-25 | 10 days | 100% | 332 | 334
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Sat 27-09-25 | Sat 04-10-25 | Sat 27-09-25 | Sat 04-10-25 | 7.75 days | 100% | 333 | 335
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | Thu 25-09-25 | Mon 13-10-25 | Thu 25-09-25 | Mon 13-10-25 | 17.88 days | 100% | 334 | 345354361
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | Thu 04-09-25 | Thu 30-10-25 | Thu 04-09-25 | Thu 30-10-25 | 55 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Thu 04-09-25 | Tue 09-09-25 | Thu 04-09-25 | Tue 09-09-25 | 5.5 days | 100% | 329 | 338
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Wed 10-09-25 | Mon 15-09-25 | Wed 10-09-25 | Mon 15-09-25 | 5.5 days | 100% | 337 | 339
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Tue 16-09-25 | Thu 25-09-25 | Tue 16-09-25 | Thu 25-09-25 | 10 days | 100% | 338 | 340
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Sat 27-09-25 | Sat 04-10-25 | Sat 27-09-25 | Sat 04-10-25 | 7.75 days | 100% | 339 | 341
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Thu 25-09-25 | Thu 30-10-25 | Thu 25-09-25 | Thu 30-10-25 | 24.75 days | 100% | 340 | 342SS+7 days
Transportation in Multiple Lot for Civil | Tue 15-04-25 | Thu 17-07-25 | 90 days | Thu 25-09-25 | NA | Thu 25-09-25 | Sat 03-01-26 | 90 days | 30% | 341SS+7 days | 343SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Mon 09-06-25 | 45 days | Wed 15-10-25 | NA | Wed 15-10-25 | Sat 29-11-25 | 45 days | 0% | 342SS+7 days | 346344
Brick block work ( side walls) | Mon 09-06-25 | Wed 09-07-25 | 30 days | NA | NA | Mon 01-12-25 | Wed 31-12-25 | 30 days | 0% | 343 | 348
Transportation in Multiple Lot for PEB | Fri 09-05-25 | Mon 09-06-25 | 30 days | NA | NA | Mon 13-10-25 | Thu 13-11-25 | 30 days | 0% | 335 | 346SS+7 days
Installation/Erection of Structures on the pedastal | Mon 09-06-25 | Tue 24-06-25 | 15 days | NA | NA | Mon 01-12-25 | Tue 16-12-25 | 15 days | 0% | 343,345SS+7 days | 347
Roof sheeting & Wall Clading | Tue 24-06-25 | Wed 09-07-25 | 15 days | NA | NA | Tue 16-12-25 | Wed 31-12-25 | 15 days | 0% | 346 | 348350
PCC / Grade slab / Flooring work | Wed 09-07-25 | Wed 16-07-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 344347 | 349SS+7 days
VDF Flooring | Thu 17-07-25 | Thu 24-07-25 | 7 days | NA | NA | Wed 07-01-26 | Thu 15-01-26 | 7 days | 0% | 348SS+7 days | 3.5115e+58
PEB Finishing | Wed 09-07-25 | Wed 16-07-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 347 | 352
Painting | Thu 24-07-25 | Thu 31-07-25 | 7 days | NA | NA | Thu 15-01-26 | Thu 22-01-26 | 7 days | 0% | 349 | 352
Handover - Gas Yard | Thu 31-07-25 | Thu 31-07-25 | 0 days | NA | NA | Thu 22-01-26 | Thu 22-01-26 | 0 days | 0% | 350351
Fire Door / Emergency | Fri 09-05-25 | Fri 25-07-25 | 74 days | NA | NA | Mon 13-10-25 | Mon 29-12-25 | 74 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 13-10-25 | Tue 21-10-25 | 7 days | 0% | 335 | 355
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 21-10-25 | Tue 28-10-25 | 7 days | 0% | 354 | 356
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 355 | 357
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 356 | 358
Manufacturing Duration | Sat 07-06-25 | Mon 09-06-25 | 1 day | NA | NA | Tue 11-11-25 | Wed 12-11-25 | 1 day | 0% | 357 | 359
Transporation in Multiple Lot | Mon 09-06-25 | Fri 25-07-25 | 45 days | NA | NA | Wed 12-11-25 | Mon 29-12-25 | 45 days | 0% | 358 | 1507
Rolling Shutter | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Mon 13-10-25 | Sat 27-12-25 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Mon 13-10-25 | Tue 21-10-25 | 7 days | 0% | 335 | 362
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Tue 21-10-25 | Tue 28-10-25 | 7 days | 0% | 361 | 363
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Tue 28-10-25 | Tue 04-11-25 | 7 days | 0% | 362 | 364
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Tue 04-11-25 | Tue 11-11-25 | 7 days | 0% | 363 | 365
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Tue 11-11-25 | Fri 12-12-25 | 30 days | 0% | 364 | 366
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Fri 12-12-25 | Sat 27-12-25 | 15 days | 0% | 365 | 1508
PCW Yard | Fri 07-02-25 | Thu 11-09-25 | 209 days | Wed 01-10-25 | NA | Wed 01-10-25 | Mon 27-04-26 | 201 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Wed 01-10-25 | NA | Wed 01-10-25 | Fri 31-10-25 | 30 days | 0% | 57,55 | 370
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | NA | NA | Fri 31-10-25 | Wed 31-12-25 | 58 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 31-10-25 | Fri 07-11-25 | 7 days | 0% | 368 | 371
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Fri 07-11-25 | Sat 15-11-25 | 7 days | 0% | 370 | 372
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Sat 15-11-25 | Sat 22-11-25 | 7 days | 0% | 371 | 373
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Sat 22-11-25 | Sat 29-11-25 | 7 days | 0% | 372 | 374
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Sat 29-11-25 | Wed 31-12-25 | 30 days | 0% | 373 | 375SS+7 days,386,393
Transportation in Multiple Lot for Civil | Tue 15-04-25 | Mon 18-08-25 | 120 days | NA | NA | Sat 06-12-25 | Sat 07-02-26 | 60 days | 0% | 374SS+7 days | 376SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Tue 24-06-25 | 60 days | NA | NA | Mon 15-12-25 | Sat 14-02-26 | 60 days | 0% | 375SS+7 days | 377
Slab 1 ( RCC) | Tue 24-06-25 | Tue 15-07-25 | 20 days | NA | NA | Sat 14-02-26 | Sat 07-03-26 | 20 days | 0% | 376 | 378379
Slab 2 (RCC) | Tue 15-07-25 | Mon 04-08-25 | 20 days | NA | NA | Sat 07-03-26 | Fri 27-03-26 | 20 days | 0% | 377 | 380
Brick block work ( side walls) - Level 1 | Tue 15-07-25 | Wed 30-07-25 | 15 days | NA | NA | Sat 07-03-26 | Mon 23-03-26 | 15 days | 0% | 377 | 381SS+15 days
Brick block work ( side walls) - Level 2 | Tue 05-08-25 | Wed 20-08-25 | 15 days | NA | NA | Fri 27-03-26 | Mon 13-04-26 | 15 days | 0% | 378 | 381SS
PCC / Grade slab / Flooring work | Tue 05-08-25 | Wed 20-08-25 | 15 days | NA | NA | Fri 27-03-26 | Mon 13-04-26 | 15 days | 0% | 379SS+15 days,380SS | 382SS+7 days
VDF Flooring | Tue 12-08-25 | Wed 27-08-25 | 15 days | NA | NA | Sat 04-04-26 | Mon 20-04-26 | 15 days | 0% | 381SS+7 days | 3.8315e+86
Painting | Wed 27-08-25 | Thu 11-09-25 | 15 days | NA | NA | Mon 20-04-26 | Mon 27-04-26 | 7 days | 0% | 382 | 384
Handover - PCW Yard | Thu 11-09-25 | Thu 11-09-25 | 0 days | NA | NA | Mon 27-04-26 | Mon 27-04-26 | 0 days | 0% | 383
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 374 | 387
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 386 | 388
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 387 | 389
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 388 | 390
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 389 | 391
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 390 | 1527
Rolling Shutter | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 374 | 394
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 393 | 395
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 394 | 396
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 395 | 397
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 396 | 398
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 397 | 1528
N2 yard | Fri 07-02-25 | Fri 19-12-25 | 304 days | Wed 01-10-25 | NA | Wed 01-10-25 | Thu 30-04-26 | 204.75 days | 16%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Wed 01-10-25 | Wed 19-11-25 | Wed 01-10-25 | Wed 19-11-25 | 48.25 days | 100% | 57,55 | 402
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Wed 19-11-25 | Tue 02-12-25 | 12 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Wed 19-11-25 | Sat 22-11-25 | 3 days | 0% | 400 | 403
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Sat 22-11-25 | Wed 26-11-25 | 3 days | 0% | 402 | 404
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Wed 26-11-25 | Fri 28-11-25 | 3 days | 0% | 403 | 405
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Fri 28-11-25 | Tue 02-12-25 | 3 days | 0% | 404 | 406
Detail Enginering & Drawing - Civil | Wed 09-07-25 | Sat 09-08-25 | 30 days | NA | NA | Tue 13-01-26 | Tue 20-01-26 | 7 days | 0% | 405,726,714,738,750,759,771,783,796,808,820,832,845,869,882,894,906,918,930,943,955,967,980,992,1004,1016,1029,1041,1053,1065,1078,1090,1102,1114,1126,1138,1147,1159,1171,1183,1195,1207,1220,1230,1242,1254,1266,1278,1290,1302,1315,1327,1339,857,1352,136... | 407415422
Transportation in Multiple Lot for Civil | Sat 09-08-25 | Fri 10-10-25 | 60 days | NA | NA | Tue 20-01-26 | Tue 27-01-26 | 7 days | 0% | 406 | 408SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Sat 16-08-25 | Fri 17-10-25 | 60 days | NA | NA | Wed 28-01-26 | Fri 27-02-26 | 30 days | 0% | 407SS+7 days | 409
Brick block work ( side walls) | Sat 18-10-25 | Mon 03-11-25 | 15 days | NA | NA | Fri 27-02-26 | Sat 14-03-26 | 15 days | 0% | 408 | 410
PCC / Grade slab / Flooring work | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Mon 16-03-26 | Tue 31-03-26 | 15 days | 0% | 409 | 411
VDF Flooring | Tue 18-11-25 | Wed 03-12-25 | 15 days | NA | NA | Tue 31-03-26 | Wed 15-04-26 | 15 days | 0% | 410 | 4.1215e+54
Painting | Thu 04-12-25 | Fri 19-12-25 | 15 days | NA | NA | Wed 15-04-26 | Thu 30-04-26 | 15 days | 0% | 411 | 413
Handover - N2 Yard | Fri 19-12-25 | Fri 19-12-25 | 0 days | NA | NA | Thu 30-04-26 | Thu 30-04-26 | 0 days | 0% | 412
Door / Emergency | Sat 09-08-25 | Fri 24-10-25 | 73 days | NA | NA | Tue 20-01-26 | Mon 06-04-26 | 73 days | 0%
RFQ | Sat 09-08-25 | Sat 16-08-25 | 7 days | NA | NA | Tue 20-01-26 | Tue 27-01-26 | 7 days | 0% | 406 | 416
Offer Receipt | Sat 16-08-25 | Sat 23-08-25 | 7 days | NA | NA | Wed 28-01-26 | Wed 04-02-26 | 7 days | 0% | 415 | 417
PO Release | Sat 23-08-25 | Mon 01-09-25 | 7 days | NA | NA | Wed 04-02-26 | Wed 11-02-26 | 7 days | 0% | 416 | 418
Payment | Mon 01-09-25 | Mon 08-09-25 | 7 days | NA | NA | Wed 11-02-26 | Wed 18-02-26 | 7 days | 0% | 417 | 419
Manufacturing Duration | Mon 08-09-25 | Wed 08-10-25 | 30 days | NA | NA | Wed 18-02-26 | Sat 21-03-26 | 30 days | 0% | 418 | 420
Transporation in Multiple Lot | Thu 09-10-25 | Fri 24-10-25 | 15 days | NA | NA | Sat 21-03-26 | Mon 06-04-26 | 15 days | 0% | 419 | 1553
Rolling Shutter | Sat 09-08-25 | Fri 24-10-25 | 73 days | NA | NA | Tue 20-01-26 | Mon 06-04-26 | 73 days | 0%
RFQ | Sat 09-08-25 | Sat 16-08-25 | 7 days | NA | NA | Tue 20-01-26 | Tue 27-01-26 | 7 days | 0% | 406 | 423
Offer Receipt | Sat 16-08-25 | Sat 23-08-25 | 7 days | NA | NA | Wed 28-01-26 | Wed 04-02-26 | 7 days | 0% | 422 | 424
PO Release | Sat 23-08-25 | Mon 01-09-25 | 7 days | NA | NA | Wed 04-02-26 | Wed 11-02-26 | 7 days | 0% | 423 | 425
Payment | Mon 01-09-25 | Mon 08-09-25 | 7 days | NA | NA | Wed 11-02-26 | Wed 18-02-26 | 7 days | 0% | 424 | 426
Manufacturing Duration | Mon 08-09-25 | Wed 08-10-25 | 30 days | NA | NA | Wed 18-02-26 | Sat 21-03-26 | 30 days | 0% | 425 | 427
Transporation in Multiple Lot | Thu 09-10-25 | Fri 24-10-25 | 15 days | NA | NA | Sat 21-03-26 | Mon 06-04-26 | 15 days | 0% | 426 | 1554
Admin Building (Main Office) | Fri 07-02-25 | Mon 13-10-25 | 239 days | Wed 01-10-25 | NA | Wed 01-10-25 | Fri 05-06-26 | 239 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Wed 01-10-25 | NA | Wed 01-10-25 | Fri 31-10-25 | 30 days | 0% | 57 | 431
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | NA | NA | Fri 31-10-25 | Wed 31-12-25 | 58 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 31-10-25 | Fri 07-11-25 | 7 days | 0% | 429 | 432
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Fri 07-11-25 | Sat 15-11-25 | 7 days | 0% | 431 | 433
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Sat 15-11-25 | Sat 22-11-25 | 7 days | 0% | 432 | 434
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Sat 22-11-25 | Sat 29-11-25 | 7 days | 0% | 433 | 435
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Sat 29-11-25 | Wed 31-12-25 | 30 days | 0% | 434 | 436SS+7 days,447,454,461
Transportation in Multiple Lot for Civil | Tue 15-04-25 | Mon 18-08-25 | 120 days | NA | NA | Sat 06-12-25 | Tue 10-03-26 | 90 days | 0% | 435SS+7 days | 437SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Tue 24-06-25 | 60 days | NA | NA | Mon 15-12-25 | Sat 14-02-26 | 60 days | 0% | 436SS+7 days | 438
Slab 1 ( RCC) | Tue 24-06-25 | Tue 15-07-25 | 20 days | NA | NA | Sat 14-02-26 | Sat 07-03-26 | 20 days | 0% | 437 | 439440
Slab 2 (RCC) | Tue 15-07-25 | Mon 04-08-25 | 20 days | NA | NA | Sat 07-03-26 | Fri 27-03-26 | 20 days | 0% | 438 | 441
Brick block work ( side walls) - Level 1 | Wed 20-08-25 | Thu 04-09-25 | 15 days | NA | NA | Mon 13-04-26 | Tue 28-04-26 | 15 days | 0% | 438441 | 442SS+15 days
Brick block work ( side walls) - Level 2 | Tue 05-08-25 | Wed 20-08-25 | 15 days | NA | NA | Fri 27-03-26 | Mon 13-04-26 | 15 days | 0% | 439 | 440
PCC / Grade slab / Flooring work | Thu 04-09-25 | Fri 19-09-25 | 15 days | NA | NA | Tue 28-04-26 | Wed 13-05-26 | 15 days | 0% | 440SS+15 days | 443SS+7 days
VDF Flooring | Thu 11-09-25 | Sat 27-09-25 | 15 days | NA | NA | Tue 05-05-26 | Thu 21-05-26 | 15 days | 0% | 442SS+7 days | 4.4416e+42
Painting | Sat 27-09-25 | Mon 13-10-25 | 15 days | NA | NA | Thu 21-05-26 | Fri 05-06-26 | 15 days | 0% | 443 | 445
Handover Structure - Admin Building (Main Office) | Mon 13-10-25 | Mon 13-10-25 | 0 days | NA | NA | Fri 05-06-26 | Fri 05-06-26 | 0 days | 0% | 444
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 435 | 448
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 447 | 449
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 448 | 450
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 449 | 451
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 450 | 452
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 451 | 1611
Elevator - Human | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 435 | 455
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 454 | 456
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 455 | 457
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 456 | 458
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 457 | 459
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 458 | 1612
Interior | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 435 | 462
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 461 | 463
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 462 | 464
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 463 | 465
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 464 | 466
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 465 | 1613
Canteen Building | Fri 07-02-25 | Thu 31-07-25 | 168 days | Wed 01-10-25 | NA | Wed 01-10-25 | Tue 24-03-26 | 168 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Wed 01-10-25 | NA | Wed 01-10-25 | Fri 31-10-25 | 30 days | 0% | 57 | 470476598630
Order for PEB | Mon 10-03-25 | Fri 09-05-25 | 58 days | NA | NA | Fri 31-10-25 | Wed 31-12-25 | 58 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 31-10-25 | Fri 07-11-25 | 7 days | 0% | 468 | 471
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Fri 07-11-25 | Sat 15-11-25 | 7 days | 0% | 470 | 472
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Sat 15-11-25 | Sat 22-11-25 | 7 days | 0% | 471 | 473
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Sat 22-11-25 | Sat 29-11-25 | 7 days | 0% | 472 | 474
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Sat 29-11-25 | Wed 31-12-25 | 30 days | 0% | 473 | 484493500
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | NA | NA | Fri 31-10-25 | Wed 31-12-25 | 58 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 31-10-25 | Fri 07-11-25 | 7 days | 0% | 468 | 477
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Fri 07-11-25 | Sat 15-11-25 | 7 days | 0% | 476 | 478
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Sat 15-11-25 | Sat 22-11-25 | 7 days | 0% | 477 | 479
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Sat 22-11-25 | Sat 29-11-25 | 7 days | 0% | 478 | 480
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Sat 29-11-25 | Wed 31-12-25 | 30 days | 0% | 479 | 481SS+7 days
Transportation in Multiple Lot for Civil | Tue 15-04-25 | Thu 17-07-25 | 90 days | NA | NA | Sat 06-12-25 | Tue 10-03-26 | 90 days | 0% | 480SS+7 days | 482SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Mon 09-06-25 | 45 days | NA | NA | Mon 15-12-25 | Thu 29-01-26 | 45 days | 0% | 481SS+7 days | 485483
Brick block work ( side walls) | Mon 09-06-25 | Wed 09-07-25 | 30 days | NA | NA | Fri 30-01-26 | Mon 02-03-26 | 30 days | 0% | 482 | 487
Transportation in Multiple Lot for PEB | Fri 09-05-25 | Mon 09-06-25 | 30 days | NA | NA | Wed 31-12-25 | Fri 30-01-26 | 30 days | 0% | 474602634 | 485SS+7 days
Installation/Erection of Structures on the pedastal | Mon 09-06-25 | Tue 24-06-25 | 15 days | NA | NA | Fri 30-01-26 | Sat 14-02-26 | 15 days | 0% | 482,484SS+7 days | 486
Roof sheeting & Wall Clading | Tue 24-06-25 | Wed 09-07-25 | 15 days | NA | NA | Sat 14-02-26 | Mon 02-03-26 | 15 days | 0% | 485 | 487489
PCC / Grade slab / Flooring work | Wed 09-07-25 | Wed 16-07-25 | 7 days | NA | NA | Mon 02-03-26 | Mon 09-03-26 | 7 days | 0% | 483486 | 488SS+7 days
VDF Flooring | Thu 17-07-25 | Thu 24-07-25 | 7 days | NA | NA | Mon 09-03-26 | Tue 17-03-26 | 7 days | 0% | 487SS+7 days | 4.9016e+34
PEB Finishing | Wed 09-07-25 | Wed 16-07-25 | 7 days | NA | NA | Mon 02-03-26 | Mon 09-03-26 | 7 days | 0% | 486 | 491
Painting | Thu 24-07-25 | Thu 31-07-25 | 7 days | NA | NA | Tue 17-03-26 | Tue 24-03-26 | 7 days | 0% | 488 | 491
Handover Structure - Canteen Building | Thu 31-07-25 | Thu 31-07-25 | 0 days | NA | NA | Tue 24-03-26 | Tue 24-03-26 | 0 days | 0% | 489490
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 474602634 | 494
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 493 | 495
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 494 | 496
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 495 | 497
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 496 | 498
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 497 | 1622
Interior | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 474602634 | 501
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 500 | 502
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 501 | 503
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 502 | 504
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 503 | 505
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 504 | 1623
Security / HR / Creche / OHC | Fri 07-02-25 | Mon 13-10-25 | 239 days | Wed 01-10-25 | NA | Wed 01-10-25 | Fri 05-06-26 | 239 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Wed 01-10-25 | NA | Wed 01-10-25 | Fri 31-10-25 | 30 days | 0% | 57 | 509
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | NA | NA | Fri 31-10-25 | Wed 31-12-25 | 58 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 31-10-25 | Fri 07-11-25 | 7 days | 0% | 507 | 510
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Fri 07-11-25 | Sat 15-11-25 | 7 days | 0% | 509 | 511
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Sat 15-11-25 | Sat 22-11-25 | 7 days | 0% | 510 | 512
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Sat 22-11-25 | Sat 29-11-25 | 7 days | 0% | 511 | 513
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Sat 29-11-25 | Wed 31-12-25 | 30 days | 0% | 512 | 514SS+7 days,525,532
Transportation in Multiple Lot for Civil | Tue 15-04-25 | Mon 18-08-25 | 120 days | NA | NA | Sat 06-12-25 | Tue 10-03-26 | 90 days | 0% | 513SS+7 days | 515SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Tue 24-06-25 | 60 days | NA | NA | Mon 15-12-25 | Sat 14-02-26 | 60 days | 0% | 514SS+7 days | 516
Slab 1 ( RCC) | Tue 24-06-25 | Tue 15-07-25 | 20 days | NA | NA | Sat 14-02-26 | Sat 07-03-26 | 20 days | 0% | 515 | 517518
Slab 2 (RCC) | Tue 15-07-25 | Mon 04-08-25 | 20 days | NA | NA | Sat 07-03-26 | Fri 27-03-26 | 20 days | 0% | 516 | 519
Brick block work ( side walls) - Level 1 | Wed 20-08-25 | Thu 04-09-25 | 15 days | NA | NA | Mon 13-04-26 | Tue 28-04-26 | 15 days | 0% | 516519 | 520SS+15 days
Brick block work ( side walls) - Level 2 | Tue 05-08-25 | Wed 20-08-25 | 15 days | NA | NA | Fri 27-03-26 | Mon 13-04-26 | 15 days | 0% | 517 | 518
PCC / Grade slab / Flooring work | Thu 04-09-25 | Fri 19-09-25 | 15 days | NA | NA | Tue 28-04-26 | Wed 13-05-26 | 15 days | 0% | 518SS+15 days | 521SS+7 days
VDF Flooring | Thu 11-09-25 | Sat 27-09-25 | 15 days | NA | NA | Tue 05-05-26 | Thu 21-05-26 | 15 days | 0% | 520SS+7 days | 5.2216e+38
Painting | Sat 27-09-25 | Mon 13-10-25 | 15 days | NA | NA | Thu 21-05-26 | Fri 05-06-26 | 15 days | 0% | 521 | 523
Handover Structure - Security / HR / Creche / OHC | Mon 13-10-25 | Mon 13-10-25 | 0 days | NA | NA | Fri 05-06-26 | Fri 05-06-26 | 0 days | 0% | 522
Fire Door / Emergency | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 513 | 526
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 525 | 527
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 526 | 528
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 527 | 529
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 528 | 530
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 529 | 1631
Interior | Fri 09-05-25 | Thu 24-07-25 | 73 days | NA | NA | Wed 31-12-25 | Tue 17-03-26 | 73 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 31-12-25 | Wed 07-01-26 | 7 days | 0% | 513 | 533
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 07-01-26 | Wed 14-01-26 | 7 days | 0% | 532 | 534
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 533 | 535
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Wed 21-01-26 | Thu 29-01-26 | 7 days | 0% | 534 | 536
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 29-01-26 | Sat 28-02-26 | 30 days | 0% | 535 | 537
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 536 | 1632
Compound Wall | Fri 07-02-25 | Sat 18-10-25 | 245 days | Sun 01-06-25 | NA | Sun 01-06-25 | Sat 21-02-26 | 256 days | 26%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Sun 01-06-25 | Fri 20-06-25 | Sun 01-06-25 | Fri 20-06-25 | 19 days | 100% | 57 | 541
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | Fri 20-06-25 | Wed 30-07-25 | Fri 20-06-25 | Wed 30-07-25 | 39.25 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Fri 20-06-25 | Mon 30-06-25 | Fri 20-06-25 | Mon 30-06-25 | 9 days | 100% | 539 | 542
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Tue 01-07-25 | Fri 04-07-25 | Tue 01-07-25 | Fri 04-07-25 | 4.38 days | 100% | 541 | 543
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Fri 04-07-25 | Thu 17-07-25 | Fri 04-07-25 | Thu 17-07-25 | 12.38 days | 100% | 542 | 544
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Mon 21-07-25 | Wed 30-07-25 | Mon 21-07-25 | Wed 30-07-25 | 10 days | 100% | 543 | 545
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Thu 17-07-25 | Mon 20-10-25 | Thu 17-07-25 | Mon 20-10-25 | 78.75 days | 100% | 544 | 546
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Wed 10-09-25 | 120 days | Thu 17-07-25 | NA | Thu 17-07-25 | Sat 21-02-26 | 120 days | 0% | 545 | 547SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Fri 16-05-25 | Thu 17-07-25 | 60 days | Thu 17-07-25 | NA | Thu 17-07-25 | Wed 24-09-25 | 60 days | 0% | 546SS+7 days | 548SS+30 days,551
Brick block work ( side walls) | Tue 17-06-25 | Mon 18-08-25 | 60 days | Sun 10-08-25 | NA | Sun 10-08-25 | Fri 17-10-25 | 60 days | 0% | 547SS+30 days | 549SS+30 days,551
RCC Wall | Thu 17-07-25 | Thu 18-09-25 | 60 days | Sun 10-08-25 | NA | Sun 10-08-25 | Tue 11-11-25 | 60 days | 0% | 548SS+30 days | 551,550SS+30 days
Fenching | NA | NA | 60 days | NA | NA | Wed 10-09-25 | Tue 11-11-25 | 60 days | 0% | 549SS+30 days | 552
Painting | Thu 18-09-25 | Sat 18-10-25 | 30 days | Sat 11-10-25 | NA | Sat 11-10-25 | Fri 12-12-25 | 30 days | 0% | 548549547 | 552
Handover - Compound Wall | Sat 18-10-25 | Sat 18-10-25 | 0 days | NA | NA | Fri 12-12-25 | Fri 12-12-25 | 0 days | 0% | 551550
Main Building - Phase 2 | Fri 07-02-25 | Tue 18-11-25 | 274 days | Mon 31-03-25 | NA | Mon 31-03-25 | Wed 11-02-26 | 306.63 days | 9%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 31-03-25 | Tue 15-04-25 | Mon 31-03-25 | Tue 15-04-25 | 15.63 days | 100% | 57 | 556562
Order for PEB | Mon 10-03-25 | Fri 09-05-25 | 58 days | NA | NA | Tue 15-04-25 | Sat 14-06-25 | 58 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Tue 15-04-25 | Wed 23-04-25 | 7 days | 0% | 554 | 557
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Wed 23-04-25 | Wed 30-04-25 | 7 days | 0% | 556 | 558
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Wed 30-04-25 | Wed 07-05-25 | 7 days | 0% | 557 | 559
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Wed 07-05-25 | Wed 14-05-25 | 7 days | 0% | 558 | 560
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Wed 14-05-25 | Sat 14-06-25 | 30 days | 0% | 559 | 570
Order for Civil | Mon 10-03-25 | Fri 09-05-25 | 58 days | Mon 26-05-25 | Sat 05-07-25 | Mon 26-05-25 | Sat 05-07-25 | 40.38 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Sun 01-06-25 | Sat 07-06-25 | Sun 01-06-25 | Sat 07-06-25 | 6.63 days | 100% | 554 | 563
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Sat 07-06-25 | Wed 11-06-25 | Sat 07-06-25 | Wed 11-06-25 | 3.38 days | 100% | 562 | 564
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Tue 17-06-25 | Thu 26-06-25 | Tue 17-06-25 | Thu 26-06-25 | 10 days | 100% | 563 | 565
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Sat 28-06-25 | Sat 05-07-25 | Sat 28-06-25 | Sat 05-07-25 | 7.75 days | 100% | 564 | 566
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Mon 26-05-25 | Mon 16-06-25 | Mon 26-05-25 | Mon 16-06-25 | 21.25 days | 100% | 565 | 567SS+7 days
Transportation in Multiple Lot for Civil | Tue 15-04-25 | Thu 18-09-25 | 150 days | Tue 17-06-25 | NA | Tue 17-06-25 | Wed 19-11-25 | 150 days | 0% | 566SS+7 days | 568SS+7 days
Civil Works (Foundation, Column, Plinth, beam and Backfilling) | Wed 23-04-25 | Tue 24-06-25 | 60 days | Thu 17-07-25 | NA | Thu 17-07-25 | Wed 17-09-25 | 60 days | 0% | 567SS+7 days | 571569
Brick block work ( side walls) | Tue 24-06-25 | Fri 25-07-25 | 30 days | NA | NA | Wed 17-09-25 | Fri 17-10-25 | 30 days | 0% | 568 | 573SS+15 days
Transportation in Multiple Lot for PEB | Fri 09-05-25 | Mon 11-08-25 | 90 days | NA | NA | Sat 14-06-25 | Tue 16-09-25 | 90 days | 0% | 560 | 571SS+7 days
Installation/Erection of Structures on the pedastal | Tue 24-06-25 | Mon 25-08-25 | 60 days | NA | NA | Wed 17-09-25 | Tue 18-11-25 | 60 days | 0% | 568,570SS+7 days | 572SS+30 days
Roof sheeting & Wall Clading | Fri 25-07-25 | Thu 25-09-25 | 60 days | NA | NA | Sat 18-10-25 | Fri 19-12-25 | 60 days | 0% | 571SS+30 days | 573SS+30 days,575
PCC / Grade slab / Flooring work | Mon 25-08-25 | Mon 27-10-25 | 60 days | NA | NA | Tue 18-11-25 | Mon 19-01-26 | 60 days | 0% | 569SS+15 days,572SS+30 days | 574SS+7 days
VDF Flooring | Tue 02-09-25 | Mon 03-11-25 | 60 days | NA | NA | Tue 25-11-25 | Tue 27-01-26 | 60 days | 0% | 573SS+7 days | 576
PEB Finishing | Thu 25-09-25 | Fri 10-10-25 | 15 days | NA | NA | Fri 19-12-25 | Sat 03-01-26 | 15 days | 0% | 572 | 577
Painting | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Tue 27-01-26 | Wed 11-02-26 | 15 days | 0% | 574 | 577
Handover Structure | Tue 18-11-25 | Tue 18-11-25 | 0 days | NA | NA | Wed 11-02-26 | Wed 11-02-26 | 0 days | 0% | 575576
Road Network | Fri 07-02-25 | Thu 18-09-25 | 215 days | Mon 01-09-25 | NA | Mon 01-09-25 | Sat 11-04-26 | 215.25 days | 9%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 01-09-25 | Wed 01-10-25 | Mon 01-09-25 | Wed 01-10-25 | 30.25 days | 100% | 57 | 581
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Wed 01-10-25 | Thu 30-10-25 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Wed 01-10-25 | Thu 09-10-25 | 7 days | 0% | 579 | 582
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Thu 09-10-25 | Thu 16-10-25 | 7 days | 0% | 581 | 583
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Thu 16-10-25 | Thu 23-10-25 | 7 days | 0% | 582 | 584
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Thu 23-10-25 | Thu 30-10-25 | 7 days | 0% | 583 | 585
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Thu 30-10-25 | Mon 01-12-25 | 30 days | 0% | 584 | 586
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Wed 10-09-25 | 120 days | NA | NA | Mon 01-12-25 | Sat 04-04-26 | 120 days | 0% | 585 | 587SS+7 days
Civil Works (Land Leveling , GSB , PCC, VDF) | Fri 16-05-25 | Mon 18-08-25 | 90 days | NA | NA | Mon 08-12-25 | Wed 11-03-26 | 90 days | 0% | 586SS+7 days | 588
Road Marking | Mon 18-08-25 | Thu 18-09-25 | 30 days | NA | NA | Wed 11-03-26 | Sat 11-04-26 | 30 days | 0% | 587 | 589
Handover - Road Network | Thu 18-09-25 | Thu 18-09-25 | 0 days | NA | NA | Sat 11-04-26 | Sat 11-04-26 | 0 days | 0% | 588
Parking Network | Fri 07-02-25 | Mon 27-10-25 | 252 days | NA | NA | Mon 31-03-25 | Wed 31-12-25 | 265.75 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | NA | NA | Mon 31-03-25 | Wed 30-04-25 | 30 days | 0% | 57 | 593
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Wed 30-04-25 | Thu 29-05-25 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Wed 30-04-25 | Wed 07-05-25 | 7 days | 0% | 591 | 594
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Wed 07-05-25 | Thu 15-05-25 | 7 days | 0% | 593 | 595
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Thu 15-05-25 | Thu 22-05-25 | 7 days | 0% | 594 | 596
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Thu 22-05-25 | Thu 29-05-25 | 7 days | 0% | 595 | 603
Order for PEB Shed | Mon 10-03-25 | Fri 09-05-25 | 58 days | NA | NA | Fri 31-10-25 | Wed 31-12-25 | 58 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 31-10-25 | Fri 07-11-25 | 7 days | 0% | 468 | 599
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Fri 07-11-25 | Sat 15-11-25 | 7 days | 0% | 598 | 600
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Sat 15-11-25 | Sat 22-11-25 | 7 days | 0% | 599 | 601
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Sat 22-11-25 | Sat 29-11-25 | 7 days | 0% | 600 | 602
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Sat 29-11-25 | Wed 31-12-25 | 30 days | 0% | 601 | 484493500
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Thu 29-05-25 | Mon 30-06-25 | 30 days | 0% | 596 | 604
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Wed 10-09-25 | 120 days | NA | NA | Mon 30-06-25 | Sat 30-08-25 | 60 days | 0% | 603 | 605SS+7 days
Civil Works (Land Leveling , GSB , PCC, VDF) | Fri 16-05-25 | Mon 18-08-25 | 90 days | NA | NA | Mon 07-07-25 | Fri 22-08-25 | 45 days | 0% | 604SS+7 days | 606
Installation/Erection of Structures | Mon 18-08-25 | Thu 18-09-25 | 30 days | NA | NA | Fri 22-08-25 | Tue 23-09-25 | 30 days | 0% | 605 | 607
PEB Shed Finishing | Thu 18-09-25 | Thu 25-09-25 | 7 days | NA | NA | Tue 23-09-25 | Tue 30-09-25 | 7 days | 0% | 606 | 608
Painting | Thu 25-09-25 | Mon 27-10-25 | 30 days | NA | NA | Tue 30-09-25 | Thu 30-10-25 | 30 days | 0% | 607 | 609
Handover - Parking Area | Mon 27-10-25 | Mon 27-10-25 | 0 days | NA | NA | Thu 30-10-25 | Thu 30-10-25 | 0 days | 0% | 608
Strom & Drain Network + Chemical Trench | Fri 07-02-25 | Thu 18-09-25 | 215 days | Mon 01-09-25 | NA | Mon 01-09-25 | Wed 11-03-26 | 185.25 days | 13%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 01-09-25 | Wed 01-10-25 | Mon 01-09-25 | Wed 01-10-25 | 30.25 days | 100% | 57 | 613
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Wed 01-10-25 | Thu 30-10-25 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Wed 01-10-25 | Thu 09-10-25 | 7 days | 0% | 611 | 614
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Thu 09-10-25 | Thu 16-10-25 | 7 days | 0% | 613 | 615
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Thu 16-10-25 | Thu 23-10-25 | 7 days | 0% | 614 | 616
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Thu 23-10-25 | Thu 30-10-25 | 7 days | 0% | 615 | 617
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Thu 30-10-25 | Mon 01-12-25 | 30 days | 0% | 616 | 618
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Wed 10-09-25 | 120 days | NA | NA | Mon 01-12-25 | Sat 31-01-26 | 60 days | 0% | 617 | 619SS+7 days
Civil Works (Land Leveling , GSB , PCC, VDF) | Fri 16-05-25 | Mon 18-08-25 | 90 days | NA | NA | Mon 08-12-25 | Sat 07-02-26 | 60 days | 0% | 618SS+7 days | 620
Finishing | Mon 18-08-25 | Thu 18-09-25 | 30 days | NA | NA | Mon 09-02-26 | Wed 11-03-26 | 30 days | 0% | 619 | 621
Handover - Strom & Drain Network + Chemical Trench | Thu 18-09-25 | Thu 18-09-25 | 0 days | NA | NA | Wed 11-03-26 | Wed 11-03-26 | 0 days | 0% | 620
Bridge Network (Pipe Rack) | Fri 07-02-25 | Sat 02-08-25 | 170 days | NA | NA | Mon 31-03-25 | Wed 31-12-25 | 265.75 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | NA | NA | Mon 31-03-25 | Wed 30-04-25 | 30 days | 0% | 57 | 625
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Wed 30-04-25 | Thu 29-05-25 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Wed 30-04-25 | Wed 07-05-25 | 7 days | 0% | 623 | 626
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Wed 07-05-25 | Thu 15-05-25 | 7 days | 0% | 625 | 627
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Thu 15-05-25 | Thu 22-05-25 | 7 days | 0% | 626 | 628
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Thu 22-05-25 | Thu 29-05-25 | 7 days | 0% | 627 | 635
Order for PEB Structure | Mon 10-03-25 | Fri 09-05-25 | 58 days | NA | NA | Fri 31-10-25 | Wed 31-12-25 | 58 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 31-10-25 | Fri 07-11-25 | 7 days | 0% | 468 | 631
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Fri 07-11-25 | Sat 15-11-25 | 7 days | 0% | 630 | 632
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Sat 15-11-25 | Sat 22-11-25 | 7 days | 0% | 631 | 633
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Sat 22-11-25 | Sat 29-11-25 | 7 days | 0% | 632 | 634
Detail Enginering & Drawing - PEB | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Sat 29-11-25 | Wed 31-12-25 | 30 days | 0% | 633 | 484493500
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Thu 29-05-25 | Mon 30-06-25 | 30 days | 0% | 628 | 636638
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Thu 10-07-25 | 60 days | NA | NA | Mon 30-06-25 | Sat 30-08-25 | 60 days | 0% | 635 | 637SS+7 days
Civil Works (Land Leveling , GSB , PCC, VDF) | Fri 16-05-25 | Thu 17-07-25 | 60 days | NA | NA | Mon 07-07-25 | Sat 06-09-25 | 60 days | 0% | 636SS+7 days,638SS+7 days | 639SS+15 days
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Thu 10-07-25 | 60 days | NA | NA | Mon 30-06-25 | Sat 30-08-25 | 60 days | 0% | 635 | 637SS+7 days,639SS+7 days
Installation/Erection of Structures | Sat 31-05-25 | Sat 02-08-25 | 60 days | NA | NA | Tue 22-07-25 | Tue 23-09-25 | 60 days | 0% | 637SS+15 days,638SS+7 days | 1.5612e+59
Raw Water & Soft Water Tank | Fri 07-02-25 | Wed 10-09-25 | 208 days | NA | NA | Mon 31-03-25 | Sat 06-09-25 | 155 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | NA | NA | Mon 31-03-25 | Wed 30-04-25 | 30 days | 0% | 57 | 643
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Wed 30-04-25 | Thu 29-05-25 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Wed 30-04-25 | Wed 07-05-25 | 7 days | 0% | 641 | 644
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Wed 07-05-25 | Thu 15-05-25 | 7 days | 0% | 643 | 645
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Thu 15-05-25 | Thu 22-05-25 | 7 days | 0% | 644 | 646
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Thu 22-05-25 | Thu 29-05-25 | 7 days | 0% | 645 | 647
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Thu 29-05-25 | Mon 30-06-25 | 30 days | 0% | 646 | 648
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Wed 10-09-25 | 120 days | NA | NA | Mon 30-06-25 | Wed 30-07-25 | 30 days | 0% | 647 | 649SS+7 days
Civil Works Base Work | Fri 16-05-25 | Wed 02-07-25 | 45 days | NA | NA | Mon 07-07-25 | Thu 07-08-25 | 30 days | 0% | 648SS+7 days | 650
Raw Water Tank - Civil Erection & Installation | Wed 02-07-25 | Mon 18-08-25 | 45 days | NA | NA | Thu 07-08-25 | Sat 06-09-25 | 30 days | 0% | 649 | 651
Handover - Raw Water Tank | Mon 18-08-25 | Mon 18-08-25 | 0 days | NA | NA | Sat 06-09-25 | Sat 06-09-25 | 0 days | 0% | 650
DG Yard | Fri 07-02-25 | Wed 10-09-25 | 208 days | Mon 01-09-25 | NA | Mon 01-09-25 | Tue 23-12-25 | 109.5 days | 11%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 01-09-25 | Mon 15-09-25 | Mon 01-09-25 | Mon 15-09-25 | 14.5 days | 100% | 57 | 655
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Mon 15-09-25 | Tue 14-10-25 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Mon 15-09-25 | Tue 23-09-25 | 7 days | 0% | 653 | 656
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Tue 23-09-25 | Tue 30-09-25 | 7 days | 0% | 655 | 657
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Tue 30-09-25 | Tue 07-10-25 | 7 days | 0% | 656 | 658
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Tue 07-10-25 | Tue 14-10-25 | 7 days | 0% | 657 | 659
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Thu 18-09-25 | NA | Thu 18-09-25 | Fri 14-11-25 | 30 days | 0% | 658 | 660
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Wed 10-09-25 | 120 days | NA | NA | Fri 14-11-25 | Tue 16-12-25 | 30 days | 0% | 659 | 661SS+7 days
Civil Works (Foundationand Trench) | Fri 16-05-25 | Mon 18-08-25 | 90 days | NA | NA | Fri 21-11-25 | Tue 23-12-25 | 30 days | 0% | 660SS+7 days | 6621653
DG Yard - Handover | Mon 18-08-25 | Mon 18-08-25 | 0 days | NA | NA | Tue 23-12-25 | Tue 23-12-25 | 0 days | 0% | 661
PNG Gas Yard | Fri 07-02-25 | Tue 17-06-25 | 125 days | NA | NA | Mon 31-03-25 | Thu 07-08-25 | 125 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | NA | NA | Mon 31-03-25 | Wed 30-04-25 | 30 days | 0% | 57 | 666
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Wed 30-04-25 | Thu 29-05-25 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Wed 30-04-25 | Wed 07-05-25 | 7 days | 0% | 664 | 667
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Wed 07-05-25 | Thu 15-05-25 | 7 days | 0% | 666 | 668
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Thu 15-05-25 | Thu 22-05-25 | 7 days | 0% | 667 | 669
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Thu 22-05-25 | Thu 29-05-25 | 7 days | 0% | 668 | 670
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Thu 29-05-25 | Mon 30-06-25 | 30 days | 0% | 669 | 671
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Mon 09-06-25 | 30 days | NA | NA | Mon 30-06-25 | Wed 30-07-25 | 30 days | 0% | 670 | 672SS+7 days
Civil Works (Land Leveling , GSB , PCC, VDF) | Fri 16-05-25 | Tue 17-06-25 | 30 days | NA | NA | Mon 07-07-25 | Thu 07-08-25 | 30 days | 0% | 671SS+7 days | 6731650
PNG Yard - Handover | Tue 17-06-25 | Tue 17-06-25 | 0 days | NA | NA | Thu 07-08-25 | Thu 07-08-25 | 0 days | 0% | 672
Sub Station Yard | Fri 07-02-25 | Wed 10-09-25 | 208 days | Mon 30-06-25 | NA | Mon 30-06-25 | Mon 02-02-26 | 208.88 days | 13%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Mon 01-09-25 | Mon 15-09-25 | Mon 01-09-25 | Mon 15-09-25 | 14.5 days | 100% | 57 | 677
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | Mon 01-09-25 | Tue 09-09-25 | Mon 01-09-25 | Tue 09-09-25 | 8.88 days | 100%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | Mon 01-09-25 | Wed 03-09-25 | Mon 01-09-25 | Wed 03-09-25 | 0 days | 100% | 675 | 678
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | Thu 04-09-25 | Sat 06-09-25 | Thu 04-09-25 | Sat 06-09-25 | 3.25 days | 100% | 677 | 679
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | Sun 07-09-25 | Mon 08-09-25 | Sun 07-09-25 | Mon 08-09-25 | 1 day | 100% | 678 | 680
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | Mon 08-09-25 | Tue 09-09-25 | Mon 08-09-25 | Tue 09-09-25 | 1.13 days | 100% | 679 | 681
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | Mon 15-09-25 | Tue 30-09-25 | Mon 15-09-25 | Tue 30-09-25 | 15.63 days | 100% | 680 | 682
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Wed 10-09-25 | 120 days | Mon 15-09-25 | NA | Mon 15-09-25 | Mon 02-02-26 | 120 days | 0% | 681 | 683SS+7 days
Civil Works (Land Leveling , GSB , PCC, Foundation) | Fri 16-05-25 | Mon 18-08-25 | 90 days | Mon 15-09-25 | NA | Mon 15-09-25 | Sat 22-11-25 | 60 days | 0% | 682SS+7 days | 6.8516e+34
Tower Work Structure & Bus Bar Control Room Structure | Sat 22-02-25 | Fri 27-06-25 | 120 days | NA | NA | Mon 30-06-25 | Mon 01-09-25 | 60 days | 0% | 58 | 16451637
Sub station - Handover | Mon 18-08-25 | Mon 18-08-25 | 0 days | NA | NA | Sat 22-11-25 | Sat 22-11-25 | 0 days | 0% | 683
Culvert & Gate Entry | Fri 07-02-25 | Sat 18-10-25 | 245 days | Sun 01-06-25 | NA | Sun 01-06-25 | Sat 13-12-25 | 189 days | 6%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Sun 01-06-25 | Fri 20-06-25 | Sun 01-06-25 | Fri 20-06-25 | 19 days | 100% | 57 | 689
Order for Civil | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Fri 20-06-25 | Sat 19-07-25 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 20-06-25 | Sat 28-06-25 | 7 days | 0% | 687 | 690
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Sat 28-06-25 | Sat 05-07-25 | 7 days | 0% | 689 | 691
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Sat 05-07-25 | Sat 12-07-25 | 7 days | 0% | 690 | 692
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Sat 12-07-25 | Sat 19-07-25 | 7 days | 0% | 691 | 693
Detail Enginering & Drawing - Civil | Tue 08-04-25 | Fri 09-05-25 | 30 days | NA | NA | Sat 19-07-25 | Wed 20-08-25 | 30 days | 0% | 692 | 694698
Transportation in Multiple Lot for Civil | Fri 09-05-25 | Wed 10-09-25 | 120 days | NA | NA | Wed 20-08-25 | Tue 21-10-25 | 60 days | 0% | 693 | 695SS+7 days
Civil Works (Land Leveling , GSB , PCC, VDF) | Fri 16-05-25 | Mon 18-08-25 | 90 days | NA | NA | Wed 27-08-25 | Tue 28-10-25 | 60 days | 0% | 694SS+7 days | 696
Handover of Civil Work | Mon 18-08-25 | Thu 18-09-25 | 30 days | NA | NA | Wed 29-10-25 | Thu 13-11-25 | 15 days | 0% | 695 | 704
Interior | Fri 09-05-25 | Sat 18-10-25 | 157 days | NA | NA | Wed 20-08-25 | Sat 13-12-25 | 112 days | 0%
RFQ | Fri 09-05-25 | Fri 16-05-25 | 7 days | NA | NA | Wed 20-08-25 | Wed 27-08-25 | 7 days | 0% | 693 | 699
Offer Receipt | Fri 16-05-25 | Fri 23-05-25 | 7 days | NA | NA | Wed 27-08-25 | Wed 03-09-25 | 7 days | 0% | 698 | 700
PO Release | Fri 23-05-25 | Fri 30-05-25 | 7 days | NA | NA | Wed 03-09-25 | Thu 11-09-25 | 7 days | 0% | 699 | 701
Payment | Sat 31-05-25 | Sat 07-06-25 | 7 days | NA | NA | Thu 11-09-25 | Thu 18-09-25 | 7 days | 0% | 700 | 702
Manufacturing Duration | Sat 07-06-25 | Tue 08-07-25 | 30 days | NA | NA | Thu 18-09-25 | Sat 18-10-25 | 30 days | 0% | 701 | 703
Transporation in Multiple Lot | Tue 08-07-25 | Thu 24-07-25 | 15 days | NA | NA | Mon 20-10-25 | Tue 04-11-25 | 15 days | 0% | 702 | 1623704
Execution of External Work | Thu 18-09-25 | Sat 18-10-25 | 30 days | NA | NA | Thu 13-11-25 | Sat 13-12-25 | 30 days | 0% | 696703 | 705
Handover - Gate and Exteriors of Gate | Sat 18-10-25 | Sat 18-10-25 | 0 days | NA | NA | Sat 13-12-25 | Sat 13-12-25 | 0 days | 0% | 704
Utilities - Procurement | Wed 08-01-25 | Wed 25-03-26 | 425 days | Mon 07-04-25 | NA | Mon 07-04-25 | Wed 15-04-26 | 360.25 days | 31%
Water Packages | Wed 08-01-25 | Sat 21-02-26 | 395 days | Mon 07-04-25 | NA | Mon 07-04-25 | Fri 20-03-26 | 336.25 days | 46%
Water Package (UPW/ETP/ZLD/STP/DI) | Wed 08-01-25 | Sat 21-02-26 | 395 days | Thu 01-05-25 | NA | Thu 01-05-25 | Fri 06-03-26 | 299 days | 60%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 711
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Mon 02-06-25 | Sat 05-07-25 | Mon 02-06-25 | Sat 05-07-25 | 33.63 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Mon 02-06-25 | Thu 05-06-25 | Mon 02-06-25 | Thu 05-06-25 | 4.38 days | 100% | 709 | 712
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Thu 05-06-25 | Mon 16-06-25 | Thu 05-06-25 | Mon 16-06-25 | 10.13 days | 100% | 711 | 713
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Mon 16-06-25 | Wed 25-06-25 | Mon 16-06-25 | Wed 25-06-25 | 9 days | 100% | 712 | 714
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Wed 25-06-25 | Sat 05-07-25 | Wed 25-06-25 | Sat 05-07-25 | 10.13 days | 100% | 713 | 406715
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Fri 01-08-25 | Sat 25-10-25 | Fri 01-08-25 | Sat 25-10-25 | 79.88 days | 100% | 714,55 | 716
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Sun 10-08-25 | Sat 25-10-25 | Sun 10-08-25 | Sat 25-10-25 | 49.88 days | 100% | 715 | 717
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Tue 30-09-25 | NA | Tue 30-09-25 | Sat 27-12-25 | 60 days | 0% | 716 | 718
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Sat 27-12-25 | Sat 03-01-26 | 7 days | 0% | 717 | 719
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Sat 03-01-26 | Fri 06-03-26 | 60 days | 0% | 718 | 1477SS+7 days
Water Package (Lime Liquid Handlling Dosing Sytem) | Wed 08-01-25 | Tue 06-01-26 | 350 days | Thu 01-05-25 | NA | Thu 01-05-25 | Tue 27-01-26 | 262 days | 48%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 723
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Wed 30-07-25 | Thu 25-09-25 | Wed 30-07-25 | Thu 25-09-25 | 55.13 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Wed 30-07-25 | Wed 30-07-25 | Wed 30-07-25 | Wed 30-07-25 | 0 days | 100% | 721 | 724
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Mon 01-09-25 | Sat 06-09-25 | Mon 01-09-25 | Sat 06-09-25 | 6.63 days | 100% | 723 | 725
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Mon 08-09-25 | Fri 19-09-25 | Mon 08-09-25 | Fri 19-09-25 | 12.25 days | 100% | 724 | 726
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 22-09-25 | Thu 25-09-25 | Mon 22-09-25 | Thu 25-09-25 | 4.38 days | 100% | 725 | 406727
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Fri 19-09-25 | Sat 25-10-25 | Fri 19-09-25 | Sat 25-10-25 | 29.25 days | 100% | 726,55 | 728
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Fri 19-09-25 | Sat 25-10-25 | Fri 19-09-25 | Sat 25-10-25 | 0 days | 100% | 727 | 729
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Sat 25-10-25 | NA | Sat 25-10-25 | Sat 27-12-25 | 60 days | 0% | 728 | 730
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Sat 27-12-25 | Mon 12-01-26 | 15 days | 0% | 729 | 731
Transportation in Multiple Lot | Tue 28-10-25 | Thu 13-11-25 | 15 days | NA | NA | Mon 12-01-26 | Tue 27-01-26 | 15 days | 0% | 730 | 1479SS+7 days
Water Package (Solid Lime Handling System Dosing) | Wed 08-01-25 | Tue 06-01-26 | 350 days | Thu 01-05-25 | NA | Thu 01-05-25 | Sat 31-01-26 | 266.5 days | 60%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 735
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Wed 30-07-25 | Thu 25-09-25 | Wed 30-07-25 | Thu 25-09-25 | 56.13 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Wed 30-07-25 | Wed 30-07-25 | Wed 30-07-25 | Wed 30-07-25 | 1 day | 100% | 733 | 736
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Mon 01-09-25 | Sat 06-09-25 | Mon 01-09-25 | Sat 06-09-25 | 6.63 days | 100% | 735 | 737
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Mon 08-09-25 | Fri 19-09-25 | Mon 08-09-25 | Fri 19-09-25 | 12.25 days | 100% | 736 | 738
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 22-09-25 | Thu 25-09-25 | Mon 22-09-25 | Thu 25-09-25 | 4.38 days | 100% | 737 | 406739
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Fri 19-09-25 | Thu 30-10-25 | Fri 19-09-25 | Thu 30-10-25 | 40.38 days | 100% | 738,55 | 740
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Fri 19-09-25 | Thu 30-10-25 | Fri 19-09-25 | Thu 30-10-25 | 40.38 days | 100% | 739 | 741
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Sat 25-10-25 | NA | Sat 25-10-25 | Thu 01-01-26 | 60 days | 0% | 740 | 742
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Thu 01-01-26 | Fri 16-01-26 | 15 days | 0% | 741 | 743
Transportation in Multiple Lot | Tue 28-10-25 | Thu 13-11-25 | 15 days | NA | NA | Fri 16-01-26 | Sat 31-01-26 | 15 days | 0% | 742 | 1481SS+7 days
PNG Gas | Wed 08-01-25 | Sat 03-01-26 | 348 days | Mon 07-04-25 | NA | Mon 07-04-25 | Mon 22-12-25 | 250.75 days | 74%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Mon 07-04-25 | Tue 06-05-25 | Mon 07-04-25 | Tue 06-05-25 | 29.13 days | 100% | 54 | 747
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Mon 07-04-25 | NA | Mon 07-04-25 | Wed 29-10-25 | 198.38 days | 90%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Mon 07-04-25 | Tue 14-10-25 | Mon 07-04-25 | Tue 14-10-25 | 131.63 days | 100% | 745 | 748
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Tue 14-10-25 | Tue 14-10-25 | Tue 14-10-25 | Tue 14-10-25 | 0 days | 100% | 747 | 749
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Tue 14-10-25 | Wed 22-10-25 | 7 days | 0% | 748 | 750
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Wed 22-10-25 | Wed 29-10-25 | 7 days | 0% | 749 | 406751
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Thu 30-10-25 | Wed 05-11-25 | Thu 30-10-25 | Wed 05-11-25 | 6.63 days | 100% | 750,55 | 752
Yard input | Sat 10-05-25 | Tue 10-06-25 | 30 days | NA | NA | Wed 05-11-25 | Mon 22-12-25 | 45 days | 0% | 751 | 1650
PNG Piping | Wed 22-01-25 | Thu 27-11-25 | 298 days | Wed 01-10-25 | NA | Wed 01-10-25 | Mon 09-03-26 | 154.13 days | 19%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Thu 30-10-25 | Wed 01-10-25 | Thu 30-10-25 | 29.13 days | 100% | 54,56,55 | 756
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | NA | NA | Thu 30-10-25 | Fri 28-11-25 | 28 days | 0%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Thu 30-10-25 | Fri 07-11-25 | 7 days | 0% | 754 | 757
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Fri 07-11-25 | Fri 14-11-25 | 7 days | 0% | 756 | 758
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 14-11-25 | Fri 21-11-25 | 7 days | 0% | 757 | 759
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | NA | NA | Fri 21-11-25 | Fri 28-11-25 | 7 days | 0% | 758 | 406760
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | NA | NA | Fri 28-11-25 | Mon 15-12-25 | 15 days | 0% | 759,55 | 761
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Mon 15-12-25 | Tue 30-12-25 | 15 days | 0% | 760 | 762
Manufacturing | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Tue 30-12-25 | Sat 14-02-26 | 45 days | 0% | 761 | 763
Inspection ( at factory) | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Sat 14-02-26 | Sat 21-02-26 | 7 days | 0% | 762 | 764
Transportation in Multiple Lot | Wed 12-11-25 | Thu 27-11-25 | 15 days | NA | NA | Sat 21-02-26 | Mon 09-03-26 | 15 days | 0% | 763 | 1560SS+7 days
Raw Water Storage & Softner | Wed 08-01-25 | Tue 06-01-26 | 350 days | Tue 30-09-25 | NA | Tue 30-09-25 | Sat 21-02-26 | 140.63 days | 11%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Tue 30-09-25 | Wed 15-10-25 | Tue 30-09-25 | Wed 15-10-25 | 15.63 days | 100% | 54 | 768
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | NA | NA | Wed 15-10-25 | Thu 13-11-25 | 28 days | 0%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | NA | NA | Wed 15-10-25 | Thu 23-10-25 | 7 days | 0% | 766 | 769
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | NA | NA | Thu 23-10-25 | Thu 30-10-25 | 7 days | 0% | 768 | 770
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Thu 30-10-25 | Thu 06-11-25 | 7 days | 0% | 769 | 771
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Thu 06-11-25 | Thu 13-11-25 | 7 days | 0% | 770 | 406772
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | NA | NA | Thu 13-11-25 | Sat 29-11-25 | 15 days | 0% | 771,55 | 773
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | NA | NA | Sat 29-11-25 | Mon 15-12-25 | 15 days | 0% | 772 | 774
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | NA | NA | Mon 15-12-25 | Fri 30-01-26 | 45 days | 0% | 773 | 775
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Fri 30-01-26 | Fri 06-02-26 | 7 days | 0% | 774 | 776
Transportation in Multiple Lot | Tue 28-10-25 | Thu 13-11-25 | 15 days | NA | NA | Fri 06-02-26 | Sat 21-02-26 | 15 days | 0% | 775 | 1575SS+7 days
DI Water Piping | Wed 22-01-25 | Thu 27-11-25 | 298 days | Wed 01-10-25 | NA | Wed 01-10-25 | Fri 20-03-26 | 165.25 days | 14%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Wed 15-10-25 | Wed 01-10-25 | Wed 15-10-25 | 14.5 days | 100% | 54,56 | 780
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Tue 04-11-25 | NA | Tue 04-11-25 | Tue 02-12-25 | 27.63 days | 24%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Tue 04-11-25 | Mon 10-11-25 | Tue 04-11-25 | Mon 10-11-25 | 6.63 days | 100% | 778 | 781
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 10-11-25 | NA | Mon 10-11-25 | Tue 18-11-25 | 7 days | 0% | 780 | 782
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | NA | NA | Tue 18-11-25 | Tue 25-11-25 | 7 days | 0% | 781 | 783
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | NA | NA | Tue 25-11-25 | Tue 02-12-25 | 7 days | 0% | 782 | 406784
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | NA | NA | Tue 02-12-25 | Wed 17-12-25 | 15 days | 0% | 783,55 | 785
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Wed 17-12-25 | Fri 02-01-26 | 15 days | 0% | 784 | 786
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Fri 02-01-26 | Wed 18-02-26 | 45 days | 0% | 785 | 787
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Wed 18-02-26 | Thu 05-03-26 | 15 days | 0% | 786 | 788
Transportation in Multiple Lot | Wed 12-11-25 | Thu 27-11-25 | 15 days | NA | NA | Thu 05-03-26 | Fri 20-03-26 | 15 days | 0% | 787 | 1418SS+7 days,1561SS+7 days
Gas Package | Wed 08-01-25 | Mon 23-03-26 | 423 days | Thu 01-05-25 | NA | Thu 01-05-25 | Fri 03-04-26 | 325.88 days | 63%
Bulk Gas Generation ( N & O2 ) | Wed 08-01-25 | Mon 23-03-26 | 423 days | Thu 01-05-25 | NA | Thu 01-05-25 | Fri 03-04-26 | 325.88 days | 47%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 793
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Tue 22-07-25 | Mon 22-09-25 | Tue 22-07-25 | Mon 22-09-25 | 60.63 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Mon 01-09-25 | Sat 06-09-25 | Mon 01-09-25 | Sat 06-09-25 | 6.63 days | 100% | 791 | 794
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Mon 08-09-25 | Wed 10-09-25 | Mon 08-09-25 | Wed 10-09-25 | 3.25 days | 100% | 793 | 795
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Thu 11-09-25 | Mon 22-09-25 | Thu 11-09-25 | Mon 22-09-25 | 11.13 days | 100% | 794 | 796
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Tue 22-07-25 | Wed 30-07-25 | Tue 22-07-25 | Wed 30-07-25 | 8.88 days | 100% | 795 | 406797
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Mon 22-09-25 | Wed 08-10-25 | Mon 22-09-25 | Wed 08-10-25 | 15.75 days | 100% | 796,55 | 798803
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Mon 27-10-25 | Sun 30-11-25 | Mon 27-10-25 | Sun 30-11-25 | 33.75 days | 100% | 797 | 799
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Wed 08-10-25 | NA | Wed 08-10-25 | Tue 03-03-26 | 90 days | 0% | 798 | 800
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Wed 04-03-26 | Thu 19-03-26 | 15 days | 0% | 799 | 801
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Thu 19-03-26 | Fri 03-04-26 | 15 days | 0% | 800 | 1557SS+7 days
Bulk Gas Piping | Sat 10-05-25 | Mon 16-03-26 | 298 days | Thu 01-05-25 | NA | Thu 01-05-25 | Thu 29-01-26 | 263.75 days | 71%
Basic Engineering | Sat 10-05-25 | Tue 10-06-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 797821833 | 805
Order Process | Tue 10-06-25 | Wed 09-07-25 | 28 days | Tue 01-07-25 | Wed 30-07-25 | Tue 01-07-25 | Wed 30-07-25 | 29.13 days | 100%
RFQ | Tue 10-06-25 | Wed 18-06-25 | 7 days | Tue 01-07-25 | Mon 07-07-25 | Tue 01-07-25 | Mon 07-07-25 | 6.63 days | 100% | 803 | 806
Offer Receipt | Wed 18-06-25 | Wed 25-06-25 | 7 days | Tue 08-07-25 | Thu 10-07-25 | Tue 08-07-25 | Thu 10-07-25 | 3.25 days | 100% | 805 | 807
PO Release | Wed 25-06-25 | Wed 02-07-25 | 7 days | Fri 11-07-25 | Mon 21-07-25 | Fri 11-07-25 | Mon 21-07-25 | 10 days | 100% | 806 | 808
Payment | Wed 02-07-25 | Wed 09-07-25 | 7 days | Tue 22-07-25 | Wed 30-07-25 | Tue 22-07-25 | Wed 30-07-25 | 8.88 days | 100% | 807 | 406809
Detail Engineering | Wed 09-07-25 | Wed 10-09-25 | 60 days | Mon 04-08-25 | Mon 06-10-25 | Mon 04-08-25 | Mon 06-10-25 | 61.75 days | 100% | 808,55 | 810
Drawing (GA + P&ID) | Wed 10-09-25 | Fri 10-10-25 | 30 days | Mon 04-08-25 | Thu 20-11-25 | Mon 04-08-25 | Thu 20-11-25 | 43.88 days | 100% | 809 | 811
Manufacturing Duration | Fri 10-10-25 | Thu 12-02-26 | 120 days | Mon 06-10-25 | NA | Mon 06-10-25 | Tue 06-01-26 | 45 days | 0% | 810 | 812
Inspection at Supplier End | Thu 12-02-26 | Fri 27-02-26 | 15 days | NA | NA | Tue 06-01-26 | Wed 14-01-26 | 7 days | 0% | 811 | 813
Transportation in Multiple Lot | Fri 27-02-26 | Mon 16-03-26 | 15 days | NA | NA | Wed 14-01-26 | Thu 29-01-26 | 15 days | 0% | 812 | 1419SS+7 days,1562SS+7 days
Bullk Gas System | Wed 08-01-25 | Sat 21-02-26 | 395 days | Thu 01-05-25 | Mon 06-10-25 | Thu 01-05-25 | Mon 06-10-25 | 152.88 days | 100%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 817
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Thu 10-07-25 | Sun 10-08-25 | Thu 10-07-25 | Sun 10-08-25 | 30.38 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Thu 10-07-25 | Tue 22-07-25 | Thu 10-07-25 | Tue 22-07-25 | 12.25 days | 100% | 815 | 818
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Wed 23-07-25 | Wed 30-07-25 | Wed 23-07-25 | Wed 30-07-25 | 7.75 days | 100% | 817 | 819
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Wed 30-07-25 | Sat 02-08-25 | Wed 30-07-25 | Sat 02-08-25 | 3.38 days | 100% | 818 | 820
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 04-08-25 | Sun 10-08-25 | Mon 04-08-25 | Sun 10-08-25 | 6.75 days | 100% | 819 | 406821
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Tue 01-07-25 | Mon 07-07-25 | Tue 01-07-25 | Mon 07-07-25 | 6.63 days | 100% | 820,55 | 822803
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Tue 08-07-25 | Thu 10-07-25 | Tue 08-07-25 | Thu 10-07-25 | 3.25 days | 100% | 821 | 823
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Fri 11-07-25 | Mon 21-07-25 | Fri 11-07-25 | Mon 21-07-25 | 10 days | 100% | 822 | 824
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | Tue 22-07-25 | Wed 30-07-25 | Tue 22-07-25 | Wed 30-07-25 | 8.88 days | 100% | 823 | 825
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | Mon 04-08-25 | Mon 06-10-25 | Mon 04-08-25 | Mon 06-10-25 | 61.75 days | 100% | 824 | 1511SS+7 days
NH3(Ammonia) - Decanting System | Wed 08-01-25 | Sat 21-02-26 | 395 days | Thu 01-05-25 | NA | Thu 01-05-25 | Wed 04-03-26 | 296.13 days | 42%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 829
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Mon 06-10-25 | NA | Mon 06-10-25 | Tue 02-12-25 | 55.25 days | 86%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Mon 06-10-25 | Wed 15-10-25 | Mon 06-10-25 | Wed 15-10-25 | 10 days | 100% | 827 | 830
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Wed 15-10-25 | Sat 15-11-25 | Wed 15-10-25 | Sat 15-11-25 | 30.38 days | 100% | 829 | 831
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Mon 24-11-25 | Mon 24-11-25 | Mon 24-11-25 | Mon 24-11-25 | 1 day | 100% | 830 | 832
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 24-11-25 | NA | Mon 24-11-25 | Tue 02-12-25 | 7 days | 0% | 831 | 406833
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Mon 24-11-25 | NA | Mon 24-11-25 | Tue 09-12-25 | 7 days | 0% | 832,55 | 834803
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Mon 24-11-25 | NA | Mon 24-11-25 | Tue 16-12-25 | 7 days | 0% | 833 | 835
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Mon 24-11-25 | NA | Mon 24-11-25 | Sat 31-01-26 | 45 days | 0% | 834 | 836
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Sat 31-01-26 | Mon 16-02-26 | 15 days | 0% | 835 | 837
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Mon 16-02-26 | Wed 04-03-26 | 15 days | 0% | 836 | 1513SS+7 days
Chemical Packages | Wed 08-01-25 | Sat 21-02-26 | 395 days | Thu 01-05-25 | NA | Thu 01-05-25 | Thu 26-03-26 | 317.88 days | 45%
Chemical System | Wed 08-01-25 | Sat 21-02-26 | 395 days | Thu 01-05-25 | NA | Thu 01-05-25 | Thu 26-03-26 | 317.88 days | 42%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 842
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Tue 01-07-25 | Wed 30-07-25 | Tue 01-07-25 | Wed 30-07-25 | 29.13 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Tue 01-07-25 | Mon 07-07-25 | Tue 01-07-25 | Mon 07-07-25 | 6.63 days | 100% | 840 | 843
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Tue 08-07-25 | Thu 10-07-25 | Tue 08-07-25 | Thu 10-07-25 | 3.25 days | 100% | 842 | 844
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Fri 11-07-25 | Mon 21-07-25 | Fri 11-07-25 | Mon 21-07-25 | 10 days | 100% | 843 | 845
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Tue 22-07-25 | Wed 30-07-25 | Tue 22-07-25 | Wed 30-07-25 | 8.88 days | 100% | 844 | 406846
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 30 days | Mon 04-08-25 | Mon 06-10-25 | Mon 04-08-25 | Mon 06-10-25 | 61.75 days | 100% | 845,55 | 847852
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Mon 06-10-25 | NA | Mon 06-10-25 | Thu 06-11-25 | 30 days | 0% | 846 | 848
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Thu 06-11-25 | NA | Thu 06-11-25 | Sat 07-02-26 | 90 days | 0% | 847 | 849
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Sat 07-02-26 | Mon 23-02-26 | 15 days | 0% | 848 | 850
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Mon 23-02-26 | Thu 26-03-26 | 30 days | 0% | 849 | 1497SS+7 days
Chemical Piping | Sat 10-05-25 | Mon 12-01-26 | 238 days | Thu 01-05-25 | NA | Thu 01-05-25 | Sat 06-12-25 | 211.88 days | 67%
Basic Engineering | Sat 10-05-25 | Tue 10-06-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 846 | 854
Order Process | Tue 10-06-25 | Wed 09-07-25 | 28 days | Tue 01-07-25 | Wed 30-07-25 | Tue 01-07-25 | Wed 30-07-25 | 29.13 days | 100%
RFQ | Tue 10-06-25 | Wed 18-06-25 | 7 days | Tue 01-07-25 | Mon 07-07-25 | Tue 01-07-25 | Mon 07-07-25 | 6.63 days | 100% | 852 | 855
Offer Receipt | Wed 18-06-25 | Wed 25-06-25 | 7 days | Tue 08-07-25 | Thu 10-07-25 | Tue 08-07-25 | Thu 10-07-25 | 3.25 days | 100% | 854 | 856
PO Release | Wed 25-06-25 | Wed 02-07-25 | 7 days | Fri 11-07-25 | Mon 21-07-25 | Fri 11-07-25 | Mon 21-07-25 | 10 days | 100% | 855 | 857
Payment | Wed 02-07-25 | Wed 09-07-25 | 7 days | Tue 22-07-25 | Wed 30-07-25 | Tue 22-07-25 | Wed 30-07-25 | 8.88 days | 100% | 856 | 406858
Detail Engineering | Wed 09-07-25 | Wed 10-09-25 | 60 days | Mon 04-08-25 | Mon 06-10-25 | Mon 04-08-25 | Mon 06-10-25 | 61.75 days | 100% | 857,55 | 859
Drawing (GA + P&ID) | Wed 10-09-25 | Fri 10-10-25 | 30 days | Mon 06-10-25 | NA | Mon 06-10-25 | Tue 14-10-25 | 7 days | 0% | 858 | 860
Manufacturing Duration | Fri 10-10-25 | Fri 12-12-25 | 60 days | Mon 06-10-25 | NA | Mon 06-10-25 | Thu 13-11-25 | 30 days | 0% | 859 | 861
Inspection at Supplier End | Fri 12-12-25 | Sat 27-12-25 | 15 days | NA | NA | Thu 13-11-25 | Thu 20-11-25 | 7 days | 0% | 860 | 862
Transportation in Multiple Lot | Sat 27-12-25 | Mon 12-01-26 | 15 days | NA | NA | Fri 21-11-25 | Sat 06-12-25 | 15 days | 0% | 861 | 1420SS+7 days,1563SS+7 days
Chemical Waste Piping Network (PEN) | Wed 22-01-25 | Thu 27-11-25 | 298 days | Mon 01-09-25 | NA | Mon 01-09-25 | Wed 14-01-26 | 131.13 days | 22%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Mon 01-09-25 | Tue 30-09-25 | Mon 01-09-25 | Tue 30-09-25 | 29.13 days | 100% | 54,56 | 866
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | NA | NA | Tue 30-09-25 | Wed 29-10-25 | 28 days | 0%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Tue 30-09-25 | Wed 08-10-25 | 7 days | 0% | 864 | 867
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Wed 08-10-25 | Wed 15-10-25 | 7 days | 0% | 866 | 868
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | NA | NA | Wed 15-10-25 | Wed 22-10-25 | 7 days | 0% | 867 | 869
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | NA | NA | Wed 22-10-25 | Wed 29-10-25 | 7 days | 0% | 868 | 406870
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | NA | NA | Wed 29-10-25 | Wed 05-11-25 | 7 days | 0% | 869,55 | 871
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Thu 06-11-25 | Thu 13-11-25 | 7 days | 0% | 870 | 872
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Thu 13-11-25 | Sat 13-12-25 | 30 days | 0% | 871 | 873
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Sat 13-12-25 | Tue 30-12-25 | 15 days | 0% | 872 | 874
Transportation in Multiple Lot | Wed 12-11-25 | Thu 27-11-25 | 15 days | NA | NA | Tue 30-12-25 | Wed 14-01-26 | 15 days | 0% | 873 | 1421SS+7 days
Air Packages | Wed 08-01-25 | Wed 25-03-26 | 425 days | Thu 01-05-25 | NA | Thu 01-05-25 | Wed 11-02-26 | 276.63 days | 33%
Air-Compressors & Dryer & Cooling Tower | Wed 08-01-25 | Sat 21-02-26 | 395 days | Thu 01-05-25 | NA | Thu 01-05-25 | Wed 17-12-25 | 222.63 days | 53%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 879925
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Tue 01-07-25 | Fri 08-08-25 | Tue 01-07-25 | Fri 08-08-25 | 38.13 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Tue 01-07-25 | Mon 07-07-25 | Tue 01-07-25 | Mon 07-07-25 | 6.63 days | 100% | 877 | 880
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Tue 08-07-25 | Fri 25-07-25 | Tue 08-07-25 | Fri 25-07-25 | 17.88 days | 100% | 879 | 881
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Sat 26-07-25 | Fri 01-08-25 | Sat 26-07-25 | Fri 01-08-25 | 6.63 days | 100% | 880 | 882
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 04-08-25 | Fri 08-08-25 | Mon 04-08-25 | Fri 08-08-25 | 5.5 days | 100% | 881 | 406883
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Fri 01-08-25 | Sat 30-08-25 | Fri 01-08-25 | Sat 30-08-25 | 21.38 days | 100% | 882,55 | 884
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Sat 30-08-25 | Mon 15-09-25 | Sat 30-08-25 | Mon 15-09-25 | 14.63 days | 100% | 883 | 885
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Sat 30-08-25 | NA | Sat 30-08-25 | Mon 17-11-25 | 60 days | 0% | 884 | 886
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Mon 17-11-25 | Tue 02-12-25 | 15 days | 0% | 885 | 887
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Tue 02-12-25 | Wed 17-12-25 | 15 days | 0% | 886 | 1538
Receiver Tank | Wed 08-01-25 | Sat 21-02-26 | 395 days | Thu 01-05-25 | NA | Thu 01-05-25 | Fri 21-11-25 | 197.13 days | 18%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 891
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | NA | NA | Fri 30-05-25 | Sat 28-06-25 | 28 days | 0%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | NA | NA | Fri 30-05-25 | Sat 07-06-25 | 7 days | 0% | 889 | 892
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | NA | NA | Sat 07-06-25 | Sat 14-06-25 | 7 days | 0% | 891 | 893
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Sat 14-06-25 | Sat 21-06-25 | 7 days | 0% | 892 | 894
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Sat 21-06-25 | Sat 28-06-25 | 7 days | 0% | 893 | 406895
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | NA | NA | Mon 04-08-25 | Wed 20-08-25 | 15 days | 0% | 894,55 | 896
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | NA | NA | Wed 20-08-25 | Thu 04-09-25 | 15 days | 0% | 895 | 897
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | NA | NA | Thu 04-09-25 | Tue 21-10-25 | 45 days | 0% | 896 | 898
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Tue 21-10-25 | Wed 05-11-25 | 15 days | 0% | 897 | 899
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Wed 05-11-25 | Fri 21-11-25 | 15 days | 0% | 898 | 1540
CDA - Pre- Receiver Piping | Wed 08-01-25 | Sat 21-02-26 | 395 days | Thu 01-05-25 | NA | Thu 01-05-25 | Tue 28-10-25 | 174.13 days | 21%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 903
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | NA | NA | Fri 30-05-25 | Sat 28-06-25 | 28 days | 0%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | NA | NA | Fri 30-05-25 | Sat 07-06-25 | 7 days | 0% | 901 | 904
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | NA | NA | Sat 07-06-25 | Sat 14-06-25 | 7 days | 0% | 903 | 905
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Sat 14-06-25 | Sat 21-06-25 | 7 days | 0% | 904 | 906
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Sat 21-06-25 | Sat 28-06-25 | 7 days | 0% | 905 | 406907
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | NA | NA | Mon 04-08-25 | Wed 20-08-25 | 15 days | 0% | 906,55 | 908
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | NA | NA | Wed 20-08-25 | Thu 04-09-25 | 15 days | 0% | 907 | 909
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | NA | NA | Thu 04-09-25 | Mon 06-10-25 | 30 days | 0% | 908 | 910
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Mon 06-10-25 | Mon 13-10-25 | 7 days | 0% | 909 | 911
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Mon 13-10-25 | Tue 28-10-25 | 15 days | 0% | 910 | 1541
CDA - Post Receiver Piping | Wed 08-01-25 | Tue 30-12-25 | 343 days | Thu 01-05-25 | NA | Thu 01-05-25 | Thu 13-11-25 | 189.13 days | 19%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Thu 01-05-25 | Fri 30-05-25 | Thu 01-05-25 | Fri 30-05-25 | 29.13 days | 100% | 54 | 915
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | NA | NA | Fri 30-05-25 | Sat 28-06-25 | 28 days | 0%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | NA | NA | Fri 30-05-25 | Sat 07-06-25 | 7 days | 0% | 913 | 916
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | NA | NA | Sat 07-06-25 | Sat 14-06-25 | 7 days | 0% | 915 | 917
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Sat 14-06-25 | Sat 21-06-25 | 7 days | 0% | 916 | 918
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Sat 21-06-25 | Sat 28-06-25 | 7 days | 0% | 917 | 406919
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | NA | NA | Mon 04-08-25 | Wed 20-08-25 | 15 days | 0% | 918,55 | 920
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | NA | NA | Wed 20-08-25 | Thu 04-09-25 | 15 days | 0% | 919 | 921
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | NA | NA | Thu 04-09-25 | Mon 06-10-25 | 30 days | 0% | 920 | 922
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Mon 06-10-25 | Mon 13-10-25 | 7 days | 0% | 921 | 923
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Mon 13-10-25 | Thu 13-11-25 | 30 days | 0% | 922 | 1422SS+7 days,1564SS+7 days
Soft Starter for compressor | Sat 08-02-25 | Wed 25-03-26 | 395 days | Mon 01-09-25 | NA | Mon 01-09-25 | Wed 11-02-26 | 158.5 days | 45%
Basic Engineering | Sat 08-02-25 | Tue 11-03-25 | 30 days | Mon 01-09-25 | Mon 15-09-25 | Mon 01-09-25 | Mon 15-09-25 | 14.5 days | 100% | 54877 | 927
Order Process | Tue 11-03-25 | Wed 09-04-25 | 28 days | Mon 15-09-25 | Mon 20-10-25 | Mon 15-09-25 | Mon 20-10-25 | 34.75 days | 100%
RFQ | Tue 11-03-25 | Tue 18-03-25 | 7 days | Mon 15-09-25 | Sat 20-09-25 | Mon 15-09-25 | Sat 20-09-25 | 5.63 days | 100% | 925 | 928
Offer Receipt | Tue 18-03-25 | Wed 26-03-25 | 7 days | Sat 20-09-25 | Thu 25-09-25 | Sat 20-09-25 | Thu 25-09-25 | 4.5 days | 100% | 927 | 929
PO Release | Wed 26-03-25 | Wed 02-04-25 | 7 days | Thu 25-09-25 | Fri 10-10-25 | Thu 25-09-25 | Fri 10-10-25 | 14.63 days | 100% | 928 | 930
Payment | Wed 02-04-25 | Wed 09-04-25 | 7 days | Wed 15-10-25 | Mon 20-10-25 | Wed 15-10-25 | Mon 20-10-25 | 5.5 days | 100% | 929 | 406931
Detail Engineering | Wed 09-04-25 | Tue 10-06-25 | 60 days | Fri 10-10-25 | Mon 10-11-25 | Fri 10-10-25 | Mon 10-11-25 | 30.25 days | 100% | 930,55 | 932
Drawing (GA + P&ID) | Tue 10-06-25 | Fri 11-07-25 | 30 days | Fri 10-10-25 | Mon 10-11-25 | Fri 10-10-25 | Mon 10-11-25 | 0 days | 100% | 931 | 933
Manufacturing Duration | Fri 11-07-25 | Thu 13-11-25 | 120 days | Fri 10-10-25 | NA | Fri 10-10-25 | Mon 12-01-26 | 60 days | 0% | 932 | 934
Inspection at Supplier End | Thu 13-11-25 | Fri 28-11-25 | 15 days | NA | NA | Mon 12-01-26 | Tue 27-01-26 | 15 days | 0% | 933 | 935
Transportation in Multiple Lot | Fri 28-11-25 | Thu 29-01-26 | 60 days | NA | NA | Tue 27-01-26 | Wed 11-02-26 | 15 days | 0% | 934 | 1542
HVAC Packages | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Wed 04-03-26 | 148.63 days | 32%
AHUs | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Thu 29-01-26 | 116.38 days | 31%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Tue 07-10-25 | Wed 01-10-25 | Tue 07-10-25 | 6.63 days | 100% | 54,56 | 940
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Wed 22-10-25 | Fri 14-11-25 | Wed 22-10-25 | Fri 14-11-25 | 23.5 days | 100%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Wed 22-10-25 | Fri 24-10-25 | Wed 22-10-25 | Fri 24-10-25 | 3.25 days | 100% | 938 | 941
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Thu 30-10-25 | Tue 04-11-25 | Thu 30-10-25 | Tue 04-11-25 | 5.5 days | 100% | 940 | 942
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | Thu 06-11-25 | Fri 07-11-25 | Thu 06-11-25 | Fri 07-11-25 | 2.13 days | 100% | 941 | 943
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | Sat 08-11-25 | Fri 14-11-25 | Sat 08-11-25 | Fri 14-11-25 | 6.63 days | 100% | 942 | 406944
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | Wed 12-11-25 | Thu 20-11-25 | Wed 12-11-25 | Thu 20-11-25 | 5.63 days | 100% | 943,55 | 945
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Wed 12-11-25 | Thu 20-11-25 | Wed 12-11-25 | Thu 20-11-25 | 0 days | 100% | 944 | 946
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | Wed 12-11-25 | NA | Wed 12-11-25 | Tue 06-01-26 | 45 days | 0% | 945 | 947
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Tue 06-01-26 | Wed 14-01-26 | 7 days | 0% | 946 | 948
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Wed 14-01-26 | Thu 29-01-26 | 15 days | 0% | 947 | 1425SS+7 days
Low Side | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Sat 21-02-26 | 138.5 days | 29%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Wed 15-10-25 | Wed 01-10-25 | Wed 15-10-25 | 14.5 days | 100% | 54,56 | 952
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Wed 15-10-25 | Wed 12-11-25 | Wed 15-10-25 | Wed 12-11-25 | 28 days | 100%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Wed 15-10-25 | Thu 30-10-25 | Wed 15-10-25 | Thu 30-10-25 | 14.63 days | 100% | 950 | 953
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Sat 01-11-25 | Thu 06-11-25 | Sat 01-11-25 | Thu 06-11-25 | 5.5 days | 100% | 952 | 954
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | Thu 06-11-25 | Sat 08-11-25 | Thu 06-11-25 | Sat 08-11-25 | 2.25 days | 100% | 953 | 955
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | Sat 08-11-25 | Wed 12-11-25 | Sat 08-11-25 | Wed 12-11-25 | 3.38 days | 100% | 954 | 406956
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | Thu 06-11-25 | NA | Thu 06-11-25 | Fri 28-11-25 | 15 days | 0% | 955,55 | 957
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Thu 06-11-25 | NA | Thu 06-11-25 | Sat 13-12-25 | 15 days | 0% | 956 | 958
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Sat 13-12-25 | Wed 14-01-26 | 30 days | 0% | 957 | 959
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 958 | 960
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Wed 21-01-26 | Sat 21-02-26 | 30 days | 0% | 959 | 1427SS+7 days
High Side | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Wed 04-03-26 | 148.63 days | 35%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Wed 15-10-25 | Wed 01-10-25 | Wed 15-10-25 | 14.5 days | 100% | 54,56 | 964
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Wed 15-10-25 | NA | Wed 15-10-25 | Sat 22-11-25 | 38.13 days | 99%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Wed 15-10-25 | Thu 30-10-25 | Wed 15-10-25 | Thu 30-10-25 | 15.63 days | 100% | 962 | 965
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Sat 01-11-25 | Thu 06-11-25 | Sat 01-11-25 | Thu 06-11-25 | 5.5 days | 100% | 964 | 966
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | Thu 06-11-25 | Tue 18-11-25 | Thu 06-11-25 | Tue 18-11-25 | 12.25 days | 100% | 965 | 967
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | Wed 19-11-25 | NA | Wed 19-11-25 | Sat 22-11-25 | 4.38 days | 99% | 966 | 406968
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | Mon 17-11-25 | NA | Mon 17-11-25 | Tue 09-12-25 | 15 days | 0% | 967,55 | 969
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Mon 17-11-25 | NA | Mon 17-11-25 | Wed 24-12-25 | 15 days | 0% | 968 | 970
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Wed 24-12-25 | Sat 24-01-26 | 30 days | 0% | 969 | 971
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Sat 24-01-26 | Sat 31-01-26 | 7 days | 0% | 970 | 972
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Sat 31-01-26 | Wed 04-03-26 | 30 days | 0% | 971 | 1429SS+7 days
PCW Packages | Wed 22-01-25 | Tue 13-01-26 | 343 days | Mon 15-09-25 | NA | Mon 15-09-25 | Wed 15-04-26 | 205 days | 26%
Chillers (PCW / HVAC) | Wed 22-01-25 | Tue 13-01-26 | 343 days | Mon 15-09-25 | NA | Mon 15-09-25 | Tue 17-02-26 | 149.88 days | 30%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Mon 15-09-25 | Fri 19-09-25 | Mon 15-09-25 | Fri 19-09-25 | 5.5 days | 100% | 54,56 | 977
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Fri 19-09-25 | Mon 13-10-25 | Fri 19-09-25 | Mon 13-10-25 | 23.5 days | 100%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Fri 19-09-25 | Wed 24-09-25 | Fri 19-09-25 | Wed 24-09-25 | 4.5 days | 100% | 975 | 978
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Thu 25-09-25 | Fri 03-10-25 | Thu 25-09-25 | Fri 03-10-25 | 8.88 days | 100% | 977 | 979
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | Fri 03-10-25 | Mon 06-10-25 | Fri 03-10-25 | Mon 06-10-25 | 2.25 days | 100% | 978 | 980
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | Mon 06-10-25 | Mon 13-10-25 | Mon 06-10-25 | Mon 13-10-25 | 7.75 days | 100% | 979 | 406981
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | Mon 13-10-25 | Thu 30-10-25 | Mon 13-10-25 | Thu 30-10-25 | 16.88 days | 100% | 980,55 | 982
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Mon 13-10-25 | Thu 30-10-25 | Mon 13-10-25 | Thu 30-10-25 | 0 days | 100% | 981 | 983
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | Thu 30-10-25 | NA | Thu 30-10-25 | Mon 01-12-25 | 30 days | 0% | 982 | 984
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Mon 01-12-25 | Tue 16-12-25 | 15 days | 0% | 983 | 985
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Tue 16-12-25 | Tue 17-02-26 | 60 days | 0% | 984 | 1431SS+7 days,1531SS+7 days
Pump (PCW/HVAC) | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Mon 23-03-26 | 167 days | 23%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Wed 15-10-25 | Wed 01-10-25 | Wed 15-10-25 | 14.5 days | 100% | 54,56 | 989
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Fri 24-10-25 | Sat 15-11-25 | Fri 24-10-25 | Sat 15-11-25 | 22.38 days | 100%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Fri 24-10-25 | Sat 25-10-25 | Fri 24-10-25 | Sat 25-10-25 | 2.13 days | 100% | 987 | 990
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Sat 25-10-25 | Mon 03-11-25 | Sat 25-10-25 | Mon 03-11-25 | 7.88 days | 100% | 989 | 991
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | Tue 04-11-25 | Thu 13-11-25 | Tue 04-11-25 | Thu 13-11-25 | 10 days | 100% | 990 | 992
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | Fri 14-11-25 | Sat 15-11-25 | Fri 14-11-25 | Sat 15-11-25 | 2.13 days | 100% | 991 | 406993
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | Tue 04-11-25 | NA | Tue 04-11-25 | Tue 18-11-25 | 2.13 days | 0% | 992,55 | 994
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Tue 04-11-25 | NA | Tue 04-11-25 | Thu 04-12-25 | 15 days | 0% | 993 | 995
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | Tue 04-11-25 | NA | Tue 04-11-25 | Sat 03-01-26 | 30 days | 0% | 994 | 996
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Sat 03-01-26 | Tue 20-01-26 | 15 days | 0% | 995 | 997
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Tue 20-01-26 | Mon 23-03-26 | 60 days | 0% | 996 | 1433SS+7 days,1533SS+7 days
Primary & Secondary Piping | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Wed 15-04-26 | 189.25 days | 25%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Wed 15-10-25 | Wed 01-10-25 | Wed 15-10-25 | 14.5 days | 100% | 54,56 | 1001
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Wed 15-10-25 | NA | Wed 15-10-25 | Wed 26-11-25 | 40.75 days | 83%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Wed 15-10-25 | Thu 30-10-25 | Wed 15-10-25 | Thu 30-10-25 | 15.63 days | 100% | 999 | 1002
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Sat 01-11-25 | Thu 06-11-25 | Sat 01-11-25 | Thu 06-11-25 | 5.5 days | 100% | 1001 | 1003
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | Thu 06-11-25 | Tue 18-11-25 | Thu 06-11-25 | Tue 18-11-25 | 12.25 days | 100% | 1002 | 1004
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | Wed 19-11-25 | NA | Wed 19-11-25 | Wed 26-11-25 | 7 days | 0% | 1003 | 4061005
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | Mon 17-11-25 | NA | Mon 17-11-25 | Thu 11-12-25 | 15 days | 0% | 1004,55 | 1006
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Mon 17-11-25 | NA | Mon 17-11-25 | Fri 26-12-25 | 15 days | 0% | 1005 | 1007
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1006 | 1008
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Tue 27-01-26 | Wed 11-02-26 | 15 days | 0% | 1007 | 1009
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Wed 11-02-26 | Wed 15-04-26 | 60 days | 0% | 1008 | 1423SS+7 days,1535SS+7 days,1565SS+7 days
Heat Exchanger | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Wed 15-04-26 | 189.25 days | 25%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Wed 15-10-25 | Wed 01-10-25 | Wed 15-10-25 | 14.5 days | 100% | 54,56 | 1013
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Wed 15-10-25 | NA | Wed 15-10-25 | Wed 26-11-25 | 40.75 days | 83%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Wed 15-10-25 | Thu 30-10-25 | Wed 15-10-25 | Thu 30-10-25 | 15.63 days | 100% | 1011 | 1014
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Sat 01-11-25 | Thu 06-11-25 | Sat 01-11-25 | Thu 06-11-25 | 5.5 days | 100% | 1013 | 1015
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | Thu 06-11-25 | Tue 18-11-25 | Thu 06-11-25 | Tue 18-11-25 | 12.25 days | 100% | 1014 | 1016
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | Wed 19-11-25 | NA | Wed 19-11-25 | Wed 26-11-25 | 7 days | 0% | 1015 | 4061017
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | Mon 17-11-25 | NA | Mon 17-11-25 | Thu 11-12-25 | 15 days | 0% | 1016,55 | 1018
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Mon 17-11-25 | NA | Mon 17-11-25 | Fri 26-12-25 | 15 days | 0% | 1017 | 1019
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1018 | 1020
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Tue 27-01-26 | Wed 11-02-26 | 15 days | 0% | 1019 | 1021
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Wed 11-02-26 | Wed 15-04-26 | 60 days | 0% | 1020 | 1435SS+7 days,1536SS+7 days
Exhaust Packages | Wed 08-01-25 | Tue 30-12-25 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Thu 26-03-26 | 170.75 days | 24%
Exhuast - Blower | Wed 08-01-25 | Tue 30-12-25 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Tue 03-03-26 | 148.25 days | 14%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Wed 01-10-25 | Fri 10-10-25 | Wed 01-10-25 | Fri 10-10-25 | 10 days | 100% | 54 | 1026
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Fri 10-10-25 | Wed 22-10-25 | Fri 10-10-25 | Wed 22-10-25 | 12.25 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Fri 10-10-25 | Sat 11-10-25 | Fri 10-10-25 | Sat 11-10-25 | 1.13 days | 100% | 1024 | 1027
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Mon 13-10-25 | Fri 17-10-25 | Mon 13-10-25 | Fri 17-10-25 | 5.5 days | 100% | 1026 | 1028
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Fri 17-10-25 | Sat 18-10-25 | Fri 17-10-25 | Sat 18-10-25 | 1.13 days | 100% | 1027 | 1029
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Sat 18-10-25 | Wed 22-10-25 | Sat 18-10-25 | Wed 22-10-25 | 3.38 days | 100% | 1028 | 4061030
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Wed 22-10-25 | NA | Wed 22-10-25 | Fri 07-11-25 | 15 days | 0% | 1029,55 | 1031
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Wed 22-10-25 | NA | Wed 22-10-25 | Sat 22-11-25 | 15 days | 0% | 1030 | 1032
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | NA | NA | Sat 22-11-25 | Fri 23-01-26 | 60 days | 0% | 1031 | 1033
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Fri 23-01-26 | Sat 31-01-26 | 7 days | 0% | 1032 | 1034
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Sat 31-01-26 | Tue 03-03-26 | 30 days | 0% | 1033 | 1438SS+7 days
Exhuast - Scrubber | Wed 08-01-25 | Tue 30-12-25 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Thu 26-03-26 | 170.75 days | 25%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Wed 01-10-25 | Fri 24-10-25 | Wed 01-10-25 | Fri 24-10-25 | 23.5 days | 100% | 54 | 1038
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Fri 24-10-25 | Fri 14-11-25 | Fri 24-10-25 | Fri 14-11-25 | 21.25 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Fri 24-10-25 | Thu 30-10-25 | Fri 24-10-25 | Thu 30-10-25 | 5.63 days | 100% | 1036 | 1039
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Sat 01-11-25 | Fri 07-11-25 | Sat 01-11-25 | Fri 07-11-25 | 6.63 days | 100% | 1038 | 1040
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Fri 07-11-25 | Mon 10-11-25 | Fri 07-11-25 | Mon 10-11-25 | 2.25 days | 100% | 1039 | 1041
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 10-11-25 | Fri 14-11-25 | Mon 10-11-25 | Fri 14-11-25 | 4.5 days | 100% | 1040 | 4061042
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Fri 14-11-25 | NA | Fri 14-11-25 | Mon 01-12-25 | 15 days | 0% | 1041,55 | 1043
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Fri 14-11-25 | NA | Fri 14-11-25 | Tue 16-12-25 | 15 days | 0% | 1042 | 1044
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | NA | NA | Tue 16-12-25 | Mon 16-02-26 | 60 days | 0% | 1043 | 1045
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Mon 16-02-26 | Tue 24-02-26 | 7 days | 0% | 1044 | 1046
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Tue 24-02-26 | Thu 26-03-26 | 30 days | 0% | 1045 | 1440SS+7 days
Exhaust - Plastic Ducting | Wed 08-01-25 | Tue 30-12-25 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Thu 26-03-26 | 170.75 days | 26%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Wed 01-10-25 | Fri 24-10-25 | Wed 01-10-25 | Fri 24-10-25 | 23.5 days | 100% | 54 | 1050
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Fri 24-10-25 | Fri 14-11-25 | Fri 24-10-25 | Fri 14-11-25 | 21.25 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Fri 24-10-25 | Thu 30-10-25 | Fri 24-10-25 | Thu 30-10-25 | 6.63 days | 100% | 1048 | 1051
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Sat 01-11-25 | Fri 07-11-25 | Sat 01-11-25 | Fri 07-11-25 | 6.63 days | 100% | 1050 | 1052
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Fri 07-11-25 | Mon 10-11-25 | Fri 07-11-25 | Mon 10-11-25 | 3.25 days | 100% | 1051 | 1053
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 10-11-25 | Fri 14-11-25 | Mon 10-11-25 | Fri 14-11-25 | 5.5 days | 100% | 1052 | 4061054
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Fri 14-11-25 | NA | Fri 14-11-25 | Mon 01-12-25 | 15 days | 0% | 1053,55 | 1055
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Fri 14-11-25 | NA | Fri 14-11-25 | Tue 16-12-25 | 15 days | 0% | 1054 | 1056
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | NA | NA | Tue 16-12-25 | Mon 16-02-26 | 60 days | 0% | 1055 | 1057
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Mon 16-02-26 | Tue 24-02-26 | 7 days | 0% | 1056 | 1058
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Tue 24-02-26 | Thu 26-03-26 | 30 days | 0% | 1057 | 1442SS+7 days
Exhaust - Metallic Ducting | Wed 08-01-25 | Tue 30-12-25 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Tue 24-02-26 | 140.75 days | 32%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Wed 01-10-25 | Fri 24-10-25 | Wed 01-10-25 | Fri 24-10-25 | 23.5 days | 100% | 54 | 1062
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Fri 24-10-25 | Fri 14-11-25 | Fri 24-10-25 | Fri 14-11-25 | 21.25 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Fri 24-10-25 | Thu 30-10-25 | Fri 24-10-25 | Thu 30-10-25 | 6.63 days | 100% | 1060 | 1063
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Sat 01-11-25 | Fri 07-11-25 | Sat 01-11-25 | Fri 07-11-25 | 6.63 days | 100% | 1062 | 1064
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Fri 07-11-25 | Mon 10-11-25 | Fri 07-11-25 | Mon 10-11-25 | 3.25 days | 100% | 1063 | 1065
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 10-11-25 | Fri 14-11-25 | Mon 10-11-25 | Fri 14-11-25 | 5.5 days | 100% | 1064 | 4061066
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Fri 14-11-25 | NA | Fri 14-11-25 | Mon 01-12-25 | 15 days | 0% | 1065,55 | 1067
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Fri 14-11-25 | NA | Fri 14-11-25 | Tue 16-12-25 | 15 days | 0% | 1066 | 1068
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | NA | NA | Tue 16-12-25 | Fri 16-01-26 | 30 days | 0% | 1067 | 1069
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Fri 16-01-26 | Fri 23-01-26 | 7 days | 0% | 1068 | 1070
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Fri 23-01-26 | Tue 24-02-26 | 30 days | 0% | 1069 | 1443SS+7 days
Clean Room | Wed 08-01-25 | Tue 13-01-26 | 357 days | Mon 01-09-25 | NA | Mon 01-09-25 | Tue 17-03-26 | 190.38 days | 29%
Wall & Ceiling Panel & Door | Wed 22-01-25 | Tue 13-01-26 | 343 days | Mon 01-09-25 | NA | Mon 01-09-25 | Sat 07-02-26 | 154.75 days | 28%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Mon 01-09-25 | Sat 20-09-25 | Mon 01-09-25 | Sat 20-09-25 | 20.13 days | 100% | 54,56,55 | 1075
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Sat 20-09-25 | Wed 15-10-25 | Sat 20-09-25 | Wed 15-10-25 | 24.63 days | 100%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Sat 20-09-25 | Tue 30-09-25 | Sat 20-09-25 | Tue 30-09-25 | 10 days | 100% | 1073 | 1076
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Wed 01-10-25 | Sat 04-10-25 | Wed 01-10-25 | Sat 04-10-25 | 3.38 days | 100% | 1075 | 1077
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | Sat 04-10-25 | Wed 08-10-25 | Sat 04-10-25 | Wed 08-10-25 | 3.38 days | 100% | 1076 | 1078
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | Wed 08-10-25 | Wed 15-10-25 | Wed 08-10-25 | Wed 15-10-25 | 6.75 days | 100% | 1077 | 4061079
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | Wed 08-10-25 | NA | Wed 08-10-25 | Thu 23-10-25 | 7 days | 0% | 1078 | 1080
Drawing (GA) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Wed 08-10-25 | NA | Wed 08-10-25 | Thu 30-10-25 | 7 days | 0% | 1079 | 1081
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | Mon 20-10-25 | NA | Mon 20-10-25 | Sat 29-11-25 | 30 days | 0% | 1080 | 1082
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Mon 01-12-25 | Mon 08-12-25 | 7 days | 0% | 1081 | 1083
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Mon 08-12-25 | Sat 07-02-26 | 60 days | 0% | 1082 | 1445SS+7 days
Fan Filter Unit | Wed 08-01-25 | Tue 30-12-25 | 343 days | Mon 01-09-25 | NA | Mon 01-09-25 | Thu 05-02-26 | 152.88 days | 47%
Basic Engineering | Wed 08-01-25 | Fri 07-02-25 | 30 days | Mon 01-09-25 | Sat 20-09-25 | Mon 01-09-25 | Sat 20-09-25 | 20.13 days | 100% | 54,55 | 1087
Order Process | Sat 08-02-25 | Sat 08-03-25 | 28 days | Sat 20-09-25 | Fri 24-10-25 | Sat 20-09-25 | Fri 24-10-25 | 33.63 days | 100%
RFQ | Sat 08-02-25 | Sat 15-02-25 | 7 days | Sat 20-09-25 | Tue 30-09-25 | Sat 20-09-25 | Tue 30-09-25 | 10 days | 100% | 1085 | 1088
Offer Receipt | Sat 15-02-25 | Sat 22-02-25 | 7 days | Wed 01-10-25 | Fri 10-10-25 | Wed 01-10-25 | Fri 10-10-25 | 10 days | 100% | 1087 | 1089
PO Release | Sat 22-02-25 | Sat 01-03-25 | 7 days | Fri 10-10-25 | Mon 13-10-25 | Fri 10-10-25 | Mon 13-10-25 | 3.25 days | 100% | 1088 | 1090
Payment | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 13-10-25 | Fri 24-10-25 | Mon 13-10-25 | Fri 24-10-25 | 12.25 days | 100% | 1089 | 4061091
Detail Engineering | Sat 08-03-25 | Sat 10-05-25 | 60 days | Mon 13-10-25 | Fri 07-11-25 | Mon 13-10-25 | Fri 07-11-25 | 18 days | 100% | 1090 | 1092
Drawing (GA + P&ID) | Sat 10-05-25 | Tue 10-06-25 | 30 days | Mon 13-10-25 | Fri 07-11-25 | Mon 13-10-25 | Fri 07-11-25 | 0 days | 100% | 1091 | 1093
Manufacturing Duration | Tue 10-06-25 | Mon 13-10-25 | 120 days | Thu 13-11-25 | NA | Thu 13-11-25 | Mon 29-12-25 | 45 days | 0% | 1092 | 1094
Inspection at Supplier End | Mon 13-10-25 | Tue 28-10-25 | 15 days | NA | NA | Tue 30-12-25 | Tue 06-01-26 | 7 days | 0% | 1093 | 1095
Transportation in Multiple Lot | Tue 28-10-25 | Tue 30-12-25 | 60 days | NA | NA | Tue 06-01-26 | Thu 05-02-26 | 30 days | 0% | 1094 | 1447SS+7 days
Air Showers | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Tue 17-03-26 | 161.13 days | 18%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Thu 30-10-25 | Wed 01-10-25 | Thu 30-10-25 | 29.13 days | 100% | 54,56,55 | 1099
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | NA | NA | Thu 30-10-25 | Fri 28-11-25 | 28 days | 0%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Thu 30-10-25 | Fri 07-11-25 | 7 days | 0% | 1097 | 1100
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Fri 07-11-25 | Fri 14-11-25 | 7 days | 0% | 1099 | 1101
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 14-11-25 | Fri 21-11-25 | 7 days | 0% | 1100 | 1102
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | NA | NA | Fri 21-11-25 | Fri 28-11-25 | 7 days | 0% | 1101 | 4061103
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | NA | NA | Fri 28-11-25 | Fri 05-12-25 | 7 days | 0% | 1102 | 1104
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 06-12-25 | Sat 13-12-25 | 7 days | 0% | 1103 | 1105
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Sat 13-12-25 | Fri 13-02-26 | 60 days | 0% | 1104 | 1106
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Fri 13-02-26 | Sat 28-02-26 | 15 days | 0% | 1105 | 1107
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Sat 28-02-26 | Tue 17-03-26 | 15 days | 0% | 1106 | 1449SS+7 days
Epoxy Flooring | Wed 22-01-25 | Tue 13-01-26 | 343 days | Wed 01-10-25 | NA | Wed 01-10-25 | Sat 21-02-26 | 139.13 days | 21%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Wed 01-10-25 | Thu 30-10-25 | Wed 01-10-25 | Thu 30-10-25 | 29.13 days | 100% | 54,56,55 | 1111
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | NA | NA | Thu 30-10-25 | Fri 28-11-25 | 28 days | 0%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | NA | NA | Thu 30-10-25 | Fri 07-11-25 | 7 days | 0% | 1109 | 1112
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | NA | NA | Fri 07-11-25 | Fri 14-11-25 | 7 days | 0% | 1111 | 1113
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | NA | NA | Fri 14-11-25 | Fri 21-11-25 | 7 days | 0% | 1112 | 1114
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | NA | NA | Fri 21-11-25 | Fri 28-11-25 | 7 days | 0% | 1113 | 4061115
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | NA | NA | Fri 28-11-25 | Mon 15-12-25 | 15 days | 0% | 1114 | 1116
Drawing - Pattern | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Mon 15-12-25 | Tue 30-12-25 | 15 days | 0% | 1115 | 1117
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | NA | NA | Tue 30-12-25 | Wed 14-01-26 | 15 days | 0% | 1116 | 1118
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Wed 14-01-26 | Wed 21-01-26 | 7 days | 0% | 1117 | 1119
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Thu 22-01-26 | Sat 21-02-26 | 30 days | 0% | 1118 | 1451SS+7 days
Fire Hydrant / Sprinkler / Alarm / Pump System | Wed 22-01-25 | Sat 11-10-25 | 253 days | Thu 16-10-25 | NA | Thu 16-10-25 | Fri 06-03-26 | 135.5 days | 22%
Basic Engineering | Wed 22-01-25 | Sat 22-02-25 | 30 days | Thu 16-10-25 | Thu 30-10-25 | Thu 16-10-25 | Thu 30-10-25 | 13.5 days | 100% | 54,56 | 1123
Order Process | Sat 22-02-25 | Mon 24-03-25 | 28 days | Sat 01-11-25 | NA | Sat 01-11-25 | Wed 03-12-25 | 30.75 days | 54%
RFQ | Sat 22-02-25 | Sat 01-03-25 | 7 days | Sat 01-11-25 | Sat 08-11-25 | Sat 01-11-25 | Sat 08-11-25 | 7.75 days | 100% | 1121 | 1124
Offer Receipt | Sat 01-03-25 | Sat 08-03-25 | 7 days | Mon 10-11-25 | Tue 18-11-25 | Mon 10-11-25 | Tue 18-11-25 | 8.88 days | 100% | 1123 | 1125
PO Release | Sat 08-03-25 | Mon 17-03-25 | 7 days | NA | NA | Tue 18-11-25 | Wed 26-11-25 | 7 days | 0% | 1124 | 1126
Payment | Mon 17-03-25 | Mon 24-03-25 | 7 days | NA | NA | Wed 26-11-25 | Wed 03-12-25 | 7 days | 0% | 1125 | 4061127
Detail Engineering | Mon 24-03-25 | Sat 24-05-25 | 60 days | NA | NA | Wed 03-12-25 | Thu 18-12-25 | 15 days | 0% | 1126 | 1128
Drawing (GA + P&ID) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Thu 18-12-25 | Fri 02-01-26 | 15 days | 0% | 1127 | 1129
Manufacturing Duration | Wed 25-06-25 | Fri 25-07-25 | 30 days | NA | NA | Sat 03-01-26 | Tue 03-02-26 | 30 days | 0% | 1128 | 1130
Inspection at Supplier End | Sat 26-07-25 | Mon 11-08-25 | 15 days | NA | NA | Tue 03-02-26 | Wed 18-02-26 | 15 days | 0% | 1129 | 1131
Transportation in Multiple Lot | Mon 11-08-25 | Sat 11-10-25 | 60 days | NA | NA | Thu 19-02-26 | Fri 06-03-26 | 15 days | 0% | 1130 | 1.4121e+43
BMS | Fri 07-02-25 | Tue 24-03-26 | 395 days | Fri 14-11-25 | NA | Fri 14-11-25 | Mon 16-03-26 | 118 days | 0%
Basic Engineering | Fri 07-02-25 | Mon 10-03-25 | 30 days | Fri 14-11-25 | NA | Fri 14-11-25 | Mon 15-12-25 | 30 days | 0% | 54,57 | 1135
Order Process | Mon 10-03-25 | Tue 08-04-25 | 28 days | NA | NA | Mon 15-12-25 | Tue 13-01-26 | 28 days | 0%
RFQ | Mon 10-03-25 | Mon 17-03-25 | 7 days | NA | NA | Mon 15-12-25 | Mon 22-12-25 | 7 days | 0% | 1133 | 1136
Offer Receipt | Tue 18-03-25 | Tue 25-03-25 | 7 days | NA | NA | Mon 22-12-25 | Tue 30-12-25 | 7 days | 0% | 1135 | 1137
PO Release | Tue 25-03-25 | Tue 01-04-25 | 7 days | NA | NA | Tue 30-12-25 | Tue 06-01-26 | 7 days | 0% | 1136 | 1138
Payment | Tue 01-04-25 | Tue 08-04-25 | 7 days | NA | NA | Tue 06-01-26 | Tue 13-01-26 | 7 days | 0% | 1137 | 4061139
Detail Engineering | Tue 08-04-25 | Mon 09-06-25 | 60 days | NA | NA | Tue 13-01-26 | Mon 16-03-26 | 60 days | 0% | 1138 | 1657
Electrical Packages (220KVA Upto 415VAC) | Sat 22-02-25 | Fri 20-02-26 | 350 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 10-04-26 | 214 days | 20%
HV Electrical - Transformer HV 220/ 11 KVA - 50 MVA | Sat 22-02-25 | Mon 29-12-25 | 298 days | Mon 01-09-25 | NA | Mon 01-09-25 | Wed 18-03-26 | 191.88 days | 39%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Mon 15-09-25 | Mon 01-09-25 | Mon 15-09-25 | 14.5 days | 100% | 58 | 1144
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | Mon 15-09-25 | Wed 15-10-25 | Mon 15-09-25 | Wed 15-10-25 | 30.25 days | 100%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | Mon 15-09-25 | Sat 20-09-25 | Mon 15-09-25 | Sat 20-09-25 | 5.63 days | 100% | 1142 | 1145
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | Sat 20-09-25 | Wed 01-10-25 | Sat 20-09-25 | Wed 01-10-25 | 10.13 days | 100% | 1144 | 1146
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | Wed 01-10-25 | Fri 03-10-25 | Wed 01-10-25 | Fri 03-10-25 | 2.25 days | 100% | 1145 | 1147
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | Fri 03-10-25 | Wed 15-10-25 | Fri 03-10-25 | Wed 15-10-25 | 11.25 days | 100% | 1146 | 4061148
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | Fri 03-10-25 | Thu 13-11-25 | Fri 03-10-25 | Thu 13-11-25 | 32.38 days | 100% | 1147 | 1149
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Fri 03-10-25 | Thu 13-11-25 | Fri 03-10-25 | Thu 13-11-25 | 0 days | 100% | 1148 | 1150
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | Tue 21-10-25 | NA | Tue 21-10-25 | Sat 14-02-26 | 90 days | 0% | 1149 | 1151
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Sat 14-02-26 | Tue 03-03-26 | 15 days | 0% | 1150 | 1152
Transportation in Multiple Lot | Wed 12-11-25 | Thu 27-11-25 | 15 days | NA | NA | Tue 03-03-26 | Wed 18-03-26 | 15 days | 0% | 1151 | 1638
LV Electrical - Transformer LV (11KV to 400V/ 433V) | Sat 22-02-25 | Sat 11-10-25 | 223 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 30-01-26 | 146.5 days | 28%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Fri 05-09-25 | Mon 01-09-25 | Fri 05-09-25 | 5.5 days | 100% | 58,55 | 1156
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | Fri 05-09-25 | Sat 20-09-25 | Fri 05-09-25 | Sat 20-09-25 | 15.63 days | 100%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | Fri 05-09-25 | Mon 08-09-25 | Fri 05-09-25 | Mon 08-09-25 | 2.25 days | 100% | 1154 | 1157
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | Mon 08-09-25 | Wed 10-09-25 | Mon 08-09-25 | Wed 10-09-25 | 2.25 days | 100% | 1156 | 1158
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | Wed 10-09-25 | Fri 12-09-25 | Wed 10-09-25 | Fri 12-09-25 | 2.25 days | 100% | 1157 | 1159
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | Sat 13-09-25 | Sat 20-09-25 | Sat 13-09-25 | Sat 20-09-25 | 7.75 days | 100% | 1158 | 4061160
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | Tue 23-09-25 | Mon 13-10-25 | Tue 23-09-25 | Mon 13-10-25 | 20.13 days | 100% | 1159 | 1161
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Tue 23-09-25 | Mon 13-10-25 | Tue 23-09-25 | Mon 13-10-25 | 0 days | 100% | 1160 | 1162
Manufacturing Duration | Wed 25-06-25 | Tue 26-08-25 | 60 days | Mon 13-10-25 | NA | Mon 13-10-25 | Mon 15-12-25 | 60 days | 0% | 1161 | 1163
Inspection at Supplier End | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Mon 15-12-25 | Tue 30-12-25 | 15 days | 0% | 1162 | 1164
Transportation in Multiple Lot | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Tue 30-12-25 | Fri 30-01-26 | 30 days | 0% | 1163 | 1397SS+7 days,1459SS+7 days,1485SS+7 days,1500SS+7 days,1518SS+7 days,1579SS+7 days
HV Electrical - DG Set | Sat 22-02-25 | Fri 20-02-26 | 350 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 13-03-26 | 187 days | 44%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Fri 05-09-25 | Mon 01-09-25 | Fri 05-09-25 | 5.5 days | 100% | 58,55 | 1168
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | Fri 05-09-25 | Tue 23-09-25 | Fri 05-09-25 | Tue 23-09-25 | 17.88 days | 100%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | Fri 05-09-25 | Mon 08-09-25 | Fri 05-09-25 | Mon 08-09-25 | 2.25 days | 100% | 1166 | 1169
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | Mon 08-09-25 | Tue 16-09-25 | Mon 08-09-25 | Tue 16-09-25 | 7.88 days | 100% | 1168 | 1170
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | Tue 16-09-25 | Thu 18-09-25 | Tue 16-09-25 | Thu 18-09-25 | 2.25 days | 100% | 1169 | 1171
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | Thu 18-09-25 | Tue 23-09-25 | Thu 18-09-25 | Tue 23-09-25 | 4.5 days | 100% | 1170 | 4061172
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | Thu 18-09-25 | Mon 24-11-25 | Thu 18-09-25 | Mon 24-11-25 | 59.63 days | 100% | 1171 | 1173
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | Thu 18-09-25 | Mon 24-11-25 | Thu 18-09-25 | Mon 24-11-25 | 0 days | 100% | 1172 | 1174
Manufacturing Duration | Wed 25-06-25 | Mon 27-10-25 | 120 days | Thu 18-09-25 | NA | Thu 18-09-25 | Mon 26-01-26 | 60 days | 0% | 1173 | 1175
Inspection at Supplier End | Tue 28-10-25 | Wed 12-11-25 | 15 days | NA | NA | Mon 26-01-26 | Tue 10-02-26 | 15 days | 0% | 1174 | 1176
Transportation in Multiple Lot | Wed 12-11-25 | Tue 13-01-26 | 60 days | NA | NA | Tue 10-02-26 | Fri 13-03-26 | 30 days | 0% | 1175 | 1653SS+7 days
HV Electrical - AMF Panel | Sat 22-02-25 | Fri 26-09-25 | 208 days | Wed 01-10-25 | NA | Wed 01-10-25 | Thu 02-04-26 | 177.13 days | 16%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Wed 01-10-25 | Thu 30-10-25 | Wed 01-10-25 | Thu 30-10-25 | 29.13 days | 100% | 58,55 | 1180
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Thu 30-10-25 | Fri 28-11-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Thu 30-10-25 | Fri 07-11-25 | 7 days | 0% | 1178 | 1181
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Fri 07-11-25 | Fri 14-11-25 | 7 days | 0% | 1180 | 1182
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Fri 14-11-25 | Fri 21-11-25 | 7 days | 0% | 1181 | 1183
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Fri 21-11-25 | Fri 28-11-25 | 7 days | 0% | 1182 | 4061184
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Fri 28-11-25 | Mon 15-12-25 | 15 days | 0% | 1183 | 1185
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Mon 15-12-25 | Tue 30-12-25 | 15 days | 0% | 1184 | 1186
Manufacturing Duration | Wed 25-06-25 | Tue 26-08-25 | 60 days | NA | NA | Tue 30-12-25 | Mon 02-03-26 | 60 days | 0% | 1185 | 1187
Inspection at Supplier End | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Mon 02-03-26 | Wed 18-03-26 | 15 days | 0% | 1186 | 1188
Transportation in Multiple Lot | Thu 11-09-25 | Fri 26-09-25 | 15 days | NA | NA | Wed 18-03-26 | Thu 02-04-26 | 15 days | 0% | 1187 | 1640SS+7 days
HV Electical - Bus Bar | Sat 22-02-25 | Mon 27-10-25 | 238 days | Wed 01-10-25 | NA | Wed 01-10-25 | Thu 02-04-26 | 177.13 days | 16%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Wed 01-10-25 | Thu 30-10-25 | Wed 01-10-25 | Thu 30-10-25 | 29.13 days | 100% | 58,55 | 1192
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Thu 30-10-25 | Fri 28-11-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Thu 30-10-25 | Fri 07-11-25 | 7 days | 0% | 1190 | 1193
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Fri 07-11-25 | Fri 14-11-25 | 7 days | 0% | 1192 | 1194
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Fri 14-11-25 | Fri 21-11-25 | 7 days | 0% | 1193 | 1195
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Fri 21-11-25 | Fri 28-11-25 | 7 days | 0% | 1194 | 4061196
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Fri 28-11-25 | Mon 15-12-25 | 15 days | 0% | 1195 | 1197
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Mon 15-12-25 | Tue 30-12-25 | 15 days | 0% | 1196 | 1198
Manufacturing Duration | Wed 25-06-25 | Fri 26-09-25 | 90 days | NA | NA | Tue 30-12-25 | Mon 02-03-26 | 60 days | 0% | 1197 | 1199
Inspection at Supplier End | Fri 26-09-25 | Sat 11-10-25 | 15 days | NA | NA | Mon 02-03-26 | Wed 18-03-26 | 15 days | 0% | 1198 | 1200
Transportation in Multiple Lot | Sat 11-10-25 | Mon 27-10-25 | 15 days | NA | NA | Wed 18-03-26 | Thu 02-04-26 | 15 days | 0% | 1199 | 1399SS+7 days
HV Electrical - 11 HV Panel | Sat 22-02-25 | Mon 27-10-25 | 238 days | Wed 01-10-25 | NA | Wed 01-10-25 | Fri 10-04-26 | 184.75 days | 21%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Wed 01-10-25 | Thu 30-10-25 | Wed 01-10-25 | Thu 30-10-25 | 29.13 days | 100% | 58 | 1204
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | Sat 01-11-25 | NA | Sat 01-11-25 | Sat 06-12-25 | 34.38 days | 39%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | Sat 01-11-25 | Fri 14-11-25 | Sat 01-11-25 | Fri 14-11-25 | 13.38 days | 100% | 1202 | 1205
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | Fri 14-11-25 | NA | Fri 14-11-25 | Sat 22-11-25 | 7 days | 0% | 1204 | 1206
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Sat 22-11-25 | Sat 29-11-25 | 7 days | 0% | 1205 | 1207
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Sat 29-11-25 | Sat 06-12-25 | 7 days | 0% | 1206 | 4061208
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Sat 06-12-25 | Mon 22-12-25 | 15 days | 0% | 1207,55 | 1209
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Mon 22-12-25 | Wed 07-01-26 | 15 days | 0% | 1208 | 1210
Manufacturing Duration | Wed 25-06-25 | Fri 26-09-25 | 90 days | NA | NA | Wed 07-01-26 | Tue 10-03-26 | 60 days | 0% | 1209 | 1211
Inspection at Supplier End | Fri 26-09-25 | Sat 11-10-25 | 15 days | NA | NA | Tue 10-03-26 | Wed 25-03-26 | 15 days | 0% | 1210 | 12121213
Transportation in Multiple Lot | Sat 11-10-25 | Mon 27-10-25 | 15 days | NA | NA | Wed 25-03-26 | Fri 10-04-26 | 15 days | 0% | 1211 | 1641
Transportation of HT Panel - Inside Building | Sat 11-10-25 | Mon 27-10-25 | 15 days | NA | NA | Wed 25-03-26 | Fri 10-04-26 | 15 days | 0% | 1211 | 1398146015191540
HV Electrical - HV Cable | Sat 22-02-25 | Wed 12-11-25 | 253 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 30-01-26 | 146.5 days | 28%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1217
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | Wed 10-09-25 | Mon 13-10-25 | Wed 10-09-25 | Mon 13-10-25 | 32.5 days | 100%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | Wed 10-09-25 | Mon 15-09-25 | Wed 10-09-25 | Mon 15-09-25 | 4.5 days | 100% | 1215 | 1218
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | Mon 15-09-25 | Sat 20-09-25 | Mon 15-09-25 | Sat 20-09-25 | 5.63 days | 100% | 1217 | 1219
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | Sat 20-09-25 | Mon 29-09-25 | Sat 20-09-25 | Mon 29-09-25 | 7.88 days | 100% | 1218 | 1220
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | Mon 29-09-25 | Mon 13-10-25 | Mon 29-09-25 | Mon 13-10-25 | 13.5 days | 100% | 1219 | 4061221
Manufacturing Duration | Wed 25-06-25 | Tue 26-08-25 | 60 days | Mon 13-10-25 | NA | Mon 13-10-25 | Mon 15-12-25 | 60 days | 0% | 1220 | 1222
Inspection at Supplier End | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Mon 15-12-25 | Tue 30-12-25 | 15 days | 0% | 1221 | 1223
Transportation in Multiple Lot | Thu 11-09-25 | Wed 12-11-25 | 60 days | NA | NA | Tue 30-12-25 | Fri 30-01-26 | 30 days | 0% | 1222 | 1402SS+7 days,1462SS+7 days,1566SS+7 days,1642SS+7 days
HV Terminal Kit | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 02-01-26 | 120 days | 8%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1227
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1225 | 1228
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1227 | 1229
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1228 | 1230
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1229 | 4061231
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1230,55 | 1232
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Mon 10-11-25 | 15 days | 0% | 1231 | 1233
Manufacturing Duration | Wed 25-06-25 | Mon 11-08-25 | 45 days | NA | NA | Mon 10-11-25 | Thu 11-12-25 | 30 days | 0% | 1232 | 1234
Inspection at Supplier End | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Thu 11-12-25 | Thu 18-12-25 | 7 days | 0% | 1233 | 1235
Transportation in Multiple Lot | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Thu 18-12-25 | Fri 02-01-26 | 15 days | 0% | 1234 | 1403146315671640
LV Electrical - LV Panel | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Tue 27-01-26 | 143 days | 7%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1239
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1237 | 1240
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1239 | 1241
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1240 | 1242
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1241 | 4061243
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1242,55 | 1244
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Mon 10-11-25 | 15 days | 0% | 1243 | 1245
Manufacturing Duration | Wed 25-06-25 | Mon 11-08-25 | 45 days | NA | NA | Mon 10-11-25 | Fri 26-12-25 | 45 days | 0% | 1244 | 1246
Inspection at Supplier End | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Fri 26-12-25 | Sat 10-01-26 | 15 days | 0% | 1245 | 1247
Transportation in Multiple Lot | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Sat 10-01-26 | Tue 27-01-26 | 15 days | 0% | 1246 | 1.4001e+43
LV Electrical - BUS Duct & Support | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Sat 17-01-26 | 135 days | 7%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1251
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1249 | 1252
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1251 | 1253
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1252 | 1254
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1253 | 4061255
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1254,55 | 1256
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Mon 10-11-25 | 15 days | 0% | 1255 | 1257
Manufacturing Duration | Wed 25-06-25 | Mon 11-08-25 | 45 days | NA | NA | Mon 10-11-25 | Fri 26-12-25 | 45 days | 0% | 1256 | 1258
Inspection at Supplier End | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Fri 26-12-25 | Fri 02-01-26 | 7 days | 0% | 1257 | 1259
Transportation in Multiple Lot | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Fri 02-01-26 | Sat 17-01-26 | 15 days | 0% | 1258 | 1401
LV Electrical - UPS System | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 20-03-26 | 194.5 days | 13%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1263
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | Sat 01-11-25 | NA | Sat 01-11-25 | Tue 02-12-25 | 29.88 days | 30%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | Sat 01-11-25 | Mon 10-11-25 | Sat 01-11-25 | Mon 10-11-25 | 8.88 days | 100% | 1261 | 1264
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | Mon 10-11-25 | NA | Mon 10-11-25 | Tue 18-11-25 | 7 days | 0% | 1263 | 1265
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Tue 18-11-25 | Tue 25-11-25 | 7 days | 0% | 1264 | 1266
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Tue 25-11-25 | Tue 02-12-25 | 7 days | 0% | 1265 | 4061267
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Tue 02-12-25 | Wed 17-12-25 | 15 days | 0% | 1266,55 | 1268
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Wed 17-12-25 | Fri 02-01-26 | 15 days | 0% | 1267 | 1269
Manufacturing Duration | Wed 25-06-25 | Mon 11-08-25 | 45 days | NA | NA | Fri 02-01-26 | Wed 18-02-26 | 45 days | 0% | 1268 | 1270
Inspection at Supplier End | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Wed 18-02-26 | Thu 05-03-26 | 15 days | 0% | 1269 | 1271
Transportation in Multiple Lot | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Thu 05-03-26 | Fri 20-03-26 | 15 days | 0% | 1270 | 1.4041e+39
LV Electrical - Cable Tray | Sat 22-02-25 | Tue 26-08-25 | 178 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 02-01-26 | 120 days | 8%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1275
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1273 | 1276
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1275 | 1277
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1276 | 1278
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1277 | 4061279
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1278,55 | 1280
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Mon 10-11-25 | 15 days | 0% | 1279 | 1281
Manufacturing Duration | Wed 25-06-25 | Fri 25-07-25 | 30 days | NA | NA | Mon 10-11-25 | Thu 11-12-25 | 30 days | 0% | 1280 | 1282
Inspection at Supplier End | Sat 26-07-25 | Mon 11-08-25 | 15 days | NA | NA | Thu 11-12-25 | Thu 18-12-25 | 7 days | 0% | 1281 | 1283
Transportation in Multiple Lot | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Thu 18-12-25 | Fri 02-01-26 | 15 days | 0% | 1282 | 1.4051e+35
LV Electrical - Cable | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 02-01-26 | 120 days | 8%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58,55 | 1287
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1285 | 1288
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1287 | 1289
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1288 | 1290
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1289 | 4061291
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1290 | 1292
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Mon 10-11-25 | 15 days | 0% | 1291 | 1293
Manufacturing Duration | Wed 25-06-25 | Mon 11-08-25 | 45 days | NA | NA | Mon 10-11-25 | Thu 11-12-25 | 30 days | 0% | 1292 | 1294
Inspection at Supplier End | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Thu 11-12-25 | Thu 18-12-25 | 7 days | 0% | 1293 | 1295
Transportation in Multiple Lot | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Thu 18-12-25 | Fri 02-01-26 | 15 days | 0% | 1294 | 1.4061e+35
LV Electrical - Lugs and Terminal | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 02-01-26 | 120 days | 8%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58,55 | 1299
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1297 | 1300
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1299 | 1301
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1300 | 1302
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1301 | 4061303
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1302 | 1304
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Mon 10-11-25 | 15 days | 0% | 1303 | 1305
Manufacturing Duration | Wed 25-06-25 | Mon 11-08-25 | 45 days | NA | NA | Mon 10-11-25 | Thu 11-12-25 | 30 days | 0% | 1304 | 1306
Inspection at Supplier End | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Thu 11-12-25 | Thu 18-12-25 | 7 days | 0% | 1305 | 1307
Transportation in Multiple Lot | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Thu 18-12-25 | Fri 02-01-26 | 15 days | 0% | 1306 | 1.4071e+35
Electrical ( Inside and Pehripheral ) | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Sat 17-01-26 | 135 days | 8%
Buidling Lighting Inside | Sat 22-02-25 | Tue 26-08-25 | 178 days | Mon 01-09-25 | NA | Mon 01-09-25 | Sat 17-01-26 | 135 days | 7%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1312
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1310 | 1313
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1312 | 1314
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1313 | 1315
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1314 | 4061316
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1315 | 1317
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Mon 10-11-25 | 15 days | 0% | 1316 | 1318
Manufacturing Duration | Wed 25-06-25 | Fri 25-07-25 | 30 days | NA | NA | Mon 10-11-25 | Fri 26-12-25 | 45 days | 0% | 1317 | 1319
Inspection at Supplier End | Sat 26-07-25 | Mon 11-08-25 | 15 days | NA | NA | Fri 26-12-25 | Fri 02-01-26 | 7 days | 0% | 1318 | 1320
Transportation in Multiple Lot | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Fri 02-01-26 | Sat 17-01-26 | 15 days | 0% | 1319 | 1.3941e+51
LV Electrical - Area Lighting | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Thu 08-01-26 | 125 days | 8%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1324
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1322 | 1325
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1324 | 1326
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1325 | 1327
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1326 | 4061328
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1327 | 1329
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Thu 30-10-25 | 5 days | 0% | 1328 | 1330
Manufacturing Duration | Wed 25-06-25 | Mon 11-08-25 | 45 days | NA | NA | Thu 30-10-25 | Tue 16-12-25 | 45 days | 0% | 1329 | 1331
Inspection at Supplier End | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Tue 16-12-25 | Tue 23-12-25 | 7 days | 0% | 1330 | 1332
Transportation in Multiple Lot | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Tue 23-12-25 | Thu 08-01-26 | 15 days | 0% | 1331 | 1572
LV Electrical - Earthing | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Sat 17-01-26 | 135 days | 7%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1336
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1334 | 1337
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1336 | 1338
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1337 | 1339
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1338 | 4061340
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Sat 25-10-25 | 15 days | 0% | 1339 | 1341
Drawing (GA + TDS) | Sat 24-05-25 | Wed 25-06-25 | 30 days | NA | NA | Sat 25-10-25 | Mon 10-11-25 | 15 days | 0% | 1340 | 1342
Manufacturing Duration | Wed 25-06-25 | Mon 11-08-25 | 45 days | NA | NA | Mon 10-11-25 | Fri 26-12-25 | 45 days | 0% | 1341 | 1343
Inspection at Supplier End | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Fri 26-12-25 | Fri 02-01-26 | 7 days | 0% | 1342 | 1344
Transportation in Multiple Lot | Tue 26-08-25 | Wed 10-09-25 | 15 days | NA | NA | Fri 02-01-26 | Sat 17-01-26 | 15 days | 0% | 1343 | 1571
Facility Setup | Sat 22-02-25 | Wed 10-09-25 | 193 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 26-12-25 | 113 days | 9%
CCTV Network | Sat 22-02-25 | Tue 26-08-25 | 178 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 26-12-25 | 113 days | 9%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1349
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1347 | 1350
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1349 | 1351
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1350 | 1352
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1351 | 4061353
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Mon 10-11-25 | 30 days | 0% | 1352 | 1354
Manufacturing Duration | Wed 25-06-25 | Fri 25-07-25 | 30 days | NA | NA | Mon 10-11-25 | Thu 11-12-25 | 30 days | 0% | 1353 | 1355
Transportation in Multiple Lot | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Thu 11-12-25 | Fri 26-12-25 | 15 days | 0% | 1354 | 1.4101e+51
Server & Switches | Sat 22-02-25 | Tue 26-08-25 | 178 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 26-12-25 | 113 days | 9%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1359
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1357 | 1360
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1359 | 1361
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1360 | 1362
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1361 | 4061363
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Mon 10-11-25 | 30 days | 0% | 1362 | 1364
Manufacturing Duration | Wed 25-06-25 | Fri 25-07-25 | 30 days | NA | NA | Mon 10-11-25 | Thu 11-12-25 | 30 days | 0% | 1363 | 1365
Transportation in Multiple Lot | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Thu 11-12-25 | Fri 26-12-25 | 15 days | 0% | 1364 | 1.4111e+47
Boom Barrier and Entry Access | Sat 22-02-25 | Tue 26-08-25 | 178 days | Mon 01-09-25 | NA | Mon 01-09-25 | Fri 26-12-25 | 113 days | 9%
Basic Engineering | Sat 22-02-25 | Wed 26-03-25 | 30 days | Mon 01-09-25 | Wed 10-09-25 | Mon 01-09-25 | Wed 10-09-25 | 10 days | 100% | 58 | 1369
Order Process | Wed 26-03-25 | Wed 23-04-25 | 28 days | NA | NA | Wed 10-09-25 | Thu 09-10-25 | 28 days | 0%
RFQ | Wed 26-03-25 | Wed 02-04-25 | 7 days | NA | NA | Wed 10-09-25 | Thu 18-09-25 | 7 days | 0% | 1367 | 1370
Offer Receipt | Wed 02-04-25 | Wed 09-04-25 | 7 days | NA | NA | Thu 18-09-25 | Thu 25-09-25 | 7 days | 0% | 1369 | 1371
PO Release | Wed 09-04-25 | Wed 16-04-25 | 7 days | NA | NA | Thu 25-09-25 | Thu 02-10-25 | 7 days | 0% | 1370 | 1372
Payment | Wed 16-04-25 | Wed 23-04-25 | 7 days | NA | NA | Thu 02-10-25 | Thu 09-10-25 | 7 days | 0% | 1371 | 4061373
Detail Engineering | Thu 24-04-25 | Sat 24-05-25 | 30 days | NA | NA | Thu 09-10-25 | Mon 10-11-25 | 30 days | 0% | 1372 | 1374
Manufacturing Duration | Wed 25-06-25 | Fri 25-07-25 | 30 days | NA | NA | Mon 10-11-25 | Thu 11-12-25 | 30 days | 0% | 1373 | 1375
Transportation in Multiple Lot | Mon 11-08-25 | Tue 26-08-25 | 15 days | NA | NA | Thu 11-12-25 | Fri 26-12-25 | 15 days | 0% | 1374 | 1.4092e+19
Process Tool - Purchase to Supply | Fri 22-11-24 | Fri 12-09-25 | 284 days | Thu 23-10-25 | NA | Thu 23-10-25 | Mon 06-04-26 | 159 days | 4%
Tool Set - 4.8GW | Fri 22-11-24 | Mon 28-07-25 | 239 days | Thu 23-10-25 | NA | Thu 23-10-25 | Mon 06-04-26 | 159 days | 1%
PO Release | Fri 22-11-24 | Fri 13-12-24 | 20 days | Thu 23-10-25 | Thu 23-10-25 | Thu 23-10-25 | Thu 23-10-25 | 1 day | 100% | 51
Adv Payment | Sat 07-12-24 | Sat 28-12-24 | 20 days | Fri 24-10-25 | Fri 24-10-25 | Fri 24-10-25 | Fri 24-10-25 | 1 day | 100% | 52 | 1380
Manufacturing Duration | Wed 29-01-25 | Mon 02-06-25 | 120 days | Fri 24-10-25 | NA | Fri 24-10-25 | Fri 26-12-25 | 60 days | 0% | 1379 | 1382SS+10 days,1381
Inspection of Tool Set 4.8GW at Supplier End | Mon 02-06-25 | Thu 03-07-25 | 30 days | NA | NA | Fri 26-12-25 | Mon 26-01-26 | 30 days | 0% | 1380
International Transit of Tool Set - 4.8GW | Mon 12-05-25 | Fri 27-06-25 | 45 days | NA | NA | Tue 03-02-26 | Thu 05-03-26 | 30 days | 0% | 1380SS+10 days,37 | 1383SS+30 days
Domestic Delivery of Tool Set - 4.8GW | Wed 11-06-25 | Mon 28-07-25 | 45 days | NA | NA | Thu 05-03-26 | Mon 06-04-26 | 30 days | 0% | 1382SS+30 days | 1454SS+5 days
Tool Set - 2.3GW | Fri 22-11-24 | Fri 12-09-25 | 284 days | Mon 10-11-25 | NA | Mon 10-11-25 | Mon 06-04-26 | 142.13 days | 6%
PO Release | Fri 22-11-24 | Fri 13-12-24 | 20 days | Mon 10-11-25 | Tue 18-11-25 | Mon 10-11-25 | Tue 18-11-25 | 8.88 days | 100% | 51
Adv Payment | Sat 07-12-24 | Sat 28-12-24 | 20 days | Wed 19-11-25 | Wed 19-11-25 | Wed 19-11-25 | Wed 19-11-25 | 1 day | 100% | 52 | 1387
Manufacturing Duration | Wed 29-01-25 | Mon 02-06-25 | 120 days | Thu 20-11-25 | NA | Thu 20-11-25 | Wed 21-01-26 | 60 days | 0% | 1386 | 1389SS+10 days,1388
Inspection of Tool Set 2.3GW at Supplier End | Mon 02-06-25 | Thu 03-07-25 | 30 days | NA | NA | Wed 21-01-26 | Fri 20-02-26 | 30 days | 0% | 1387
International Transit of Tool Set 2.3GW | Mon 12-05-25 | Wed 13-08-25 | 90 days | NA | NA | Tue 03-02-26 | Thu 05-03-26 | 30 days | 0% | 1387SS+10 days,37 | 1390SS+30 days
Domestic Delivery of Tool Set 2.3GW | Wed 11-06-25 | Fri 12-09-25 | 90 days | NA | NA | Thu 05-03-26 | Mon 06-04-26 | 30 days | 0% | 1389SS+30 days | 1455SS+5 days
Utilities - Installation | Fri 27-06-25 | Sat 18-04-26 | 285 days | NA | NA | Mon 01-09-25 | Sat 20-06-26 | 283 days | 0%
Main Building Phase 1 | Mon 03-11-25 | Sat 18-04-26 | 161 days | NA | NA | Sat 13-12-25 | Wed 27-05-26 | 158.25 days | 0%
Electrical Installation | NA | NA | 0 days | NA | NA | Fri 02-01-26 | Wed 27-05-26 | 139 days | 0%
Rafter Lighting - Installation | Mon 03-11-25 | Fri 19-12-25 | 45 days | NA | NA | Mon 19-01-26 | Thu 05-03-26 | 45 days | 0% | 981320 | 1661
Plenum Light - Installation | Mon 03-11-25 | Fri 19-12-25 | 45 days | NA | NA | Mon 19-01-26 | Thu 05-03-26 | 45 days | 0% | 981320 | 1661
Clean Room Light - Installation | Mon 03-11-25 | Fri 19-12-25 | 45 days | NA | NA | Mon 19-01-26 | Thu 05-03-26 | 45 days | 0% | 981320 | 1661
LV Transformer -Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Tue 06-01-26 | Thu 22-01-26 | 15 days | 0% | 1164SS+7 days,98 | 1661
HT Panel Installation | Mon 03-11-25 | Fri 19-12-25 | 45 days | NA | NA | Fri 10-04-26 | Wed 27-05-26 | 45 days | 0% | 981213 | 1661
HV Bus Bar - Installation | Mon 03-11-25 | Fri 19-12-25 | 45 days | NA | NA | Wed 25-03-26 | Fri 24-04-26 | 30 days | 0% | 1200SS+7 days,98 | 1661
LV Panel - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Tue 27-01-26 | Thu 26-02-26 | 30 days | 0% | 1247,98 | 1661
LV Bus Duct - Installation | Mon 03-11-25 | Wed 04-02-26 | 90 days | NA | NA | Mon 19-01-26 | Tue 21-04-26 | 90 days | 0% | 1259,98 | 1661
HV Cable - Installation | Mon 03-11-25 | Sat 03-01-26 | 60 days | NA | NA | Tue 06-01-26 | Tue 10-03-26 | 60 days | 0% | 1223SS+7 days,98 | 1661
HV Terminal Kit - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Fri 02-01-26 | Sat 17-01-26 | 15 days | 0% | 1235,98 | 1661
UPS System - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 20-03-26 | Tue 21-04-26 | 30 days | 0% | 1271,98 | 1661
LV - Cable Tray - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1283,98 | 1661
LV - Cable - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1295,98 | 1661
LV - Lugs and Terminal - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1307,98 | 1661
Facility Installation | NA | NA | 0 days | NA | NA | Sat 13-12-25 | Mon 06-04-26 | 109.63 days | 0%
Installation - Boom Barrier and Entry Access | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1375,98 | 1661
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1355,98 | 1661
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1365,98 | 1661
Fire System - Installation | Mon 03-11-25 | Fri 19-12-25 | 45 days | NA | NA | Fri 06-03-26 | Mon 06-04-26 | 30 days | 0% | 981131 | 1661
Fire Door - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Mon 22-12-25 | Wed 21-01-26 | 30 days | 0% | 98108 | 1661
Rooling Shutter - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Sat 13-12-25 | Wed 14-01-26 | 30 days | 0% | 98115 | 1661
Docklever - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Sat 13-12-25 | Wed 14-01-26 | 30 days | 0% | 98122 | 1661
Material Lift Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Sat 13-12-25 | Wed 14-01-26 | 30 days | 0% | 98129 | 1661
Piping Installation | NA | NA | 0 days | NA | NA | Sat 13-12-25 | Mon 13-04-26 | 115.75 days | 0%
DI Water Piping - Installation | Wed 19-11-25 | Sat 20-12-25 | 30 days | NA | NA | Thu 12-03-26 | Mon 13-04-26 | 30 days | 0% | 788SS+7 days,98 | 1661
Bulk Gas Piping - Installation | Sat 07-03-26 | Tue 07-04-26 | 30 days | NA | NA | Wed 21-01-26 | Fri 20-02-26 | 30 days | 0% | 813SS+7 days,98 | 1661
Gas System Piping - Installation | Sat 03-01-26 | Wed 04-02-26 | 30 days | NA | NA | Sat 13-12-25 | Wed 14-01-26 | 30 days | 0% | 862SS+7 days,98 | 1661
Pen Piping - Installation | Wed 19-11-25 | Sat 20-12-25 | 30 days | NA | NA | Tue 06-01-26 | Fri 06-02-26 | 30 days | 0% | 874SS+7 days,98 | 1661
CDA Piping - Installation | Wed 05-11-25 | Fri 05-12-25 | 30 days | NA | NA | Sat 13-12-25 | Wed 14-01-26 | 30 days | 0% | 923SS+7 days,98 | 1661
PCW_ Piping - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Thu 19-02-26 | Tue 07-04-26 | 45 days | 0% | 1009SS+7 days,98 | 1661
HVAC & PCW | NA | NA | 0 days | NA | NA | Wed 24-12-25 | Tue 07-04-26 | 100.13 days | 0%
HVAC_AHU - Installation | Wed 19-11-25 | Tue 20-01-26 | 60 days | NA | NA | Wed 21-01-26 | Tue 24-03-26 | 60 days | 0% | 948SS+7 days,98 | 1426SS+30 days
HVAC_AHU - Testing & Commisioning | Sat 20-12-25 | Tue 20-01-26 | 30 days | NA | NA | Sat 21-02-26 | Tue 24-03-26 | 30 days | 0% | 1425SS+30 days | 1661
HVAC_AHU - Low Side - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Wed 28-01-26 | Mon 16-03-26 | 45 days | 0% | 960SS+7 days,98 | 1428SS+30 days
HVAC_AHU - Low Side - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Sat 28-02-26 | Mon 16-03-26 | 15 days | 0% | 1427SS+30 days | 1661
HVAC_AHU - High Side - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Sat 07-02-26 | Thu 26-03-26 | 45 days | 0% | 972SS+7 days,98 | 1430SS+30 days
HVAC_AHU - High Side - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Wed 11-03-26 | Thu 26-03-26 | 15 days | 0% | 1429SS+30 days | 1661
Chiller - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Wed 24-12-25 | Mon 09-02-26 | 45 days | 0% | 985SS+7 days,98 | 1432SS+30 days
Chiller - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Fri 23-01-26 | Mon 09-02-26 | 15 days | 0% | 1431SS+30 days | 1661
PCW_HVAC - Pump - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Tue 27-01-26 | Sat 14-03-26 | 45 days | 0% | 997SS+7 days,98 | 1434SS+30 days
PCW_HVAC - Pump - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Fri 27-02-26 | Sat 14-03-26 | 15 days | 0% | 1433SS+30 days | 1661
PCW_ Heat Exchanger - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Thu 19-02-26 | Tue 07-04-26 | 45 days | 0% | 1021SS+7 days,98 | 1436SS+30 days
PCW_ Heat Exchanger - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Sat 21-03-26 | Tue 07-04-26 | 15 days | 0% | 1435SS+30 days | 1661
Exhaust - Installation & Commisioining | NA | NA | 0 days | NA | NA | Fri 30-01-26 | Sat 18-04-26 | 75 days | 0%
Exhuast_Blower- Installation | Wed 05-11-25 | Tue 06-01-26 | 60 days | NA | NA | Sat 07-02-26 | Thu 26-03-26 | 45 days | 0% | 1034SS+7 days,98 | 1439SS+30 days
Exhuast_Blower - Testing & Commisioning | Fri 05-12-25 | Tue 06-01-26 | 30 days | NA | NA | Wed 11-03-26 | Thu 26-03-26 | 15 days | 0% | 1438SS+30 days | 1661
Exhuast_Scrubber - Installation | Wed 05-11-25 | Tue 06-01-26 | 60 days | NA | NA | Tue 03-03-26 | Sat 18-04-26 | 45 days | 0% | 1046SS+7 days,98 | 1441SS+30 days
Exhuast_Scrubber - Testing & Commisioning | Fri 05-12-25 | Tue 06-01-26 | 30 days | NA | NA | Fri 03-04-26 | Sat 18-04-26 | 15 days | 0% | 1440SS+30 days | 1661
Exhaust_Plastic Ducting - Installation | Wed 05-11-25 | Tue 06-01-26 | 60 days | NA | NA | Tue 03-03-26 | Sat 18-04-26 | 45 days | 0% | 1058SS+7 days,98 | 1661
Exhaust_Metallic Ducting - Installation | Wed 05-11-25 | Fri 06-02-26 | 90 days | NA | NA | Fri 30-01-26 | Wed 18-03-26 | 45 days | 0% | 1070SS+7 days,98 | 1661
Clean Room Installation & Commisioining | NA | NA | 0 days | NA | NA | Mon 15-12-25 | Mon 04-05-26 | 135 days | 0%
Wall Ceiling & Door - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Mon 15-12-25 | Wed 18-03-26 | 90 days | 0% | 1083SS+7 days,98 | 1446SS+30 days,1447,1451SS+45 days
Wall Ceiling & Door - Finishing | Sat 20-12-25 | Wed 31-12-25 | 10 days | NA | NA | Thu 15-01-26 | Sat 24-01-26 | 10 days | 0% | 1445SS+30 days | 14521661
Fan_Filter_Unit - Installation | Fri 20-02-26 | Tue 24-03-26 | 30 days | NA | NA | Wed 18-03-26 | Sat 18-04-26 | 30 days | 0% | 1095SS+7 days,1445 | 1448SS+30 days
Fan_Filter_Unit - Testing & Commisioning | Tue 24-03-26 | Wed 08-04-26 | 15 days | NA | NA | Sat 18-04-26 | Mon 04-05-26 | 15 days | 0% | 1447SS+30 days | 1661
Air Shower - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Mon 09-03-26 | Wed 08-04-26 | 30 days | 0% | 1107SS+7 days,98 | 1450SS+30 days
Air Shower - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Wed 08-04-26 | Fri 24-04-26 | 15 days | 0% | 1449SS+30 days | 1661
Epoxy - Installation as per Zone | Mon 05-01-26 | Wed 08-04-26 | 90 days | NA | NA | Fri 30-01-26 | Thu 02-04-26 | 60 days | 0% | 1119SS+7 days,98,1445SS+45 days | 1452,1454SS+30 days,1455SS+30 days
Epoxy - Finishing | Wed 08-04-26 | Sat 18-04-26 | 10 days | NA | NA | Thu 02-04-26 | Mon 13-04-26 | 10 days | 0% | 14511446 | 1661
Tool Move In - Installation | NA | NA | 0 days | NA | NA | Wed 11-03-26 | Mon 27-04-26 | 45 days | 0%
Tool Set 1 Move In | Thu 05-02-26 | Tue 24-03-26 | 45 days | NA | NA | Wed 11-03-26 | Mon 27-04-26 | 45 days | 0% | 1383SS+5 days,1451SS+30 days | 1661SS+7 days
Tool Set 2 Move In | Thu 05-02-26 | Tue 24-03-26 | 45 days | NA | NA | Wed 11-03-26 | Mon 27-04-26 | 45 days | 0% | 1390SS+5 days,1451SS+30 days | 1661SS+7 days
ETP | Mon 03-11-25 | Sat 03-01-26 | 60 days | NA | NA | Mon 23-02-26 | Wed 27-05-26 | 90 days | 0%
Electrical Installation | NA | NA | 0 days? | NA | NA | Mon 23-02-26 | Mon 11-05-26 | 75 days | 0%
Rafter Lighting - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 1511320
LV Transformer -Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Mon 23-02-26 | Tue 10-03-26 | 15 days | 0% | 1164SS+7 days,151
HT Panel Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 10-04-26 | Mon 11-05-26 | 30 days | 0% | 1511213
LV Panel - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 1247151
HV Cable - Installation | Mon 03-11-25 | Sat 03-01-26 | 60 days | NA | NA | Mon 23-02-26 | Sat 25-04-26 | 60 days | 0% | 1223SS+7 days,151
HV Terminal Kit - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Mon 23-02-26 | Tue 10-03-26 | 15 days | 0% | 1235151
UPS System - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 20-03-26 | Tue 21-04-26 | 30 days | 0% | 1271151
LV - Cable Tray - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 1283151
LV - Cable - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 1295151
LV - Lugs and Terminal - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 1307151
Facility Installation | NA | NA | 0 days? | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0%
Fire System Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Fri 06-03-26 | Sat 21-03-26 | 15 days | 0% | 1511131
Emergency_Door - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Mon 23-02-26 | Tue 10-03-26 | 15 days | 0% | 151161
Rolling Shutter - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Mon 23-02-26 | Tue 10-03-26 | 15 days | 0% | 151168
Dockleveler - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Mon 23-02-26 | Tue 10-03-26 | 15 days | 0% | 151175
ETO_Crane - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Mon 23-02-26 | Tue 10-03-26 | 15 days | 0% | 151182
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 1355151
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 1365151
Water Packages | NA | NA | 0 days? | NA | NA | Mon 23-02-26 | Wed 27-05-26 | 90 days | 0%
Water Package - ( UPW/ETP/ ZLD/ DI) - Installation | Wed 05-11-25 | Fri 06-02-26 | 90 days | NA | NA | Mon 23-02-26 | Sat 25-04-26 | 60 days | 0% | 719SS+7 days,151 | 1478SS+30 days
Water Package - ( UPW/ETP/ ZLD/ DI) - Testing & Commisioning | Fri 05-12-25 | Sat 21-02-26 | 75 days | NA | NA | Wed 25-03-26 | Wed 27-05-26 | 60 days | 0% | 1477SS+30 days
Water Package (Lime Liquid Handlling Dosing Sytem) - Installation | Wed 05-11-25 | Fri 05-12-25 | 30 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 731SS+7 days,151 | 1480
Water Package (Lime Liquid Handlling Dosing Sytem) - Testing & Commisioning | Fri 05-12-25 | Tue 06-01-26 | 30 days | NA | NA | Wed 25-03-26 | Fri 10-04-26 | 15 days | 0% | 1479
Water Package (Solid Lime Handling System Dosing) - Installation | Wed 05-11-25 | Fri 05-12-25 | 30 days | NA | NA | Mon 23-02-26 | Wed 25-03-26 | 30 days | 0% | 743SS+7 days,151 | 1482SS+30 days
Water Package (Solid Lime Handling System Dosing) - Testing & Commisioning | Fri 05-12-25 | Tue 06-01-26 | 30 days | NA | NA | Wed 25-03-26 | Sat 25-04-26 | 30 days | 0% | 1481SS+30 days
Chemical Yard | Thu 24-07-25 | Sat 11-10-25 | 77 days | NA | NA | Fri 09-01-26 | Tue 21-04-26 | 97.63 days | 0%
Rafter Lighting | Tue 26-08-25 | Fri 26-09-25 | 30 days | NA | NA | Mon 19-01-26 | Wed 18-02-26 | 30 days | 0% | 3031320
LV Transformer -Installation | Thu 18-09-25 | Fri 03-10-25 | 15 days | NA | NA | Fri 09-01-26 | Mon 26-01-26 | 15 days | 0% | 1164SS+7 days,303
LV Panel - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Tue 27-01-26 | Thu 26-02-26 | 30 days | 0% | 1247303
UPS System - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Fri 20-03-26 | Tue 21-04-26 | 30 days | 0% | 1271303
LV - Cable Tray - Installation | Tue 26-08-25 | Fri 26-09-25 | 30 days | NA | NA | Fri 09-01-26 | Tue 10-02-26 | 30 days | 0% | 1283303
LV - Cable - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Fri 09-01-26 | Tue 10-02-26 | 30 days | 0% | 1295303
LV - Lugs and Terminal - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Fri 09-01-26 | Tue 10-02-26 | 30 days | 0% | 1307303
Fire System - Installation | Thu 24-07-25 | Fri 08-08-25 | 15 days | NA | NA | Fri 06-03-26 | Sat 21-03-26 | 15 days | 0% | 3031131
Emergency_Door - Installation | Thu 24-07-25 | Fri 08-08-25 | 15 days | NA | NA | Fri 09-01-26 | Mon 26-01-26 | 15 days | 0% | 303313
Rolling Shutter - Installation | Fri 25-07-25 | Sat 09-08-25 | 15 days | NA | NA | Fri 09-01-26 | Mon 26-01-26 | 15 days | 0% | 303320
Docklever - Installation | Fri 25-07-25 | Sat 09-08-25 | 15 days | NA | NA | Fri 09-01-26 | Mon 26-01-26 | 15 days | 0% | 303327
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Fri 09-01-26 | Tue 10-02-26 | 30 days | 0% | 1355303
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Fri 09-01-26 | Tue 10-02-26 | 30 days | 0% | 1365303
Installation - Chemical System | Wed 05-11-25 | Fri 06-02-26 | 90 days | NA | NA | Tue 03-03-26 | Thu 02-04-26 | 30 days | 0% | 850SS+7 days,303
Gas Yard | Thu 24-07-25 | Sat 11-10-25 | 77 days | NA | NA | Thu 15-01-26 | Tue 21-04-26 | 92.75 days | 0%
Rafter Lighting | Tue 26-08-25 | Fri 26-09-25 | 30 days | NA | NA | Mon 19-01-26 | Wed 18-02-26 | 30 days | 0% | 3491320
LV Transformer -Installation | Thu 18-09-25 | Fri 03-10-25 | 15 days | NA | NA | Thu 15-01-26 | Fri 30-01-26 | 15 days | 0% | 1164SS+7 days,349
LV Panel - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Tue 27-01-26 | Thu 26-02-26 | 30 days | 0% | 1247349
UPS System - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Fri 20-03-26 | Tue 21-04-26 | 30 days | 0% | 1271349
LV - Cable Tray - Installation | Tue 26-08-25 | Fri 26-09-25 | 30 days | NA | NA | Thu 15-01-26 | Sat 14-02-26 | 30 days | 0% | 1283349
LV - Cable - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Thu 15-01-26 | Sat 14-02-26 | 30 days | 0% | 1295349
LV - Lugs and Terminal - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Thu 15-01-26 | Sat 14-02-26 | 30 days | 0% | 1307349
Fire System - Installation | Thu 24-07-25 | Fri 08-08-25 | 15 days | NA | NA | Fri 06-03-26 | Sat 21-03-26 | 15 days | 0% | 3491131
Door - Installation | Fri 25-07-25 | Sat 09-08-25 | 15 days | NA | NA | Thu 15-01-26 | Fri 30-01-26 | 15 days | 0% | 349359
Rolling Shutter - Installation | Thu 24-07-25 | Fri 08-08-25 | 15 days | NA | NA | Thu 15-01-26 | Fri 30-01-26 | 15 days | 0% | 349366
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Thu 15-01-26 | Sat 14-02-26 | 30 days | 0% | 1355349
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Thu 15-01-26 | Sat 14-02-26 | 30 days | 0% | 1365349
Bullk Gas System - Installation | Wed 05-11-25 | Fri 06-02-26 | 90 days | NA | NA | Thu 15-01-26 | Sat 14-02-26 | 30 days | 0% | 825SS+7 days,349 | 1512SS+30 days
Bullk Gas System - Testing & Commisioning | Fri 05-12-25 | Sat 21-02-26 | 75 days | NA | NA | Sat 14-02-26 | Tue 03-03-26 | 15 days | 0% | 1511SS+30 days
NH3(Ammonia) - Decanting System - Installation | Wed 05-11-25 | Fri 06-02-26 | 90 days | NA | NA | Tue 24-02-26 | Thu 26-03-26 | 30 days | 0% | 837SS+7 days,349 | 1514SS+30 days
NH3(Ammonia) - Decanting System - Testing & Commisioning | Fri 05-12-25 | Sat 21-02-26 | 75 days | NA | NA | Thu 26-03-26 | Sat 11-04-26 | 15 days | 0% | 1513SS+30 days
PCW Building | Wed 27-08-25 | Sat 07-03-26 | 186 days | NA | NA | Mon 20-04-26 | Sat 20-06-26 | 60 days | 0%
Electrical Installation | NA | NA | 0 days? | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0%
Rafter Lighting | Wed 27-08-25 | Sat 27-09-25 | 30 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 3821320
LV Transformer -Installation | Thu 18-09-25 | Fri 03-10-25 | 15 days | NA | NA | Mon 20-04-26 | Tue 05-05-26 | 15 days | 0% | 1164SS+7 days,382
HT Panel Installation | Tue 28-10-25 | Thu 27-11-25 | 30 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 3821213
LV Panel - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1247382
UPS System - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1271382
LV - Cable Tray - Installation | Wed 27-08-25 | Sat 27-09-25 | 30 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1283382
LV - Cable - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1295382
LV - Lugs and Terminal - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1307382
Facility - Installation | NA | NA | 0 days? | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0%
Fire System - Installation | Wed 27-08-25 | Thu 11-09-25 | 15 days | NA | NA | Mon 20-04-26 | Tue 05-05-26 | 15 days | 0% | 3821131
Emergency Door - Installation | Wed 27-08-25 | Thu 11-09-25 | 15 days | NA | NA | Mon 20-04-26 | Tue 05-05-26 | 15 days | 0% | 382391
Rolling Shutter - Installation | Wed 27-08-25 | Thu 11-09-25 | 15 days | NA | NA | Mon 20-04-26 | Tue 05-05-26 | 15 days | 0% | 382398
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1355382
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1365382
Chiller - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 985SS+7 days,382 | 1532SS+30 days
Chiller - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1531SS+30 days
PCW_HVAC - Pump - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 997SS+7 days,382 | 1534SS+30 days
PCW_HVAC - Pump - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1533SS+30 days
PCW_ Piping - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1009SS+7 days,382
PCW_ Heat Exchanger - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 1021SS+7 days,382 | 1537SS+30 days
PCW_ Heat Exchanger - Testing & Commisioning | Sat 20-12-25 | Sat 07-03-26 | 75 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1536SS+30 days
Air Compressor - Installation | Wed 05-11-25 | Fri 06-02-26 | 90 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 887382 | 1539
Air Compressor - Testing & Commisioning | Fri 05-12-25 | Sat 21-02-26 | 75 days | NA | NA | Thu 21-05-26 | Thu 28-05-26 | 7 days | 0% | 1538
Receiver Tank - Installation | Wed 05-11-25 | Fri 06-02-26 | 90 days | NA | NA | Mon 20-04-26 | Tue 05-05-26 | 15 days | 0% | 899382
CDA - Pre Receiver Piping - Installation | Wed 05-11-25 | Fri 06-02-26 | 90 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 911382
Soft Starter - Installation | Fri 05-12-25 | Mon 09-03-26 | 90 days | NA | NA | Mon 20-04-26 | Thu 21-05-26 | 30 days | 0% | 935382 | 1543
Soft Starter - Testing & Commisioning | Tue 06-01-26 | Wed 25-03-26 | 75 days | NA | NA | Thu 21-05-26 | Fri 05-06-26 | 15 days | 0% | 1542
N2 Yard | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Wed 15-04-26 | Mon 01-06-26 | 45 days | 0%
Rafter Lighting | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 4111320
HT Panel Installation | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 4111213
LV Panel - Installation | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 1247411
UPS System - Installation | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 1271411
LV - Cable Tray - Installation | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 1283411
LV - Cable - Installation | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 1295411
LV - Lugs and Terminal - Installation | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 1307411
Fire System - Installation | Thu 04-12-25 | Fri 19-12-25 | 15 days | NA | NA | Wed 15-04-26 | Thu 30-04-26 | 15 days | 0% | 4111131
Door - Installation | Thu 04-12-25 | Fri 19-12-25 | 15 days | NA | NA | Wed 15-04-26 | Thu 30-04-26 | 15 days | 0% | 420411
Rolling Shutter - Installation | Thu 04-12-25 | Fri 19-12-25 | 15 days | NA | NA | Wed 15-04-26 | Thu 30-04-26 | 15 days | 0% | 427411
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 1355411
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Wed 15-04-26 | Sat 16-05-26 | 30 days | 0% | 1365411
Bulk Gas Generation - N & O2 | Thu 04-12-25 | Fri 06-03-26 | 90 days | NA | NA | Wed 15-04-26 | Mon 01-06-26 | 45 days | 0% | 801SS+7 days,411 | 1558SS+30 days
Bulk Gas Generation - N & O2 - Testing & Commisioning | Sat 03-01-26 | Mon 23-03-26 | 75 days | NA | NA | Sat 16-05-26 | Sat 23-05-26 | 7 days | 0% | 1557SS+30 days
Peripherial Network | Tue 26-08-25 | Tue 07-04-26 | 216 days | NA | NA | Mon 20-10-25 | Sat 23-05-26 | 207.5 days | 0%
PNG Gas Piping | Wed 19-11-25 | Sat 20-12-25 | 30 days | NA | NA | Sat 28-02-26 | Wed 01-04-26 | 30 days | 0% | 764SS+7 days,639
DI Water Piping - Installation | Wed 19-11-25 | Sat 20-12-25 | 30 days | NA | NA | Thu 12-03-26 | Mon 13-04-26 | 30 days | 0% | 788SS+7 days,639
Bulk Gas Piping - Installation | Sat 07-03-26 | Tue 07-04-26 | 30 days | NA | NA | Wed 21-01-26 | Fri 20-02-26 | 30 days | 0% | 813SS+7 days,639
Chemical System Piping - Installation | Sat 03-01-26 | Wed 04-02-26 | 30 days | NA | NA | Fri 28-11-25 | Mon 29-12-25 | 30 days | 0% | 862SS+7 days,639
CDA Piping - Installation | Wed 05-11-25 | Fri 05-12-25 | 30 days | NA | NA | Mon 20-10-25 | Thu 20-11-25 | 30 days | 0% | 923SS+7 days,639
PCW_ Piping - Installation | Wed 19-11-25 | Fri 20-02-26 | 90 days | NA | NA | Thu 19-02-26 | Sat 23-05-26 | 90 days | 0% | 1009SS+7 days,639
HV Cable - Installation | Thu 18-09-25 | Wed 19-11-25 | 60 days | NA | NA | Tue 06-01-26 | Tue 10-03-26 | 60 days | 0% | 1223SS+7 days,639
HV Terminal Kit - Installation | Thu 11-09-25 | Fri 26-09-25 | 15 days | NA | NA | Fri 02-01-26 | Sat 17-01-26 | 15 days | 0% | 1235639
LV - Cable Tray - Installation | Tue 26-08-25 | Fri 26-09-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1283639
LV - Cable - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1295639
LV - Lugs and Terminal - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1307639
Earthing - Installation | Thu 11-09-25 | Mon 27-10-25 | 45 days | NA | NA | Mon 19-01-26 | Thu 05-03-26 | 45 days | 0% | 1344639
Area Light - Installation | Thu 11-09-25 | Mon 27-10-25 | 45 days | NA | NA | Thu 08-01-26 | Tue 24-02-26 | 45 days | 0% | 1332639
Installation - Boom Barrier and Entry Access | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1375639
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1355639
Raw Water Storage & Softner - Installation | Wed 05-11-25 | Fri 05-12-25 | 30 days | NA | NA | Fri 13-02-26 | Tue 17-03-26 | 30 days | 0% | 776SS+7 days | 1576SS+30 days
Raw Water Storage & Softner - Trial (Dry Run) | Fri 05-12-25 | Tue 06-01-26 | 30 days | NA | NA | Tue 17-03-26 | Wed 01-04-26 | 15 days | 0% | 1575SS+30 days
FG/RM | Mon 03-11-25 | Fri 19-12-25 | 45 days | NA | NA | Sat 13-12-25 | Sat 21-03-26 | 94.63 days | 0%
Rafter Lighting | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Mon 19-01-26 | Wed 18-02-26 | 30 days | 0% | 2041320
LV Transformer -Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Tue 06-01-26 | Thu 22-01-26 | 15 days | 0% | 1164SS+7 days,204
LV Panel - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Tue 27-01-26 | Thu 26-02-26 | 30 days | 0% | 1247204
LV - Cable Tray - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1283204
LV - Cable - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1295204
LV - Lugs and Terminal - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Fri 02-01-26 | Tue 03-02-26 | 30 days | 0% | 1307204
Fire System - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Fri 06-03-26 | Sat 21-03-26 | 15 days | 0% | 2041131
Emergency_Door - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Sat 03-01-26 | Mon 19-01-26 | 15 days | 0% | 204214
Rolling Shutter - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Sat 13-12-25 | Mon 29-12-25 | 15 days | 0% | 204221
Dock Leveler - Installation | Mon 03-11-25 | Tue 18-11-25 | 15 days | NA | NA | Sat 13-12-25 | Mon 29-12-25 | 15 days | 0% | 204228
Rack System - Installation | Mon 03-11-25 | Fri 19-12-25 | 45 days | NA | NA | Fri 16-01-26 | Wed 04-03-26 | 45 days | 0% | 204235
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1355204
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1365204
Scrap Yard ( Admin Building) | Sat 20-09-25 | Fri 21-11-25 | 60 days | NA | NA | Sat 03-01-26 | Tue 21-04-26 | 103.25 days | 0%
Rafter Lighting | Sat 20-09-25 | Tue 21-10-25 | 30 days | NA | NA | Wed 28-01-26 | Fri 27-02-26 | 30 days | 0% | 2511320
LV Panel - Installation | Sat 20-09-25 | Tue 21-10-25 | 30 days | NA | NA | Wed 28-01-26 | Fri 27-02-26 | 30 days | 0% | 1247251
UPS System - Installation | Sat 20-09-25 | Tue 21-10-25 | 30 days | NA | NA | Fri 20-03-26 | Tue 21-04-26 | 30 days | 0% | 1271251
LV - Cable Tray - Installation | Sat 20-09-25 | Tue 21-10-25 | 30 days | NA | NA | Wed 28-01-26 | Fri 27-02-26 | 30 days | 0% | 1283251
LV - Cable - Installation | Sat 20-09-25 | Tue 21-10-25 | 30 days | NA | NA | Wed 28-01-26 | Fri 27-02-26 | 30 days | 0% | 1295251
LV - Lugs and Terminal - Installation | Sat 20-09-25 | Tue 21-10-25 | 30 days | NA | NA | Wed 28-01-26 | Fri 27-02-26 | 30 days | 0% | 1307251
Fire System - Installation | Sat 20-09-25 | Mon 06-10-25 | 15 days | NA | NA | Fri 06-03-26 | Sat 21-03-26 | 15 days | 0% | 2511131
Emergency Door - Installation | Sat 20-09-25 | Mon 06-10-25 | 15 days | NA | NA | Wed 28-01-26 | Thu 12-02-26 | 15 days | 0% | 251260
Rolling Shutter - Installation | Sat 20-09-25 | Mon 06-10-25 | 15 days | NA | NA | Wed 28-01-26 | Thu 12-02-26 | 15 days | 0% | 251267
Elevator - Installation | Sat 20-09-25 | Tue 21-10-25 | 30 days | NA | NA | Wed 28-01-26 | Fri 27-02-26 | 30 days | 0% | 251274
Interiors - Installation | Sat 20-09-25 | Fri 21-11-25 | 60 days | NA | NA | Wed 28-01-26 | Tue 31-03-26 | 60 days | 0% | 251281
Installation - Boom Barrier and Entry Access | NA | NA | 0 days | NA | NA | Sat 03-01-26 | Wed 04-02-26 | 30 days | 0% | 1375281
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Sat 03-01-26 | Wed 04-02-26 | 30 days | 0% | 1355281
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Sat 03-01-26 | Wed 04-02-26 | 30 days | 0% | 1365281
Admin ( Main Office ) | Sat 27-09-25 | Fri 28-11-25 | 60 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0%
Rafter Lighting | Sat 27-09-25 | Tue 28-10-25 | 30 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 4431320
LV Panel - Installation | Sat 27-09-25 | Tue 28-10-25 | 30 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1247443
UPS System - Installation | Sat 27-09-25 | Tue 28-10-25 | 30 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1271443
Fire System - Installation | Sat 27-09-25 | Mon 13-10-25 | 15 days | NA | NA | Thu 21-05-26 | Fri 05-06-26 | 15 days | 0% | 4431131
Fire Door - Installation | Sat 27-09-25 | Mon 13-10-25 | 15 days | NA | NA | Thu 21-05-26 | Fri 05-06-26 | 15 days | 0% | 443452
Elevator - Installation | Sat 27-09-25 | Mon 13-10-25 | 15 days | NA | NA | Thu 21-05-26 | Fri 05-06-26 | 15 days | 0% | 443459
Interior - Installation | Sat 27-09-25 | Fri 28-11-25 | 60 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 443466
Installation - Boom Barrier and Entry Access | NA | NA | 0 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1375443
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1355443
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1365443
Canteen | Thu 24-07-25 | Sat 11-10-25 | 77 days | NA | NA | Tue 17-03-26 | Mon 18-05-26 | 60 days | 0%
Rafter Lighting | Tue 26-08-25 | Fri 26-09-25 | 30 days | NA | NA | Tue 17-03-26 | Thu 16-04-26 | 30 days | 0% | 4881320
LV Panel - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Tue 17-03-26 | Thu 16-04-26 | 30 days | 0% | 1247488
UPS System - Installation | Thu 11-09-25 | Sat 11-10-25 | 30 days | NA | NA | Fri 20-03-26 | Tue 21-04-26 | 30 days | 0% | 1271488
Fire System - Installation | Thu 24-07-25 | Fri 08-08-25 | 15 days | NA | NA | Tue 17-03-26 | Wed 01-04-26 | 15 days | 0% | 4881131
Emergency Door - Installation | Thu 24-07-25 | Fri 08-08-25 | 15 days | NA | NA | Tue 17-03-26 | Wed 01-04-26 | 15 days | 0% | 488498
Interior - Installation | Thu 24-07-25 | Wed 24-09-25 | 60 days | NA | NA | Tue 17-03-26 | Mon 18-05-26 | 60 days | 0% | 488505703
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Tue 17-03-26 | Thu 16-04-26 | 30 days | 0% | 1355488
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Tue 17-03-26 | Thu 16-04-26 | 30 days | 0% | 1365488
Security Building | Sat 27-09-25 | Fri 28-11-25 | 60 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0%
Rafter Lighting | Sat 27-09-25 | Tue 28-10-25 | 30 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 5211320
LV Panel - Installation | Sat 27-09-25 | Tue 28-10-25 | 30 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1247521
UPS System - Installation | Sat 27-09-25 | Tue 28-10-25 | 30 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1271521
Fire System - Installation | Sat 27-09-25 | Mon 13-10-25 | 15 days | NA | NA | Thu 21-05-26 | Fri 05-06-26 | 15 days | 0% | 5211131
Emergency Door - Installation | Sat 27-09-25 | Mon 13-10-25 | 15 days | NA | NA | Thu 21-05-26 | Fri 05-06-26 | 15 days | 0% | 521530
Interior - Installation | Sat 27-09-25 | Fri 28-11-25 | 60 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 521537
Installation - Boom Barrier and Entry Access | NA | NA | 0 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1375521
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1355521
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Thu 21-05-26 | Sat 20-06-26 | 30 days | 0% | 1365521
Sub Station | Fri 27-06-25 | Wed 28-01-26 | 208 days | NA | NA | Mon 01-09-25 | Wed 27-05-26 | 258.75 days | 0%
SubStation Civil Work Completion internal Termination | Fri 27-06-25 | Mon 28-07-25 | 30 days | NA | NA | Mon 01-09-25 | Wed 01-10-25 | 30 days | 0% | 684 | 1645
HV Electrical - Transformer HV 220/ 11 KVA - 50 MVA - Installation | Thu 27-11-25 | Fri 12-12-25 | 15 days | NA | NA | Wed 18-03-26 | Thu 02-04-26 | 15 days | 0% | 1152683 | 1639
HV Electrical - Transformer HV 220/ 11 KVA - 50 MVA - Trial (Dry Run) | Sat 13-12-25 | Mon 29-12-25 | 15 days | NA | NA | Thu 02-04-26 | Sat 18-04-26 | 15 days | 0% | 1638 | 1644
AMF Panel - Installation | Thu 18-09-25 | Sat 18-10-25 | 30 days | NA | NA | Wed 25-03-26 | Fri 24-04-26 | 30 days | 0% | 1188SS+7 days,683 | 1645
HV - HT Panel Sub Station Installation | Tue 28-10-25 | Thu 27-11-25 | 30 days | NA | NA | Fri 10-04-26 | Mon 11-05-26 | 30 days | 0% | 1212683 | 1645
HV Cable - Installation | Thu 18-09-25 | Sat 18-10-25 | 30 days | NA | NA | Tue 06-01-26 | Fri 06-02-26 | 30 days | 0% | 1223SS+7 days,683 | 1645
HV Terminal Kit - Installation | Thu 11-09-25 | Fri 26-09-25 | 15 days | NA | NA | Fri 02-01-26 | Sat 17-01-26 | 15 days | 0% | 1235683 | 1645
Transformer Intergration | Mon 29-12-25 | Tue 13-01-26 | 15 days | NA | NA | Sat 18-04-26 | Mon 04-05-26 | 15 days | 0% | 6831639 | 1645
Sub Station Charging | Tue 13-01-26 | Wed 28-01-26 | 15 days | NA | NA | Mon 11-05-26 | Wed 27-05-26 | 15 days | 0% | 1.6372e+26 | 1646
Sub Station Handover | Wed 28-01-26 | Wed 28-01-26 | 0 days | NA | NA | Wed 27-05-26 | Wed 27-05-26 | 0 days | 0% | 1645
Installation - CCTV Network | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1355683
Installation -Server & Switch | NA | NA | 0 days | NA | NA | Fri 26-12-25 | Tue 27-01-26 | 30 days | 0% | 1365683
PNG Yard | NA | NA | 0 days | NA | NA | Mon 22-12-25 | Fri 06-02-26 | 45 days | 0%
PNG Gas - Installation | Mon 03-11-25 | Wed 03-12-25 | 30 days | NA | NA | Mon 22-12-25 | Wed 07-01-26 | 15 days | 0% | 752672 | 1651SS+30 days
Trial (Dry Run) | Thu 04-12-25 | Sat 03-01-26 | 30 days | NA | NA | Thu 22-01-26 | Fri 06-02-26 | 15 days | 0% | 1650SS+30 days
DG Yard | NA | NA | 0 days | NA | NA | Tue 17-02-26 | Fri 27-03-26 | 37 days | 0%
HV Electrical - DG Set - Installation | Wed 19-11-25 | Thu 05-02-26 | 75 days | NA | NA | Tue 17-02-26 | Fri 20-03-26 | 30 days | 0% | 1176SS+7 days,661 | 1654
HV Electrical - DG Set - Trial (Dry Run) | Thu 05-02-26 | Fri 20-02-26 | 15 days | NA | NA | Fri 20-03-26 | Fri 27-03-26 | 7 days | 0% | 1653 | 1655
DG Handover | Fri 20-02-26 | Fri 20-02-26 | 0 days | NA | NA | Fri 27-03-26 | Fri 27-03-26 | 0 days | 0% | 1654
BMS | Sat 30-05-26 | Mon 15-06-26 | 15 days | NA | NA | Wed 27-05-26 | Mon 08-06-26 | 12 days | 0%
BMS - Installation | Thu 04-12-25 | Sat 07-03-26 | 90 days | NA | NA | Wed 27-05-26 | Wed 03-06-26 | 7 days | 0% | 1139,1661SS | 1658
BMS - Trial | Mon 05-01-26 | Tue 24-03-26 | 75 days | NA | NA | Wed 03-06-26 | Mon 08-06-26 | 5 days | 0% | 1657 | 1659
BMS - Handover | NA | NA | 0 days | NA | NA | Mon 08-06-26 | Mon 08-06-26 | 0 days | 0% | 1658 | 1663
Tool Hookup + First Cell Roll Out | Sat 18-04-26 | Tue 30-06-26 | 70 days | NA | NA | Wed 27-05-26 | Tue 30-06-26 | 33 days | 0%
Tool HookUp | Sat 18-04-26 | Fri 29-05-26 | 40 days | NA | NA | Wed 27-05-26 | Mon 22-06-26 | 25 days | 0% | 1454SS+7 days,1455SS+7 days,1394,1395,1396,1398,1412,1413,1414,1415,1416,1418,1419,1420,1421,1422,1426,1428,1430,1432,1434,1423,1436,1439,1441,1442,1443,1446,1448,1450,1452,1397,1399,1400,1401,1402,1403,1404,1405,1406,1407,1409,1410,1411 | 1663,1662,1657SS
First Cell Roll Out | Sat 30-05-26 | Tue 30-06-26 | 30 days | NA | NA | Mon 22-06-26 | Tue 30-06-26 | 8 days | 0% | 1661 | 1663,40FF,41FF,42FF,43FF,44FF,45FF,46FF
Handover for Production | Tue 30-06-26 | Tue 30-06-26 | 0 days | NA | NA | Tue 30-06-26 | Tue 30-06-26 | 0 days | 0% | 166116621659