## L1 Schedule
Task Name | Start | Finish | Duration
Naidupeta_TopCon-Cell_7.1GW | Tue 01-10-24 | Tue 30-06-26 | 615 days
Pre Project Approval | Tue 01-10-24 | Mon 31-03-25 | 175 days
DPR / Financial / Land details | Tue 01-10-24 | Mon 31-03-25 | 175 days
Feasibility Study | Sat 01-03-25 | Thu 20-03-25 | 19 days
Licensing & Approvals | Fri 06-12-24 | Tue 30-06-26 | 550 days
License & Drawing - Pre - approvals | Fri 06-12-24 | Mon 02-02-26 | 408days
License - Post-Construction approvals | Wed 29-04-26 | Tue 30-06-26 | 60 days
Basic Engineering | Sun 02-02-25 | Mon 04-08-25 | 175 days
Site Readiness Activity / Mobilization | Thu 01-05-25 | Mon 10-11-25 | 187days
Building | Thu 17-10-24 | Fri 05-06-26 | 576 days
Manufacturing Shed | Thu 17-10-24 | Mon 29-12-25 | 423 days
ETP Shed | Mon 31-03-25 | Tue 10-03-26 | 333 days
FG/ RM Shed | Mon 02-06-25 | Fri 16-01-26 | 221 days
Scrap Yard | Fri 01-08-25 | Thu 12-02-26 | 188 days
Chemical Yard | Mon 04-08-25 | Fri 16-01-26 | 160 days
Gas Yard | Mon 04-08-25 | Thu 22-01-26 | 165 days
PCW Yard | Wed 01-10-25 | Mon 27-04-26 | 201 days
N2 yard | Wed 01-10-25 | Thu 30-04-26 | 204 days
Admin Building | Wed 01-10-25 | Fri 05-06-26 | 239 days
Canteen Building | Wed 01-10-25 | Tue 24-03-26 | 168 days
Security / HR / Creche / OHC | Wed 01-10-25 | Fri 05-06-26 | 239 days
Compound Wall | Sun 01-06-25 | Sat 21-02-26 | 256 days
Road Network | Mon 01-09-25 | Sat 11-04-26 | 216 days
Parking Network | Mon 31-03-25 | Wed 31-12-25 | 266 days
Strom & Drain Network + Chemical Trench | Mon 01-09-25 | Wed 11-03-26 | 186 days
Bridge Network (Pipe Rack) | Mon 31-03-25 | Wed 31-12-25 | 266 days
Raw Water & Soft Water Tank | Mon 31-03-25 | Sat 06-09-25 | 155 days
DG Yard | Mon 01-09-25 | Tue 23-12-25 | 109 days
PNG Gas Yard | Mon 31-03-25 | Thu 07-08-25 | 125 days
Sub Station Yard | Mon 30-06-25 | Mon 02-02-26 | 208 days
Culvert & Gate Entry | Sun 01-06-25 | Sat 13-12-25 | 189 days
Utilities - Procurement | Mon 07-04-25 | Wed 15-04-26 | 360 days
Water Packages | Mon 07-04-25 | Fri 20-03-26 | 336 days
Gas Package | Thu 01-05-25 | Fri 03-04-26 | 325 days
Chemical Packages | Thu 01-05-25 | Thu 26-03-26 | 317days
Air Packages | Thu 01-05-25 | Wed 11-02-26 | 276 days
HVAC Packages | Wed 01-10-25 | Wed 04-03-26 | 1489 days
PCW Packages | Mon 15-09-25 | Wed 15-04-26 | 205 days
Exhaust Packages | Wed 01-10-25 | Thu 26-03-26 | 171 days
Clean Room | Mon 01-09-25 | Tue 17-03-26 | 191days
Fire Hydrant / Sprinkler / Alarm / Pump System | Thu 16-10-25 | Fri 06-03-26 | 136 days
BMS | Fri 14-11-25 | Mon 16-03-26 | 118 days
Electrical Packages (220KVA Upto 415VAC) | Mon 01-09-25 | Fri 10-04-26 | 214 days
Electrical ( Inside and Pehripheral ) | Mon 01-09-25 | Sat 17-01-26 | 135 days
Facility Setup | Mon 01-09-25 | Fri 26-12-25 | 113 days
Process Tool - Purchase to Supply | Thu 23-10-25 | Mon 06-04-26 | 159 days
Tool Set - 4.8GW | Thu 23-10-25 | Mon 06-04-26 | 159 days
Tool Set - 2.3GW | Mon 10-11-25 | Mon 06-04-26 | 142 days
Utilities - Installation | Mon 01-09-25 | Sat 20-06-26 | 283 days
Manufacturing Shed | Sat 13-12-25 | Wed 27-05-26 | 158days
ETP | Mon 23-02-26 | Wed 27-05-26 | 90 days
Chemical Yard | Fri 09-01-26 | Tue 21-04-26 | 97 days
Gas Yard | Thu 15-01-26 | Tue 21-04-26 | 92 days
PCW Building | Mon 20-04-26 | Sat 20-06-26 | 60 days
N2 Yard | Wed 15-04-26 | Mon 01-06-26 | 45 days
Peripherial Network | Mon 20-10-25 | Sat 23-05-26 | 207 days
FG/RM | Sat 13-12-25 | Sat 21-03-26 | 94 days
Scrap Yard | Sat 03-01-26 | Tue 21-04-26 | 103 days
Admin Buidling | Thu 21-05-26 | Sat 20-06-26 | 30 days
Canteen | Tue 17-03-26 | Mon 18-05-26 | 60 days
Security Building | Thu 21-05-26 | Sat 20-06-26 | 30 days
Sub Station | Mon 01-09-25 | Wed 27-05-26 | 258 days
PNG Yard | Mon 22-12-25 | Fri 06-02-26 | 45 days
DG Yard | Tue 17-02-26 | Fri 27-03-26 | 37 days
BMS | Wed 27-05-26 | Mon 08-06-26 | 12 days
Tool Hookup + First Cell Roll Out | Wed 27-05-26 | Tue 30-06-26 | 33 days
Tool Hookup | Wed 27-05-26 | Mon 22-06-26 | 25 days
First Cell Roll Out | Mon 22-06-26 | Tue 30-06-26 | 8 days
Handover for Production | Tue 30-06-26 | Tue 30-06-26 | 0 days