## Master - Civil + Utilities (hidden)
Packages | Procurement Team | Design Owner | Package | Vendor | Priority | Order Status - RFQ -Offer Receipt - Negotiation - PO Release - Adv Payment | PEB Drawing | Civil Drawing | PEB Progress - Primary - Secondary - Alignment - Roofing - Wall - Guttering - Mazzemine | Civil Progress - Footing - PCC - Back Fiiling - Plinth beam - Anchor Bolt - GSB - PCC - VDF | Accessories - Door - Shutter - Dock Leveler - Lift | Progress 10% - Order Finalize 20% - PEB Drawing 30% - Civil Drawing 40% - Material Delivery 90% - Execution 95% - Accessories 100% - Handover | Remarks | Zone
Building | Raju | RajaShekar | Main Building - Phase 1 | Civil - SRR PEB - Epack Interior - Grapid |  | Completed | Completed | Completed | 2025-11-15 | 2025-11-15 | 2025-12-15 | 80%
| Raju | RajaShekar | Main Building - Phase 2 | Civil - SRR PEB - Epack |  | Completed | Completed | Completed | 2025-10-30 | NA | NA | 50%
| Raju | RajaShekar | FG/RM Shed | Civil - CSR PEB - Bheema |  | Completed | Completed | Completed | 2025-11-30 | 2025-11-30 | 2025-12-15 | 60%
| Raju | RajaShekar | ETP (Tank + Shed) | Civil - SRR PEB - Epack |  | Completed | Completed | Completed | 2025-12-30 | 2025-11-30 | 2026-01-15 | 55%
| Raju | RajaShekar | Scrap Yard / Staff Building | Civil - CSR PEB - NA Interior - Grapid |  | Completed | NA | Completed | NA | 2026-01-16 | 2026-03-30 | 45%
| Raju | RajaShekar | Gas Yard | Civil - CSR PEB - Bheema |  | Completed | Completed | Completed | 2025-11-30 | 2025-11-30 | 2025-12-30 | 35%
| Raju | RajaShekar | Chemical Yard | Civil - SRR PEB - Steel Fab Engg |  | Completed | Completed | Completed | 2025-11-30 | 2025-11-30 | 2025-12-30 | 30%
| Raju | RajaShekar | Compound Wall | Civil - SRR PEB - NA |  | Completed | NA | Completed | NA | 2025-11-30 | NA | 75%
| Raju | RajaShekar | N2 Yard | Civil - PEB - |  |  | NA |  | NA |  | 2025-12-30 | 0%
| Raju | RajaShekar | PCW/ Compressor Yard | Civil - PEB - | [6 empty] | 2025-12-30 | 0%
| Raju | RajaShekar | Admin Building | Civil - PEB - NA Interior - Grapid |  |  | NA |  | NA |  | 2026-03-30 | 25%
| Raju | RajaShekar | Canteen Building | Civil - PEB - Interior - Grapid | [6 empty] | 2026-03-30 | 25%
| Raju | RajaShekar | 1) Security Wing 2) HR Wing 3) OHC & Creche Wing | Civil - PEB - NA Interior - Grapid |  |  | NA |  | NA |  | 2026-03-30 | 25%
| Raju | RajaShekar | Pheripheral Drain | Civil - SRR |  | Completed | NA | Completed | NA |  | 2026-03-30 | 60%
| Raju | RajaShekar | Road | Civil |  |  | NA |  | NA |  | 2026-03-30 | 5%
| Raju | RajaShekar | Chemical Trench | Civil |  |  | NA |  | NA |  | 2025-11-30 | 60% | Inside Shed
| Raju | RajaShekar | Strom Water Trench | Civil |  |  | NA |  | NA |  | 2026-01-30 | 5%
| Raju | RajaShekar | HT Trench | Civil |  |  | NA |  | NA |  | 2026-03-30 | 0% |  |  | Order [RFQ,Offer Receipt, Negotiation, PO Release, Adv Payment]
| Kumar | Younus | Sub Station | VVRR Electrical |  | Completed | NA | Completed | NA | 2026-03-30 | 2026-03-30 | 35% |  |  | Detail Engineering
| Raju | RajaShekar | Pipe Bridge | Civil - PEB - |  |  | NA |  | NA |  | 2025-11-30 | 0% |  |  | Manufacturing [ Clerance, Start ]
| Raju | RajaShekar | Cooler Water Bridge | Civil - PEB - |  |  | NA |  | NA |  | 2025-12-30 | 0% |  |  | Material Dispatch at Site
| Raju | RajaShekar | Entry (4 Path) | Civil Interior - Grapid |  |  | NA |  | NA |  | 2026-03-30 | 5% |  |  | Material Primary Installation
| Raju | RajaShekar | Land Leveling and Jungle Clerance | Civil - SRR |  | Completed | NA | Completed | NA |  | 2026-03-30 | 90%
| Raju | RajaShekar | Water Tank | Civil |  | Completed | NA | Completed | NA |  | 2026-01-30 | 0%
| Raju | RajaShekar | LandScape | Civil |  |  | NA |  | NA |  | 2026-06-30
| Raju | RajaShekar | Parking | Civil PEB - | [6 empty] | 2026-06-30
Packages | Procurement Team | Design Owner | Package | Vendor | Priority | Order Status - RFQ -Offer Receipt - Negotiation - PO Release - Adv Payment | Detail Engg - P&ID - GA Drg - Foundation Drg | Manufacturing - Clerance | Material Delivery at Site Start Target Date | Tool Move In & Installation Target Date | Hook Up & Commission Target Date | Progress 10% - Order Finalize 20% - Detail Engg Completion 30% - Manufacturing 60% - Delivery 80% Installation 95% - Commision 100% - Handover Operation | Remarks
Water Package | Praveen | Ravi | UPW | Membrane |  | Completed 24 Sep 25 | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-15 | 2026-03-30 | 2026-05-30 | 30% | Under Manufacturing
| Praveen | Ravi | ETP | Membrane |  | Completed 24 Sep 25 | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-15 | 2026-03-30 | 2026-05-30 | 30% | Under Manufacturing
| Praveen | Ravi | ZLD | Membrane |  | Completed 24 Sep 25 | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-15 | 2026-03-30 | 2026-05-30 | 30% | Under Manufacturing
| Praveen | Ravi | STP | Membrane |  | Completed 24 Sep 25 | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-15 | 2026-03-30 | 2026-05-30 | 30% | Under Manufacturing
| Praveen | Ravi | Raw Water Storage & Softner |  |  | RFQ to Rec. 16-10-2025 | [5 empty] | 5%
| Praveen | Ravi | DI Water | Membrane |  | Completed 24 Sep 25 | Foundation Drg 18 Oct 25 | Completed 24 Sep 25 | 2025-11-15 | 2026-03-30 | 2026-05-30 | 30% | Under Manufacturing
| Praveen | Madhusudan | DI Water Piping |  |  | RFQ to Rec. 16-10-2025 | NA | NA |  |  |  | 5%
| Praveen | Ravi | Liquid Lime Handling System Dosing | Membrane |  | Completed 24 Sep 25 | Foundation Drg 18 Oct 25 | Completed 24 Sep 25 | 2025-11-15 | 2026-03-30 | 2026-05-30 | 30% | Under Manufacturing
| Praveen | Ravi | Solid Lime Handling System Dosing | DYNAMIX |  | Completed 24 Sep 25 | Foundation Drg 17 Oct 25 | Completed 28 Sep 2025 | 2026-01-20 | 2026-02-15 | 2026-03-30 | 30% | Under Manufacturing
| Praveen | Vivek | PNG Gas | Think Gas |  | Sign Pending 15-10-2025 | Completed | 2025-10-30 |  |  |  | 30% | Commercial Closed
| Praveen | Younus | PNG Piping |  |  | RFQ to Rec. 16-10-2025 | NA | NA |  |  |  | 5% | Under Basic Design Stage
GAS Package | Praveen | Vivek | Bulk Gas Generation | Inox Air |  | Completed | Completed | Completed 25-09-2025 |  |  |  | 30% | Under manufacturing
| Praveen | Vivek | Bulk Gas Piping | UHP Technologies |  | Completed | Completed | Completed 07-10-2025 |  |  |  | 30%
| Praveen | Vivek | Bullk Gas System | AARON |  | Completed | Completed | Completed 13-10-2025 |  |  |  | 30% | Under Finalization of MDL
| Praveen | Vivek | NH3(Ammonia) - Decanting System |  |  | PO Pending 16-10-2025 | [5 empty] | 5%
| Praveen | Vivek | Auxillary Work ( Exh, Elec etc) |  |  | PO Pending 16-10-2025 | [5 empty] | 5%
Chemical Package | Praveen | Vivek | Chemical System | UHP Technologies |  | Completed | Completed | Completed 07-10-2025 |  |  |  | 30% | Execution Pan will be shared by 10 Oct
| Praveen | Vivek | Blower for Yard |  |  | RFQ to Rec. 16-10-2025 | [5 empty] | 5%
PEN | Praveen |  | Chemical Yard spill Drain Piping |  |  | RFQ to Rec. 16-10-2025 | NA | NA |  |  |  | 5% | Under Basic Design Stage
| Praveen | Madhusudan | Process Effluent ( 4 Stream) Piping |  |  | RFQ to Rec. 16-10-2025 | NA | NA |  |  |  | 5%
| Praveen | Madhusudan | Scrubber Drain Piping |  |  | RFQ to Rec. 16-10-2025 | NA | NA |  |  |  | 5%
| Praveen | Madhusudan | Drain from CDS Distribution( Tbox etc) |  |  | RFQ to Rec. 16-10-2025 | NA | NA |  |  |  | 5%
Air Package | Praveen | Ravi | Air-Compressors | ATLASCOPCO |  | Completed | Completed | Completed |  |  |  | 30% | Under Manufacturing and Foundation Drawing
| Praveen | Ravi | Dryer | ATLASCOPCO |  | Completed | Completed | Completed |  |  |  | 5%
| Praveen | Ravi | Receiver Tank |  |  | RFQ to Rec. 17-10-2025 | [5 empty] | 5% | Under Basic Design Stage
| Praveen | Ravi | CDA - Pre- Receiver Piping |  |  | RFQ to Rec. 17-10-2025 | [5 empty] | 5%
| Praveen | Ravi | CDA - Post Receiver Piping |  |  | RFQ to Rec. 17-10-2025 | NA | NA |  |  |  | 5% | Under Basic Design Stage
| Kumar | Shekar | Soft Starter for compressor |  |  | Completed 13-10-2025 | Completed | Completed |  |  |  | 5% | Under Technico Commercial Evaluation
| Praveen | Ravi | Cooling Tower & Piping |  |  | Technical to be shared | [5 empty] | 5%
HVAC | Praveen | Ravi | AHUs |  |  | RFQ to Rec. 17-10-2025 | [5 empty] | 5% | Engineering Discusion with ATE and Vendor
| Praveen | Ravi | Low Side |  |  | RFQ to Rec. 17-10-2025 | [5 empty] | 5%
| Praveen | Ravi | High Side |  |  | RFQ to Rec. 17-10-2025 | [5 empty] | 5%
Process Cooling Water (PCW) | Praveen | Ravi | Chillers (PCW / HVAC) | Carrier |  | Completed 13-10-2025 | Completed | 2025-10-24 |  |  |  | 20% | PO Awarded
| Praveen | Ravi | Pump (PCW/HVAC) |  |  | RFQ Floated 25-10-2025 | [5 empty] | 5%
| Praveen | Ravi | Primary Piping |  |  | RFQ Floated 25-10-2025 | [5 empty] | 5%
| Praveen | Ravi | Secondary Piping |  |  | RFQ Floated 25-10-2025 | [5 empty] | 5%
| Praveen | Ravi | Heat Exchanger |  |  | RFQ Floated 25-10-2025 | [5 empty] | 5%
Exhaust | Praveen | Ravi | Exhuast - Blower | Yet to Finalize |  | PO Pending 30-10-2025 | [5 empty] | 5% | Engineering Discusion with ATE and Vendor
| Praveen | Ravi | Exhuast - Scrubber |  |  | PO Pending 30-10-2025 | [5 empty] | 5%
| Praveen | Ravi | Exhaust - Plastic Ducting |  |  | PO Pending 30-10-2025 | [5 empty] | 5%
| Praveen | Ravi | Exhaust - Metallic Ducting |  |  | PO Pending 30-10-2025 | [5 empty] | 5%
Clean room | Praveen | Madhusudan | Wall & Ceiling Panel | Pophen |  | Completed 13-10-2025 | 2025-10-18 |  |  |  |  | 20% | PO Awaited
| Praveen | Madhusudan | Fan Filter Unit | Mayair International |  | Completed 13-10-2025 | NA | NA |  |  |  | 30%
| Praveen | Madhusudan | Doors |  |  | Quantification 30-10-2025 | [5 empty] | 5%
| Praveen | Madhusudan | Air Showers |  |  | RFQ to Rec. 30-10-2025 | [5 empty] | 0%
| Praveen | Madhusudan | Epoxy Flooring |  |  | RFQ to Rec. 15-11-2025 | [5 empty] | 0%
Fire Package | Kumar | Ravi | Fire Hydrant System | Yet to Finalize |  | RFQ to Rec. 16 Oct 25 | [5 empty] | 5% | Detail Designing under progress
| Kumar | Ravi | Fire Sprinkler System | Yet to Finalize |  | RFQ to Rec. 16 Oct 25 | [5 empty] | 5% | Detail Designing under progress
| Kumar | Ravi | Fire Alarm System | Yet to Finalize |  | RFQ to Rec. 16 Oct 25 | [5 empty] | 5% | Detail Designing under progress
| Kumar | Ravi | Fire Pump system | Yet to Finalize |  | RFQ to Rec. 16 Oct 25 | [5 empty] | 5%
BMS |  | Madhusudan | BMS | Yet to Finalize | [7 empty] | 0%
HV Packages | Kumar | Shekar | HV Electrical - Transformer HV 220/ 11 KVA - 50 MVA | 1) Bharat Bijlee - 1Qty 2) TMC - 2 Qty |  | Completed | Completed | Completed | 2026-01-30 | 2026-02-15 | 2026-03-30 | 30% | Manufacturing Clearance Given - Drawing Re Submitted
| Kumar | Shekar | HV Electrical - Transformer HV 220/ 33 KVA - 50 MVA | 1) TMC - 1 Qty |  | Completed | Completed | Completed | 2026-02-15 | 2026-03-17 | 2026-03-30 | 10% | Under GA Drawing Preparation from Vendor
| Kumar | Shekar | LV Electrical - Transformer LV (11KV to 400V/ 433V) | 1) TMC - 8 + 0 Qty 2) Volt Amp -20 + 8 Qty 3) Hitachi - 0 + 19 Qty |  | Completed | Completed | Completed | 2025-12-15 | 2026-01-15 | 2026-03-30 | 30% | Manufacturing Clearance Given - Drawing Re Submitted
| Kumar | Shekar | HV Electrical - DG Set | Jakson |  | Completed | 2026-10-15 | Completed | 2026-01-30 | 2026-02-28 | 2026-03-30 | 20% | GA Drawing under preparation
| Kumar | Shekar | HV Electrical - AMF Panel | Yet to Finalize |  | RFQ to Rec. 16 Oct 25 | [5 empty] | 5% | RFQ under Preparation
| Kumar | Shekar | HV Electical - Bus Bar | Yet to Finalize |  | RFQ to Rec. 16 Oct 25 | [5 empty] | 5% | RFQ under Preparation
| Kumar | Shekar | HV Electrical - 11 HV Panel | Yet to Finalize |  | RFQ to Rec. 18 Oct 25 | [5 empty] | 5% | RFQ Floated
| Kumar | Shekar | HV Electrical - HV Cable | Poly Cab |  | Completed | NA | NA |  |  |  | 30% | RFQ Floated
LV Package | Kumar | Shekar | LV Electrical - LV Panel | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - BUS Duct & Support | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - UPS System | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Cable Tray | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Cable | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Lugs and Terminal | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | RajaShekar N | LV Electrical - Lighting Inside | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | Yet to Start
| Kumar | RajaShekar N | LV Electrical - Area Lighting | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | Basic Design Started
| Kumar | RajaShekar N | LV Electrical - Earthing | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | Yet to Start
Facility System | Kumar | Younus | CCTV and Server | Yet to Finalize |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0% | Yet to Start
| Kumar | Younus | Boom Barrier and Access System | Yet to Finalize |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0% | Yet to Start
| Raju | Younus | Weight Bridge | Tulaman |  | Completed | Completed | Completed | Completed | Completed | Completed | 100%
| Raju | Younus | Gates |  |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0%
| Raju | Younus | Rack and System |  |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0%
DockLever | Raju | RajaShekar | Main Shed | Gandhi Automation |  | Completed | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | FG Shed | Gandhi Automation |  | Completed | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | Chemical Shed |  |  |  | NA | NA |  |  |  | 0%
Door & Shutter | Raju | RajaShekar | Main Shed | Gandhi Automation |  | PO Pending 30 Nov 25 | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | FG | Gandhi Automation |  | PO Pending 30 Nov 25 | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | Scrap Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Chemical Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Gas Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | ETP |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | PCW / CDA |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Admin Building |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Canteen |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | HR Building |  |  |  | NA | NA |  |  |  | 0%
Lift | Kiran | RajaShekar | Main Shed |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Scrap Yard |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Admin Building |  |  |  | NA | NA |  |  |  | 0%
Hoist | Kiran | RajaShekar | ETP |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Main Building |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Any |  |  |  | NA | NA |  |  |  | 0%
Formulas:
NA = [NA]+30

## Utilities-P3
Package | Procure Owner | Design Owner | Package | Vendor | Priority | Order Status - RFQ -Offer Receipt - Negotiation - PO Release - Adv Payment | Detail Engg - P&ID - GA Drg - Foundation Drg | Manufacturing - Clerance | Material Delivery at Site Start Target Date | Installation Start Target Date | Hook Up & Commission Target Date | Progress 10% - Order Finalize 20% - Detail Engg Completion 30% - Manufacturing 60% - Delivery 80% Installation 95% - Commision 100% - Handover Operation | Remarks
Water Package | Praveen | Ravi | UPW / ETP / ZLD / STP / DI Water | Membrane |  | Completed | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-30 | 2026-03-30 | 2026-05-30 | 40% | Material dispatch has commenced in batches.
| Praveen | Ravi | Raw Water Storage & Softner |  |  | 2025-12-10 | [5 empty] | 5% | Water Balance Diagram Received
| Praveen | Madhusudan | DI Water Piping |  |  | 2025-12-10 | NA | NA |  |  |  | 5% | Techno-commercial documentation is being prepared.
| Praveen | Ravi | Liquid Lime Handling System Dosing | Membrane |  | Completed 24 Sep 25 | Completed | Completed 24 Sep 25 | 2026-01-15 | 2026-03-30 | 2026-05-30 | 30% | Manufacturing activities have commenced.
| Praveen | Ravi | Solid Lime Handling System Dosing | DYNAMIX |  | Completed 24 Sep 25 | Completed 19 Oct 25 | Completed 28 Sep 2025 | 10 Dec 25 20 Jan 26 | 2026-02-15 | 2026-03-30 | 30% | Manufacturing activities have commenced.
GAS Package | Praveen | Vivek | PNG Gas | Think Gas |  | Completed 18 Oct 25 | Completed | NA | NA |  |  | 50% | Completed, "milestone achieved”
| Praveen | Younus | PNG Piping |  |  | 2025-12-10 | [5 empty] | 5% | The RFQ is currently under preparation.
| Praveen | Vivek | Bulk Gas Generation ( N2 & O) | Inox Air |  | Completed | Foundation Drg 28 Oct 25 | Completed 25-09-2025 | 2026-01-15 | 2026-01-30 | 2026-02-15 | 30% | Manufacturing activities have commenced.
| Praveen | Vivek | Bulk Gas Piping | UHP Technologies |  | Completed | Completed | Completed 07-10-2025 | 2026-01-15 | 2026-01-30 | 2026-03-30 | 30% | Manufacturing activities have commenced.
| Praveen | Vivek | Bullk Gas System | UHP Technologies |  | Completed | Completed 14 Nov 25 | Completed 13-10-2025 | 2026-01-15 | 2026-01-30 | 2026-03-30 | 30% | Manufacturing activities have commenced.
| Praveen | Vivek | NH3(Ammonia) - Decanting System | UHP Technologies |  | Completed | Completed | Completed | 2026-01-15 | 2026-01-30 | 2026-03-30 | 5% | Manufacturing activities have commenced.
Chemical Package | Praveen | Vivek | Chemical System - HF, HCL, NaOH, H2O2, TEX, POL,a-Si | AARON |  | Completed | Completed | Completed 07-10-2025 | 2025-12-25 | 2025-12-30 | 2026-04-04 | 30% | Manufacturing activities have commenced.
| Praveen | Vivek | Blower for Yard |  |  | RFQ to Rec. 16-10-2025 | [5 empty] | 5%
| Praveen |  | Chemical Yard spill Drain Piping |  |  | 2025-11-30 | NA | NA |  |  |  | 5% | Under Basic Design Stage
| Praveen | Madhusudan | Process Effluent ( 4 Stream) Piping |  |  | 2025-11-05 | NA | NA |  |  |  | 5% | Under Basic Design Stage
| Praveen | Madhusudan | Scrubber Drain Piping |  |  | 2025-11-05 | NA | NA |  |  |  | 5% | Under Basic Design Stage
| Praveen | Madhusudan | Drain from CDS Distribution( Tbox etc) |  |  | 2025-11-05 | NA | NA |  |  |  | 5% | Under Basic Design Stage
Air Package | Praveen | Ravi | Air-Compressors | ATLASCOPCO |  | Completed | Completed | Completed | 2026-01-30 | 2026-02-15 | 2026-03-15 | 40% | Manufacturing activities have commenced.
| Praveen | Ravi | Dryer | ATLASCOPCO |  | Completed | Completed | Completed | 2026-01-30 | 2026-02-15 | 2026-03-15 | 40% | Manufacturing activities have commenced.
| Praveen | Ravi | Receiver Tank |  |  | 2025-11-30 | [5 empty] | 7% | The RFQ is currently under preparation.
| Praveen | Ravi | CDA - Pre- Receiver Piping |  |  | 2025-11-30 | [5 empty] | 7% | The RFQ is currently under preparation.
| Praveen | Ravi | CDA - Post Receiver Piping |  |  | 2025-11-30 | [5 empty] | 7% | The RFQ is currently under preparation. | Details of fan and drawing is shared.
| Kumar | Shekar | Soft Starter for compressor | Lecon |  | Completed 13-10-2025 | Completed | Completed | 2026-01-30 | 2026-02-15 | 2026-03-15 | 40% | Manufacturing activities have commenced.
HVAC | Praveen | Ravi | AHUs | Luftet |  | Completed | Target 30 Nov 25 |  |  |  |  | 5% | Development of manufacturing-related engineering is in progress
| Praveen | Ravi | Low Side | Blue Star |  | Completed | Target 30 Nov 25 |  |  |  |  | 5% | Development of manufacturing-related engineering is in progress
| Praveen | Ravi | High Side | [8 empty] | 5%
Process Cooling Water (PCW) | Praveen | Ravi | Chillers (PCW / HVAC) | Carrier |  | Completed 13-10-2025 | Completed | Completed 24 Oct 25 |  |  |  | 30% | Manufacturing activities have commenced.
| Praveen | Ravi | Pump (PCW/HVAC) | Blue Star / Surekha |  | Completed | Completed | Completed |  |  |  | 5% | Manufacturing activities have commenced.
| Praveen | Ravi | Primary Piping | Blue Star |  | Completed | Target 30 Nov 25 |  |  |  |  | 5% | Development of manufacturing-related engineering is in progress
| Praveen | Ravi | Secondary Piping | Blue Star |  | Completed | Target 30 Nov 25 |  |  |  |  | 5% | Development of manufacturing-related engineering is in progress
| Praveen | Ravi | Heat Exchanger | Blue Star |  | Completed | Target 30 Nov 25 |  |  |  |  | 5% | Development of manufacturing-related engineering is in progress
Exhaust | Praveen | Ravi | Exhuast - Blower | Reitz |  | Completed 19-10-2025 | Target 30 Nov 25 |  |  |  |  | 10% | Development of manufacturing-related engineering is in progress
| Praveen | Ravi | Exhuast - Scrubber ( Damper - Exhaust Fan) | Meibao |  | Completed 29-10-2025 | Target 30 Nov 25 |  |  |  |  | 5% | Development of manufacturing-related engineering is in progress
| Praveen | Ravi | Exhaust - Plastic Ducting | RP & BS |  | Completed | Target 30 Nov 25 |  |  |  |  | 5% | Development of manufacturing-related engineering is in progress
| Praveen | Ravi | Exhaust - Metallic Ducting | RP & BS |  | Completed | Target 30 Nov 25 |  |  |  |  | 5% | Development of manufacturing-related engineering is in progress
Clean room | Praveen | Madhusudan | Wall & Ceiling Panel & Door | Pophen |  | Completed 13-10-2025 | Completed | Completed | 10 Dec 25 Onwards | 15 Dec 25 Onwards | 2026-03-30 | 30% | Manufacturing activities have commenced.
| Praveen | Madhusudan | Fan Filter Unit | Mayair International |  | Completed 13-10-2025 | Completed | Completed | 20 Dec 25 Onwards | 2026-02-15 | 2026-03-30 | 30% | Manufacturing activities have commenced.
| Praveen | Madhusudan | Air Showers |  |  | 2025-12-15 | [5 empty] | 0% | RFQ under Preparation
| Praveen | Madhusudan | Epoxy Flooring |  |  | 2025-12-15 | [5 empty] | 0% | RFQ under Preparation
Fire Package | Kumar | Ravi | Hydrant/Sprinkler/Alarm/Pump System |  |  | 2025-11-30 | [5 empty] | 5% | RFQ Floated under Commerical and Scope Evaluation
BMS |  | Madhusudan | BMS | [8 empty] | 0%
HV Packages | Kumar | Shekar | HV Electrical - Transformer HV 220/ 11 KVA - 50 MVA | 1) Bharat Bijlee - 1Qty 2) TMC - 2 Qty |  | Completed | Completed | Completed | 2026-01-30 | 2026-02-15 | 2026-03-30 | 30% | Manufacturing activities have commenced.
| Kumar | Shekar | HV Electrical - Transformer HV 220/ 33 KVA - 50 MVA | 1) TMC - 1 Qty |  | Completed | Completed | Completed | 2026-02-15 | 2026-03-17 | 2026-03-30 | 10% | Manufacturing activities have commenced.
| Kumar | Shekar | LV Electrical - Transformer LV (11KV to 400V/ 433V) | 1) TMC - 8 + 0 Qty 2) Volt Amp -20 + 8 Qty 3) Hitachi - 0 + 19 Qty |  | Completed | Completed | Completed | 2025-12-15 | 2026-01-15 | 2026-03-30 | 30% | Manufacturing activities have commenced.
| Kumar | Shekar | HV Electrical - DG Set | Jakson |  | Completed | Completed | Completed | 2026-01-30 | 2026-02-28 | 2026-03-30 | 20% | Manufacturing activities have commenced.
| Kumar | Shekar | HV Electrical - AMF Panel |  |  | 2025-11-20 | [5 empty] | 5% | The RFQ is currently under preparation.
| Kumar | Shekar | HV Electical - Bus Bar |  |  | 2025-11-20 | [5 empty] | 5% | The RFQ is currently under preparation.
| Kumar | Shekar | HV Electrical - 11 HV Panel |  |  | 2025-11-20 | [5 empty] | 5% | The RFQ is currently under preparation.
| Kumar | Shekar | HV Electrical - HV Cable | Poly Cab |  | Completed | NA | NA |  |  |  | 30% | Manufacturing activities have commenced.
LV Package | Kumar | Shekar | LV Electrical - LV Panel | Yet to Finalize |  | 2025-11-30 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - BUS Duct & Support | Yet to Finalize |  | 2025-11-30 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - UPS System | Yet to Finalize |  | 2025-11-15 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Cable Tray | Yet to Finalize |  | 2025-11-30 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Cable | Yet to Finalize |  | 2025-11-30 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Lugs and Terminal | Yet to Finalize |  | 2025-11-30 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | RajaShekar N | LV Electrical - Lighting Inside | Yet to Finalize |  | 2025-11-30 | [5 empty] | 5% | Yet to Start
| Kumar | RajaShekar N | LV Electrical - Area Lighting | Yet to Finalize |  | 2025-11-30 | [5 empty] | 5% | Basic Design Started
| Kumar | RajaShekar N | LV Electrical - Earthing | Yet to Finalize |  | 2025-11-30 | [5 empty] | 5% | Yet to Start
Facility System | Kumar | Younus | CCTV and Server | Yet to Finalize |  | RFQ to Float 30 Nov 25 | [5 empty] | 0% | Yet to Start
| Kumar | Younus | Boom Barrier and Access System | Yet to Finalize |  | RFQ to Float 30 Nov 25 | [5 empty] | 0% | Yet to Start
| Raju | Younus | Weight Bridge | Tulaman |  | Completed | Completed | Completed | Completed | Completed | Completed | 100%
| Raju | Younus | Gates |  |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0%
| Raju | Younus | Rack and System |  |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0%
DockLever | Raju | RajaShekar | Main Shed | Gandhi Automation |  | Completed | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | FG Shed | Gandhi Automation |  | Completed | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | Chemical Shed |  |  |  | NA | NA |  |  |  | 0%
Door & Shutter | Raju | RajaShekar | Main Shed | Gandhi Automation |  | PO Pending 30 Nov 25 | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | FG | Gandhi Automation |  | PO Pending 30 Nov 25 | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | Scrap Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Chemical Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Gas Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | ETP |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | PCW / CDA |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Admin Building |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Canteen |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | HR Building |  |  |  | NA | NA |  |  |  | 0%
Lift | Kiran | RajaShekar | Main Shed |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Scrap Yard |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Admin Building |  |  |  | NA | NA |  |  |  | 0%
Hoist | Kiran | RajaShekar | ETP |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Main Building |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Any |  |  |  | NA | NA |  |  |  | 0%
Formulas:
Installation Start Target Date = [NA]+30

## Utilities-P2 (hidden)
Package | Procure Owner | Design Owner | Package | Vendor | Priority | Order Status - RFQ -Offer Receipt - Negotiation - PO Release - Adv Payment | Detail Engg - P&ID - GA Drg - Foundation Drg | Manufacturing - Clerance | Material Delivery at Site Start Target Date | Tool Move In & Installation Target Date | Hook Up & Commission Target Date | Progress 10% - Order Finalize 20% - Detail Engg Completion 30% - Manufacturing 60% - Delivery 80% Installation 95% - Commision 100% - Handover Operation | Remarks
Water Package | Praveen | Ravi | UPW / ETP / ZLD / STP / Di Water | Membrane |  | Completed 24 Sep 25 | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-30 | 2026-03-30 | 2026-05-30 | 40% | Manufacturing Started
| Praveen | Ravi | ETP | Membrane |  | Completed 24 Sep 25 | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-30 | 2026-03-30 | 2026-05-30 | 40% | Manufacturing Started
| Praveen | Ravi | ZLD | Membrane |  | Completed 24 Sep 25 | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-30 | 2026-03-30 | 2026-05-30 | 40% | Manufacturing Started
| Praveen | Ravi | STP | Membrane |  | Completed 24 Sep 25 | Completed 24 Sep 25 | Completed 24 Sep 25 | 2025-11-30 | 2026-03-30 | 2026-05-30 | 40% | Manufacturing Started
| Praveen | Ravi | Raw Water Storage & Softner |  |  | 2025-11-15 | [5 empty] | 5% | RFQ under Preparation
| Praveen | Ravi | DI Water | Membrane |  | Completed 24 Sep 25 | Foundation Drg 28 Oct 25 | Completed 24 Sep 25 | 2025-11-30 | 2026-03-30 | 2026-05-30 | 30%
| Praveen | Madhusudan | DI Water Piping |  |  | 2025-11-05 | NA | NA |  |  |  | 5% | RFQ to be floated to Vendor
| Praveen | Ravi | Liquid Lime Handling System Dosing | Membrane |  | Completed 24 Sep 25 | Foundation Drg 28 Oct 25 | Completed 24 Sep 25 | 2026-01-15 | 2026-03-30 | 2026-05-30 | 30% | Civil Drawing to be Shared from Membrane
| Praveen | Ravi | Solid Lime Handling System Dosing | DYNAMIX |  | Completed 24 Sep 25 | Completed 19 Oct 25 | Completed 28 Sep 2025 | 10 Dec 25 20 Jan 26 | 2026-02-15 | 2026-03-30 | 30% | Manufacturing Started
| Praveen | Vivek | PNG Gas | Think Gas |  | Completed 18 Oct 25 | Completed | NA | NA |  |  | 50% | Commercial Closed
| Praveen | Younus | PNG Piping |  |  | 2025-11-10 | [5 empty] | 5% | RFQ under Preparation
GAS Package | Praveen | Vivek | Bulk Gas Generation | Inox Air |  | Completed | Foundation Drg 28 Oct 25 | Completed 25-09-2025 | 15 Jan 26 15 May 26 | 30 Jan 26 30 May 26 | 15 Feb 26 15 Jun 26 | 30% | Manufacturing Started
| Praveen | Vivek | Bulk Gas Piping | UHP Technologies |  | Completed | Completed | Completed 07-10-2025 | 2025-11-25 | 2025-11-30 | 2026-04-04 | 30% | Manufacturing Started
| Praveen | Vivek | Bullk Gas System | UHP Technologies |  | Completed | Design 5 Nov 25 | Completed 13-10-2025 |  |  | 2026-03-15 | 30% | Manufacturing Started and Under Final Technical Closure
| Praveen | Vivek | NH3(Ammonia) - Decanting System |  |  | 2025-11-05 | [5 empty] | 5% | UHP is the Pre vendor - Commerical Evaluation in under process
| Praveen | Vivek | Auxillary Work ( Exh, Elec etc) |  |  | 2025-11-05 | [5 empty] | 5% | UHP is the Pre vendor - Commerical Evaluation in under process
Chemical Package | Praveen | Vivek | Chemical System | AARON |  | Completed | Completed | Completed 07-10-2025 | 2025-11-25 | 2025-11-30 | 2026-04-04 | 30% | Manufacturing Started
| Praveen | Vivek | Blower for Yard |  |  | RFQ to Rec. 16-10-2025 | [5 empty] | 5%
PEN | Praveen |  | Chemical Yard spill Drain Piping |  |  | 2025-11-05 | NA | NA |  |  |  | 5% | Under Basic Design Stage
| Praveen | Madhusudan | Process Effluent ( 4 Stream) Piping |  |  | 2025-11-05 | NA | NA |  |  |  | 5% | Under Basic Design Stage
| Praveen | Madhusudan | Scrubber Drain Piping |  |  | 2025-11-05 | NA | NA |  |  |  | 5% | Under Basic Design Stage
| Praveen | Madhusudan | Drain from CDS Distribution( Tbox etc) |  |  | 2025-11-05 | NA | NA |  |  |  | 5% | Under Basic Design Stage
Air Package | Praveen | Ravi | Air-Compressors | ATLASCOPCO |  | Completed | Completed | Completed |  |  | 2026-03-15 | 40% | Manufacturing Started
| Praveen | Ravi | Dryer | ATLASCOPCO |  | Completed | Completed | Completed |  |  | 2026-03-15 | 40% | Manufacturing Started
| Praveen | Ravi | Receiver Tank |  |  | 2025-11-05 | [5 empty] | 7% | RFQ Received - Vendor evaluation in Process
| Praveen | Ravi | CDA - Pre- Receiver Piping |  |  | 2025-11-05 | [5 empty] | 7% | RFQ Received - Vendor evaluation in Process
| Praveen | Ravi | CDA - Post Receiver Piping |  |  | 2025-11-05 | NA | NA |  |  |  | 7% | RFQ Received - Vendor evaluation in Process
| Kumar | Shekar | Soft Starter for compressor | Lecon |  | Completed 13-10-2025 | Completed | Completed | 2025-12-15 |  | 2026-03-15 | 40% | Manufacturing Started
| Praveen | Ravi | Cooling Tower & Piping |  |  | 2025-11-05 | [5 empty] | 5% | RFQ under Preparation
HVAC | Praveen | Ravi | AHUs |  |  | 2025-11-10 | [5 empty] | 5% | Vendor Negoitiation in Process
| Praveen | Ravi | Low Side |  |  | 2025-11-10 | [5 empty] | 5% | Vendor Negoitiation in Process
| Praveen | Ravi | High Side |  |  | 2025-11-10 | [5 empty] | 5% | Vendor Negoitiation in Process
Process Cooling Water (PCW) | Praveen | Ravi | Chillers (PCW / HVAC) | Carrier |  | Completed 13-10-2025 | Completed | Completed 24 Oct 25 |  |  |  | 30% | Manufacturing Started
| Praveen | Ravi | Pump (PCW/HVAC) |  |  | 2025-11-10 | [5 empty] | 5% | Vendor Negoitiation in Process
| Praveen | Ravi | Primary Piping |  |  | 2025-11-10 | [5 empty] | 5% | Vendor Negoitiation in Process
| Praveen | Ravi | Secondary Piping |  |  | 2025-11-10 | [5 empty] | 5% | Vendor Negoitiation in Process
| Praveen | Ravi | Heat Exchanger |  |  | 2025-11-10 | [5 empty] | 5% | Vendor Negoitiation in Process
Exhaust | Praveen | Ravi | Exhuast - Blower | Reitz |  | Completed 19-10-2025 | [5 empty] | 10% | Detail Engineering under Discusion
| Praveen | Ravi | Exhuast - Scrubber ( Damper - Exhaust Fan) | Meibao |  | Completed 29-10-2025 | [5 empty] | 5% | Detail Engineering under Discusion
| Praveen | Ravi | Exhaust - Plastic Ducting |  |  | 2025-10-30 | [5 empty] | 5% | Vendor Negoitiation in Process
| Praveen | Ravi | Exhaust - Metallic Ducting |  |  | 2025-10-30 | [5 empty] | 5% | Vendor Negoitiation in Process
Clean room | Praveen | Madhusudan | Wall & Ceiling Panel | Pophen |  | Completed 13-10-2025 | 2025-10-18 | 2025-10-28 | 10 Dec 25 Onwards | 15 Dec 25 Onwards | 2026-03-30 | 30% | Manufacturing Started
| Praveen | Madhusudan | Fan Filter Unit | Mayair International |  | Completed 13-10-2025 | 2025-11-05 | 2025-11-05 | 20 Dec 25 Onwards | 2026-02-15 | 2026-03-30 | 30% | Manufacturing Started
| Praveen | Madhusudan | Doors | Pophen |  | Completed 13-10-2025 | 2025-10-18 | 2025-10-28 | 1 Feb 26 Onwards | 15 Feb 26 Onwards | 2026-03-30 | 30% | Manufacturing Started
| Praveen | Madhusudan | Air Showers |  |  | 2025-11-30 | [5 empty] | 0% | RFQ under Preparation
| Praveen | Madhusudan | Epoxy Flooring |  |  | 2025-11-30 | [5 empty] | 0% | RFQ under Preparation
Fire Package | Kumar | Ravi | Fire Hydrant System |  |  | 2025-11-10 | [5 empty] | 5% | RFQ to be floated to Vendor
| Kumar | Ravi | Fire Sprinkler System |  |  | 2025-11-10 | [5 empty] | 5% | RFQ to be floated to Vendor
| Kumar | Ravi | Fire Alarm System |  |  | 2025-11-10 | [5 empty] | 5% | RFQ to be floated to Vendor
| Kumar | Ravi | Fire Pump system |  |  | 2025-11-10 | [5 empty] | 5% | RFQ to be floated to Vendor
BMS |  | Madhusudan | BMS | [8 empty] | 0%
HV Packages | Kumar | Shekar | HV Electrical - Transformer HV 220/ 11 KVA - 50 MVA | 1) Bharat Bijlee - 1Qty 2) TMC - 2 Qty |  | Completed | Completed | Completed | 2026-01-30 | 2026-02-15 | 2026-03-30 | 30% | Manufacturing Started
| Kumar | Shekar | HV Electrical - Transformer HV 220/ 33 KVA - 50 MVA | 1) TMC - 1 Qty |  | Completed | Completed | Completed | 2026-02-15 | 2026-03-17 | 2026-03-30 | 10% | Manufacturing Started
| Kumar | Shekar | LV Electrical - Transformer LV (11KV to 400V/ 433V) | 1) TMC - 8 + 0 Qty 2) Volt Amp -20 + 8 Qty 3) Hitachi - 0 + 19 Qty |  | Completed | Completed | Completed | 2025-12-15 | 2026-01-15 | 2026-03-30 | 30% | Manufacturing Started
| Kumar | Shekar | HV Electrical - DG Set | Jakson |  | Completed | 2026-10-15 | Completed | 2026-01-30 | 2026-02-28 | 2026-03-30 | 20% | Manufacturing Started
| Kumar | Shekar | HV Electrical - AMF Panel |  |  | 2025-11-05 | [5 empty] | 5% | RFQ under Preparation
| Kumar | Shekar | HV Electical - Bus Bar |  |  | 2025-11-05 | [5 empty] | 5% | RFQ under Preparation
| Kumar | Shekar | HV Electrical - 11 HV Panel |  |  | 2025-11-05 | [5 empty] | 5% | RFQ under Preparation
| Kumar | Shekar | HV Electrical - HV Cable | Poly Cab |  | Completed | NA | NA |  |  |  | 30% | Manufacturing Started
LV Package | Kumar | Shekar | LV Electrical - LV Panel | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - BUS Duct & Support | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - UPS System | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Cable Tray | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Cable | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | Shekar | LV Electrical - Lugs and Terminal | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | RFQ Under Preparation
| Kumar | RajaShekar N | LV Electrical - Lighting Inside | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | Yet to Start
| Kumar | RajaShekar N | LV Electrical - Area Lighting | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | Basic Design Started
| Kumar | RajaShekar N | LV Electrical - Earthing | Yet to Finalize |  | RFQ to Rec. 25 Oct 25 | [5 empty] | 5% | Yet to Start
Facility System | Kumar | Younus | CCTV and Server | Yet to Finalize |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0% | Yet to Start
| Kumar | Younus | Boom Barrier and Access System | Yet to Finalize |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0% | Yet to Start
| Raju | Younus | Weight Bridge | Tulaman |  | Completed | Completed | Completed | Completed | Completed | Completed | 100%
| Raju | Younus | Gates |  |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0%
| Raju | Younus | Rack and System |  |  | RFQ to Rec. 30 Nov 25 | [5 empty] | 0%
DockLever | Raju | RajaShekar | Main Shed | Gandhi Automation |  | Completed | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | FG Shed | Gandhi Automation |  | Completed | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | Chemical Shed |  |  |  | NA | NA |  |  |  | 0%
Door & Shutter | Raju | RajaShekar | Main Shed | Gandhi Automation |  | PO Pending 30 Nov 25 | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | FG | Gandhi Automation |  | PO Pending 30 Nov 25 | NA | NA | 2025-11-15 | 2025-11-30 | 2025-12-30 | 0%
| Raju | RajaShekar | Scrap Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Chemical Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Gas Yard |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | ETP |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | PCW / CDA |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Admin Building |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | Canteen |  |  |  | NA | NA |  |  |  | 0%
| Raju | RajaShekar | HR Building |  |  |  | NA | NA |  |  |  | 0%
Lift | Kiran | RajaShekar | Main Shed |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Scrap Yard |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Admin Building |  |  |  | NA | NA |  |  |  | 0%
Hoist | Kiran | RajaShekar | ETP |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Main Building |  |  |  | NA | NA |  |  |  | 0%
| Kiran | RajaShekar | Any |  |  |  | NA | NA |  |  |  | 0%
Formulas:
Tool Move In & Installation Target Date = [NA]+30

## Civil-P2
Packages | Procurement Team | Design Owner | Package | Vendor | Priority | Order Status - RFQ -Offer Receipt - Negotiation - PO Release - Adv Payment | PEB Drawing | Civil Drawing | PEB Progress - Primary - Secondary - Alignment - Roofing - Wall - Guttering - Mazzemine | Civil Progress - Footing - PCC - Back Fiiling - Plinth beam - Anchor Bolt - GSB - PCC - VDF | Accessories - Door - Shutter - Dock Leveler - Lift | Progress 10% - Order Finalize 20% - PEB Drawing 30% - Civil Drawing 40% - Material Delivery 90% - Execution 95% - Accessories 100% - Handover | Remarks
Building | Raju | RajaShekar | Main Building - Phase 1 | Civil - SRR PEB - Epack Interior - Grapid |  | Completed | Completed | Completed | 2025-12-15 | 2025-12-15 | 2025-12-30 | 83% | Sheetiing & Torquing to be completed by 30th Nov
| Raju | RajaShekar | Main Building - Phase 2 | Civil - SRR PEB - Epack |  | Completed | Completed | Completed | NA | 2025-12-15 | NA | 50% | SRR Work Scoep target to be completed by 30th Nov
| Raju | RajaShekar | FG/RM Shed | Civil - CSR PEB - Bheema |  | Completed | Completed | Completed | 2025-12-15 | 2025-12-15 | 2025-12-15 | 75% | Target to Complete Sheeting & VDF by 30th Nov
| Raju | RajaShekar | ETP (Tank + Shed) | Civil - SRR PEB - Epack |  | Completed | Completed | Completed | 2025-12-30 | 2026-01-15 | 2026-01-15 | 60% | EPack - Erection Started SRR - Blasting Started
| Raju | RajaShekar | Scrap Yard / Staff Building | Civil - CSR PEB - NA Interior - Grapid |  | Completed | NA | Completed | NA | 2026-01-16 | 2026-03-30 | 50% | Target for 1st Slab Lift by 30 Nov
| Raju | RajaShekar | Gas Yard | Civil - SRR PEB - Steel Fab Engg |  | Completed | Completed | Completed | 2025-12-30 | 2025-12-30 | 2026-01-15 | 40% | Foundation
| Raju | RajaShekar | Chemical Yard | Civil - CSR PEB - Bheema |  | Completed | Completed | Completed | 2025-12-30 | 2025-12-30 | 2026-01-15 | 35% | Civil Work in Progress PEB material will be at Site targeted by 25th Nov.
| Raju | RajaShekar | Compound Wall | Civil - SRR PEB - NA |  | Completed | NA | Completed | NA | 2025-12-30 | NA | 75% | Paint Work Started.
| Raju | RajaShekar | N2 Yard | Civil - PEB - |  | 2025-11-30 | NA |  | NA |  | 2026-01-30 | 5% | Design under detail Engineering target to close by 25th Nov
| Raju | RajaShekar | PCW/ Compressor Yard | Civil - PEB - |  | 2025-11-30 |  |  |  |  | 2026-01-30 | 5% | Design under detail Engineering target to close by 25th Nov
| Raju | RajaShekar | Admin Building | Civil - PEB - NA Interior - |  | 2025-11-30 | NA |  | NA |  | 2026-03-30 | 5% | New Architect is to be OnBoarded
| Raju | RajaShekar | Canteen Building | Civil - PEB - Interior |  | 2025-11-30 |  |  |  |  | 2026-03-30 | 5% | New Architect is to be OnBoarded
| Raju | RajaShekar | Security / HR Building | Civil - PEB - NA Interior - |  | 2025-11-30 | NA |  | NA |  | 2026-03-30 | 5% | New Architect is to be OnBoarded
Auxillary Activity | Raju | RajaShekar | Pheripheral Drain | Civil - SRR |  | Completed | NA | Completed | NA |  | 2026-03-30 | 60% | Temprary Drain are executed for de water purpose
| Raju | RajaShekar | Road | Civil |  | 2025-12-15 | NA |  | NA |  | 2026-03-30 | 5% | Design Ready Waiting for Peripheral design activity to be completed to start of execution
| Raju | RajaShekar | Chemical Trench | Civil |  | Completed | NA | Design 5 Nov 25 | NA |  | 2025-11-30 | 60% | Inside cell building Execution started. Network area design under development Target by 25th Nov
| Raju | RajaShekar | Strom Water Trench | Civil |  | 2025-11-30 | NA |  | NA |  | 2026-01-30 | 3% | Target to Close to Design Concept by 25th Nov
| Raju | RajaShekar | HT Trench | Civil |  | 2025-11-30 | NA |  | NA |  | 2026-01-30 | 0% | Target to Close to Design Concept by 25th Nov
| Kumar | Younus | Sub Station | VVRR Electrical Vertex |  | Completed | NA | Completed | NA |  | 2026-03-30 | 35% | Foundation Work Started
| Raju | RajaShekar | Pipe Bridge | Civil - PEB - |  | 2025-11-30 | NA |  | NA |  | 2025-12-30 | 0% | Target to Close to Design Concept by 25th Nov
| Raju | RajaShekar | Cooler Water Bridge | Civil - PEB - |  | 2025-11-30 | NA |  | NA |  | 2025-12-30 | 0% | Target to Close to Design Concept by 25th Nov
| Raju | RajaShekar | Entry (4 Path) | Civil Interior - Grapid |  | 2025-11-30 | NA |  | NA |  | 2026-03-30 | 5% | New Architect is to be OnBoarded
| Raju | RajaShekar | Land Leveling and Jungle Clerance | s |  | 2025-11-30 | NA | Completed | NA |  | 2026-03-30 | 90%
| Raju | RajaShekar | Water Tank | Civil |  | 2025-11-30 | NA |  | NA |  | 2026-01-30 | 0% | Target to Close to Design Concept by 25th Nov
100%

## Civil -P11 (hidden)
Building | Process | Vendor | Drawing/Approval |  |  |  |  | Commercial | [6 empty] | Execution Update |  |  |  |  | Remarks
|  |  | Concept Drawing | STAAD Drawing | Anchor Bolt Drawing | GA Drawing | Foundation Drawing | Basic Engg | RFQ float | Offer Receipt | Negotiation | PO release | Advance Payment | Mobilization | Planned Start Date | Planned End Date | Projected / Actual Completion Date | Planned Progress | Actual Progress
Cell Building Phase 1 | Civil | SRR | [12 empty] | 2025-06-01 | 2025-11-15 | 2025-07-22 | 100% | 100% | Complete Box Target by 30 Oct
| PEB | Epack | [12 empty] | 2024-07-07 | 2025-11-15 |  |  | 70%
Cell Building Phase 2 | Civil | SRR | [12 empty] | 2025-08-01 | 2025-10-30 |  | 50% | 60% | Zone 1: 50% Zone 2 : 69% Zone 3: 61%
| PEB | Epack
Compound Wall | Civil | SRR | [12 empty] | 2025-06-17 | 2025-11-30 |  |  | 43% | Color Shed sample will ready by 18th Sep
FG/RM Shed | Civil | CSR | [12 empty] | 2025-06-30 | 2025-10-30 |  |  | 85% | Anchor Bolt Received at Site. PEB Struture will Start Delivery at Site from 20 Sep
| PEB | Bheema | [12 empty] | 2025-09-16 | 2025-11-30
ETP Shed & Tank | Civil | SRR | [12 empty] | 2025-08-07 | 2025-11-30 |  |  | 29% | PEB Material Inspection at Factory done on 13 Sep. Tank Foundation Progress : 29% ETP Shed Foundation Progress: 28.3%
| PEB | Epack | [12 empty] | 2025-09-15 | 2025-12-30
Scrap & Logistics Shed / Admin | Civil | CSR | [12 empty] | 2025-09-01 | 2026-01-14 |  |  | 10% | Execution Work Started at Site
Gas Yard | Civil | SRR | [12 empty] | 2025-09-27 | 2025-11-30 |  |  |  | RFQ Floated
| PEB | Steel Fab Engg | [12 empty] | 2025-09-27 | 2025-11-30
Chemical Yard | Civil | CSR | [12 empty] | 2025-09-27 | 2025-11-30 |  |  |  | RFQ Floated
| PEB | Bheema | [12 empty] | 2025-09-27 | 2025-11-30
N2 Yard | Civil | [18 empty] | Design Under Evaluation
PEB
CDA/PCW Yard | Civil | [18 empty] | Design Under Evaluation
PEB
Main Building (Admin) | Civil | [13 empty] | 2025-10-01 | 2026-03-30 |  |  |  | Architectural Drawing have been Shared. Strutural Input will be shared by 24th Sep
| Interior | Grapid
HR/Safety/ IT/Admin | Civil | [13 empty] | 2025-11-01 | 2026-03-30 |  |  |  | Awaiting Architectual Drawing - Traget by 25th Sep
| Interior | Grapid
Canteen Building | Civil | [13 empty] | 2025-11-01 | 2026-03-30 |  |  |  | Awaiting Architectual Drawing - Traget by 25th Sep
| Interior | Grapid
Other Activities
200 / 11 KVA Sub Station | Turn Key Solution | Vertex VVRR | [12 empty] | 2025-09-01 | 2026-03-31 |  |  |  | Material Order Released Site Execution Started
Weight Bridge | Acc | Tulaman | [12 empty] | 2025-06-15 | 2025-09-30 |  |  |  | Commisioning will will complleyed by 12 Sep Government License Target by 25 Sep
Peripheral Drain Network | Civil | SRR | [12 empty] | 2025-09-10 | 2025-09-30 |  |  | 5% | Execution Started at Site
Drain Network | Civil | [18 empty] | Design Ready
Sewage Network | Civil | [18 empty] | Design Ready
Road Network Inside | Civil | [18 empty] | Yet to Start
Main Gates | Civil | [18 empty] | Concept under Development
Door & Shutter | Acc | [18 empty] | RFQ for FG/ RM under Preparation
Epoxy | Acc | [18 empty] | Yet to Start
Docklever | Acc | Gandhi Automation | [17 empty] | Order Placed for Main Shed and FG / RM Shed
Lift Material | Acc | [18 empty] | RFQ Raised for Main Shed / Scrap Yard
Lift for Human | Acc | [18 empty] | Yet to Start
Rack and System | Acc | [18 empty] | Yet to Start
Air Shower | Acc | [18 empty] | Yet to Start
Formulas:
Projected / Actual Completion Date = [Execution Update]+51
Planned End Date = [Execution Update]+(4.5*30)

## Utility Meeting (hidden)
S.No. | Utility | MOM | Responsibility | Release Date | Remarks
1 | Misc. | BOQ of Fans, scrubbers etc. to be given to Praveen | Ravi | 2025-09-01
2 |  | Exhaust Design and wetting will be done by ATE | Info
3 |  | Progress meeting with ATE on Monday | Ravi | 2025-09-01
4 | Electrical | GDS, CDS, HVAC, PCW, HVAC loads | Rahul | 2025-09-01
5 |  | Water balancing dwg inputs to be shared to VMS | Ravi | 2025-08-27
6 |  | HSD system routing | Ravi | 2025-08-20
7 |  | Chemical spillages from CDS yard to be treated - Plan/Layout | Ravi
8 |  | Scrubber dwgs and new vendor for Drains | Ravi | 2025-08-25
9 |  |  |  | 2025-08-30
10
11 |  |  |  | 2025-08-20
12
13
14
15 |  |  |  | 2025-08-25
16 |  |  |  | 2025-08-25
17 |  |  |  | 2025-08-22
18 |  |  |  | 2025-08-24
19 |  |  |  | 2025-08-25
20 |  |  |  | 2025-08-25
21 |  |  |  | 2025-08-27
22 |  |  |  | 2025-08-29

## Utilities -P1 (hidden)
| Procurement Team | Package | Vendor | Basic Engg | RFQ float | Offer Receipt | Negotiation | PO release | Adv Payment | P&ID | Detail Engg | GA Drawing | Manufacturing Clerance | Engineering Target Date | Inspection Target Date | Material Delivery Target Date | Installation Target Date | Commission Target Date | Engineering % Completion | Execution % Completed | Remarks
Water Package
Water Package | Praveen | UPW | Membrane | [10 empty] | Completed |  | 2025-11-15 | 2026-03-30 | 2026-05-30 |  |  | Under Manufacturing
| Praveen | ETP | Membrane | [12 empty] | 2025-11-15 | 2026-03-30 | 2026-05-30 |  |  | Under Manufacturing
| Praveen | ZLD | Membrane | [12 empty] | 2025-11-15 | 2026-03-30 | 2026-05-30 |  |  | Under Manufacturing
| Praveen | STP | Membrane | [12 empty] | 2025-11-15 | 2026-03-30 | 2026-05-30 |  |  | Under Manufacturing
| Praveen | DI Water | Membrane | [12 empty] | 2025-11-15 | 2026-03-30 | 2026-05-30 |  |  | Under Manufacturing
| Praveen | Liquid Lime Handling System | Membrane | [10 empty] | Completed |  | 2025-11-15 | 2026-03-30 | 2026-05-30 |  |  | Under Manufacturing
| Praveen | Solid Lime Handling System | DYNAMIX | [10 empty] | 2025-11-30 |  | 2026-01-20 | 2026-02-15 | 2026-03-30 |  |  | Under Manufacturing
Gas and Chemical Package
GAS Package | Praveen | Bullk Gas System | AARON | [10 empty] | 2025-10-08 | [6 empty] | Under Finalization of MDL
| Praveen | Chemical System | UHP Technologies | [10 empty] | Completed | [6 empty] | Execution Pan will be shared by 10 Oct
| Praveen | Bulk Gas Piping | UHP Technologies
| Praveen | Bulk Gas Generation | Inox Air | [10 empty] | Completed | [6 empty] | Under manufacturing
| Praveen | PNG Gas | Think Gas | [10 empty] | 2025-10-15 | [6 empty] | Commercial Closed
| Praveen | PNG Piping | Yet to Finalize | [17 empty] | Under Basic Design Stage
| Praveen | Chemical Drain Piping | Yet to Finalize | [17 empty] | Under Basic Design Stage
| Praveen | Di Water Piping | Yet to Finalize
| Praveen | Other Water Piping | Yet to Finalize
CDA
| Praveen | Compressors | ATLASCOPCO | [10 empty] | 2025-10-15 | [6 empty] | Under Manufacturing and Foundation Drawing
| Praveen | Make- Up Tank | Yet to Finalize | [10 empty] | 2025-11-30 | [6 empty] | Under Basic Design Stage
| Praveen | CDA Piping | Yet to Finalize | [10 empty] | 2025-11-30 | [6 empty] | Under Basic Design Stage
| Kumar | Soft Starter for compressor | Yet to Finalize | [10 empty] | 2025-10-15 | [6 empty] | Under Technico Commercial Evaluation
Cooling System
| Praveen | HVAC System | Yet to Finalize | [10 empty] | 2025-10-10 | [6 empty] | Engineering Discusion with ATE and Vendor
| Praveen | Chillers | Carrier | [10 empty] | 2025-10-30 | [6 empty] | PO Awarded
| Praveen | Process Cooling Water (PCW) | Yet to Finalize | [10 empty] | 2025-10-10 | [6 empty] | Engineering Discusion with ATE and Vendor
| Praveen | Exhaust System | Yet to Finalize | [10 empty] | 2025-10-10 | [6 empty] | Engineering Discusion with ATE and Vendor
| Praveen | Clean Room | Pophen | [10 empty] | 2025-10-30 | [6 empty] | PO Awaited
| Praveen | Fan Filter Unit | Mayair International
Fire System
| Kumar | Fire Hydrant System | Yet to Finalize | [10 empty] | 2025-10-18 | [6 empty] | Detail Designing under progress
| Kumar | Fire Sprinkler System | Yet to Finalize | [10 empty] | 2025-10-18 | [6 empty] | Detail Designing under progress
| Kumar | Fire Alarm System | Yet to Finalize | [10 empty] | 2025-10-18 | [6 empty] | Detail Designing under progress
Electrical System
| Kumar | 200 / 11 KVA Sub Station | VVRR/ Vertex | [10 empty] | 2026-03-31 | [6 empty] | Major Lead Item Order - Construction Started
| Kumar | HV Electrical - Transformer HV 220/ 11 KVA - 50 MVA | 1) Bharat Bijlee - 1Qty 2) TMC - 2 Qty | [10 empty] | 2026-01-10 | [6 empty] | Manufacturing Clearance Given - Drawing Re Submitted
| Kumar | HV Electrical - Transformer HV 220/ 33 KVA - 50 MVA | 1) TMC - 1 Qty | [17 empty] | Under GA Drawing Preparation from Vendor
| Kumar | LV Electrical - Transformer LV (11KV to 400V/ 433V) | 1) TMC - 8 + 0 Qty 2) Volt Amp -20 + 8 Qty 3) Hitachi - 0 + 19 Qty | [17 empty] | Manufacturing Clearance Given - Drawing Re Submitted
| Kumar | HV Electrical - DG Set | Jakson | [10 empty] | 2025-10-10 | [6 empty] | GA Drawing under preparation
| Kumar | HV Electrical - AMF Panel | Yet to Finalize | [10 empty] | 2025-10-30 | [6 empty] | RFQ under Preparation
| Kumar | HV Electical - Bus Bar | Yet to Finalize | [10 empty] | 2025-10-30 | [6 empty] | RFQ under Preparation
| Kumar | HV Electrical - 11 HV Panel | Yet to Finalize | [10 empty] | 2025-10-30 | [6 empty] | RFQ Floated
| Kumar | HV Electrical - HV Cable | Poly Cab | [10 empty] | 2025-10-08 | [6 empty] | RFQ Floated
| Kumar | LV Electrical - LV Panel | Yet to Finalize | [17 empty] | RFQ Under Preparation
| Kumar | LV Electrical - BUS Duct & Support | Yet to Finalize | [17 empty] | RFQ Under Preparation
| Kumar | LV Electrical - UPS System | Yet to Finalize | [17 empty] | RFQ Under Preparation
| Kumar | LV Electrical - Cable Tray | Yet to Finalize | [17 empty] | RFQ Under Preparation
| Kumar | LV Electrical - Lugs and Terminal | Yet to Finalize | [17 empty] | RFQ Under Preparation
| Kumar | LV Electrical - Lighting Inside | Yet to Finalize | [17 empty] | Yet to Start
| Kumar | LV Electrical - Area Lighting | Yet to Finalize | [17 empty] | Basic Design Started
| Kumar | LV Electrical - Earthing | Yet to Finalize | [17 empty] | Yet to Start
Facility System
| Kumar | CCTV and Server | Yet to Finalize | [17 empty] | Yet to Start
| Kumar | Boom Barrier and Access System | Yet to Finalize | [17 empty] | Yet to Start
| Kumar | Other | Yet to Finalize | [17 empty] | Yet to Start
Other Elements
| Raju | Weight Bridge | Tulaman
| Raju | Main Gates
| Raju | Door & Shutter
| Raju | Epoxy
| Raju | Docklever
| Kiran | Lift Material
| Kiran | Lift for Human
| Raju | Rack and System
| Raju | Air Shower

## Civil - P1 (hidden)
Building | Process | Vendor | Drawing/Approval |  |  |  |  | Commercial | [7 empty] | Execution Update |  |  |  |  | Remarks
|  |  | Concept Drawing | STAAD Drawing | Anchor Bolt Drawing | GA Drawing | Foundation Drawing | Basic Engg | RFQ float | Offer Receipt | Negotiation | PO release | Advance Payment | Mobilization | Target Date | Planned Start Date | Planned End Date | Projected / Actual Completion Date | Planned Progress | Actual Progress
Cell Building Phase 1 | Civil | SRR | [12 empty] | Done | 2025-06-01 | 2025-07-31 | 2025-07-22 | 100% | 100% | Complete Box Target by 30 Oct
| PEB | Epack | [12 empty] | Done | 2024-07-07 | 2025-10-30 |  |  | 70%
Cell Building Phase 2 | Civil | SRR | [12 empty] | Done | 2025-08-01 | 2025-10-30 |  | 50% | 60% | Zone 1: 50% Zone 2 : 69% Zone 3: 61%
| PEB | Epack | [12 empty] | Done
Compound Wall | Civil | SRR | [12 empty] | Done | 2025-06-17 | 2025-10-30 |  |  | 43% | Color Shed sample will ready by 18th Sep
FG/RM Shed | Civil | CSR | [12 empty] | Done | 2025-06-30 | 2025-10-30 |  |  | 85% | Anchor Bolt Received at Site. PEB Struture will Start Delivery at Site from 20 Sep
| PEB | Bheema | [12 empty] | Done | 2025-09-16 | 2025-11-30
ETP Shed & Tank | Civil | SRR | [12 empty] | Done | 2025-08-07 | 2025-10-31 |  |  | 29% | PEB Material Inspection at Factory done on 13 Sep. Tank Foundation Progress : 29% ETP Shed Foundation Progress: 28.3%
| PEB | Epack | [12 empty] | Done | 2025-09-15 | 2025-11-30
Scrap & Logistics Shed / Admin | Civil | CSR | [12 empty] | Done | 2025-09-01 | 2026-01-14 |  |  | 10% | Execution Work Started at Site
Gas Yard | Civil | SRR | [13 empty] | 2025-09-27 | 2025-11-30 |  |  |  | RFQ Floated
| PEB | Steel Fab Engg | [13 empty] | 2025-09-27 | 2025-11-30
Chemical Yard | Civil | CSR | [12 empty] | 2025-09-30 | 2025-09-27 | 2025-11-30 |  |  |  | RFQ Floated
| PEB | Bheema | [13 empty] | 2025-09-27 | 2025-11-30
N2 Yard | Civil | [13 empty] | 2025-09-30 | [5 empty] | Design Under Evaluation
PEB
CDA/PCW Yard | Civil | [13 empty] | 2025-09-30 | [5 empty] | Design Under Evaluation
PEB
Main Building (Admin) | Civil | [13 empty] | 2025-10-15 | 2025-10-01 | 2025-03-30 |  |  |  | Architectural Drawing have been Shared. Strutural Input will be shared by 24th Sep
| Interior | Grapid
HR/Safety/ IT/Admin | Civil | [13 empty] | 2025-10-15 | 2025-11-01 | 2025-03-30 |  |  |  | Awaiting Architectual Drawing - Traget by 25th Sep
| Interior | Grapid
Canteen Building | Civil | [13 empty] | 2025-10-15 | 2025-11-01 | 2025-03-30 |  |  |  | Awaiting Architectual Drawing - Traget by 25th Sep
| Interior | Grapid
Other Activities
200 / 11 KVA Sub Station | Turn Key Solution | Vertex VVRR | [13 empty] | 2025-09-01 | 2026-03-31 |  |  |  | Material Order Released Site Execution Started
Weight Bridge | Acc | Tulaman | [12 empty] | Done | 2025-06-15 | 2025-09-30 |  |  |  | Commisioning will will complleyed by 12 Sep Government License Target by 25 Sep
Peripheral Drain Network | Civil | SRR | [13 empty] | 2025-09-10 | 2025-09-30 |  |  | 5% | Execution Started at Site
Drain Network | Civil | [19 empty] | Design Ready
Sewage Network | Civil | [19 empty] | Design Ready
Road Network Inside | Civil | [19 empty] | Yet to Start
Main Gates | Civil | [19 empty] | Concept under Development
Door & Shutter | Acc | [19 empty] | RFQ for FG/ RM under Preparation
Epoxy | Acc | [19 empty] | Yet to Start
Docklever | Acc | Gandhi Automation | [18 empty] | Order Placed for Main Shed and FG / RM Shed
Lift Material | Acc | [19 empty] | RFQ Raised for Main Shed / Scrap Yard
Lift for Human | Acc | [19 empty] | Yet to Start
Rack and System | Acc | [19 empty] | Yet to Start
Air Shower | Acc | [19 empty] | Yet to Start
Formulas:
Planned End Date = [Execution Update]+60
Planned End Date = [Execution Update]+(4.5*30)
Projected / Actual Completion Date = [Execution Update]+51

## Process Tools -P2
Package | Procure Owner | Design Owner | Package | Vendor | Priority | Order Status - RFQ -Offer Receipt - Negotiation - PO Release - Adv Payment | Detail Engg - P&ID - GA Drg - Foundation Drg | Manufacturing - Clerance | Material Delivery at Site | Tool Move in | Installation | Hook Up & Commission Target Date | Progress 10% - Order Finalize 20% - Detail Engg Completion 30% - Manufacturing 60% - Delivery 80% Installation 95% - Commision 100% - Handover Operation | Remarks
Process Tool Set 1 | Praveen | Ravi | THERMAL TOOLS | Viva Solar(Linyan) |  | Completed 30 Oct 25 | Completed | Completed | 2026-03-30 | 2026-04-30 | 2026-05-30 | 2026-06-30 | 30% | Manufacturing activities have commenced.
| Praveen | Ravi | WET TOOLS | Viva Solar(Linyan) |  | Completed 30 Oct 25 | Completed | Completed | 2026-03-30 | 2026-04-30 | 2026-05-30 | 2026-06-30 | 30% | Manufacturing activities have commenced.
| Praveen | Ravi | AUXILLIARIES TOOLS | Viva Solar(Linyan) |  | Completed 30 Oct 25 | Completed | Completed | 2026-03-30 | 2026-04-30 | 2026-05-30 | 2026-06-30 | 30% | Manufacturing activities have commenced.
| Praveen | Ravi | CELL MANUFACTURING EQUIPMENT | Viva Solar(Linyan) |  | Completed 30 Oct 25 | Completed | Completed | 2026-03-30 | 2026-04-30 | 2026-05-30 | 2026-06-30 | 30% | Manufacturing activities have commenced.
Process Tool Set 2 |  |  | THERMAL TOOLS | SCZ Global L.L.C.-Fz |  | Completed 19 Nov 25 | Completed | Completed | 2026-03-30 | 2026-04-30 | 2026-05-30 | 2026-06-30 | 8% | Manufacturing activities have commenced.
|  |  | WET TOOLS | SCZ Global L.L.C.-Fz |  | Completed 19 Nov 25 | Completed | Completed | 2026-03-30 | 2026-04-30 | 2026-05-30 | 2026-06-30 | 8% | Manufacturing activities have commenced.
|  |  | AUXILLIARIES TOOLS | SCZ Global L.L.C.-Fz |  | Completed 19 Nov 25 | Completed | Completed | 2026-03-30 | 2026-04-30 | 2026-05-30 | 2026-06-30 | 8% | Manufacturing activities have commenced.
|  |  | CELL MANUFACTURING EQUIPMENT | SCZ Global L.L.C.-Fz |  | Completed 19 Nov 25 | Completed | Completed | 2026-03-30 | 2026-04-30 | 2026-05-30 | 2026-06-30 | 8% | Manufacturing activities have commenced.
100%

## Process Tools
Package | Procure Owner | Design Owner | Package | Vendor | Priority | Order Status - RFQ -Offer Receipt - Negotiation - PO Release - Adv Payment | Detail Engg - P&ID - GA Drg - Foundation Drg | Manufacturing - Clerance | Material Delivery at Site Start Target Date | Tool Move In & Installation Target Date | Hook Up & Commission Target Date | Progress 10% - Order Finalize 20% - Detail Engg Completion 30% - Manufacturing 60% - Delivery 80% Installation 95% - Commision 100% - Handover Operation | Remarks
Process Tool | Praveen | Ravi | Load/Unload Automation | Viva Solar(Linyan) |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Ravi | Inline BSG Removal & Real Polish | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Ravi | Inline PSG Removal & RCA | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Ravi | Boron Diffusion | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Ravi | PECVD Automation (1 By 1) Front | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Ravi | LPCVD | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Madhusudan | LPCVD Automation (1 By 1) | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Ravi | PoCl3 Diffusion | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Ravi | ALD | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Vivek | Front-PECVD | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
| Praveen | Younus | Rear PECVD | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
|  |  | PECVD Automation (1 By 1) | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
|  |  | LECO | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
|  |  | Inline Tester & Sorter | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
|  |  | Offline Tester & Sorter | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
|  |  | AGV Charging Satation | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
|  |  | PoCl3 Diffusion Quartz Boat Cleaning Mac | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
|  |  | LPCVD Quartz Boat Cleaning Machine | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Under Manufacturing and Packaging Process
|  |  | Quartz tube Cleaning Machine | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  | Rework Tool & Automation | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  | Graphite Boat Cleaning | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  | Quartz Boats For Diffusion | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  | Aluminium Boats For ALD | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  | Graphite Boats For PECVD | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  | Automation Packaging Line | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  | Batch Texture | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  | Boron Diffusion Quartz Boat Cleaning Mac | Viva Solar |  | Completed 30 Oct 25 | Completed 26 Oct 25 | Completed 26 Oct 25 | 2026-03-30 |  |  | 30% | Manufacturing activities have commenced.
|  |  |  | SCZ Global L.L.C.-Fz | [7 empty] | 100%

## Dry Type Transformer
Dry Type Transformer
Make | 11KV/400V | 11KV/433V | Total Quantity
Volt Amp - 2500KVA | 20 | 8 | 28
Hitachi - 2500KVA | 0 | 19 | 19
TMC - 2500KVA | 8 | 0 | 8
Total | 28 | 27 | 55

## EP - PEB (hidden)
Building | Vendor Name |  | Conceptual dwg from VMS | Conceptual dwg from Vendor to VMS / Premier | Approval on concept dwg by Premier to Vendor | STAAD file submission by Vendor for review to Premier | Staad file approved by Premier/VMS | Anchor bolts plan submission by Vendor to Premier | Anchor bolts plan confirmation by Premier to Vendor | Final GA dwg submission by Vendor to Premier | Final GA dwg confirmation by Premier to Vendor
Cell Building 1 | EPACK | 2025-04-01 | 2025-04-01 |  |  | 2025-04-23 | 2025-05-02 | 2025-04-25 | 2025-05-02 | 2025-04-25 | 2025-05-02
Cell Building 1 | EPACK | 2025-04-01 | 2025-04-01 |  |  |  |  | 2025-08-02 | 2025-08-18
FG Shed | BHEEMA | 2025-06-01 | 2025-06-01 | 2025-05-29 | 2025-06-18 | 2025-07-01 | 2025-07-04 | 2025-07-04 | 2025-07-14
ETP Shed | EPACK | 2025-06-01 | 2025-06-12 | 2025-06-12 |  |  | 2025-07-05
Scrap & Logistics Shed | CSR | 2025-08-05 | 2025-08-07
Gas Yard
Chemical Yard
N2 Yard
CDA/PCW/Chiller Yard
Admin
Canteen
Hr / Admin

## Critical Drawings
S.No. | Building | Drawing | Release Date | Remarks
1 | ETP | RM/FG shed - toilet location & dwgs
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23