## Sheet1
PREMIER ENERGIES GLOBAL ENVIRONMENTAL PRIVATE LIMITED
CAPEX PROJECT AUDIT REPOERT (NAIDUPET) - ACTION PLAN
S.No | Observation | Existing Law/ Recommendation | Action plan | Responsibility | Target Date | Evidence | Evidence
1 | No occupational health & hygiene program – The plan only mentions first aid/medical rooms but does not include dust/noise/heat/ vibration monitoring or periodic health checks. | Factories Act, 1948 (Sec. 13, 41F, 87) and BOCW Act,1996 (Sec. 32, 40) require ongoing monitoring of harmful exposures and medical surveillance to protect workers from long-term illnesses. | Pre medical checkup conducted for all workers and conducted dust, noise monitoring | EHS&HR | Closed
2 | No traffic & pedestrian safety plan inside site – The plan stops at vehicle entry checks (license, reverse horn) but lacks segregation of people / vehicles, marked walkways, marshals, or speed control systems. | BOCW Rules, 1998 (Rule 36) and Motor Vehicles Act, 1988 mandate precautions for safe transport of materials and protection of workers from vehicle accidents inside sites. | 1 To be established a traffic and pedestrian management plan, with segregated routes, marked walkways 2. To be recruited marshals by contractors 3. Spped limit signages provided to be provided | Site Head - EHS | Closed
3 | Fall protection measures not detailed – The plan says workers should use PPE at height, but it does not specify rescue arrangements, scaffold tagging, anchor point standards, or inspection systems. | BOCW Act, 1996 (Sec. 32, Part VII Rules) and IS 3696 require detailed safe systems of work at height, as falls are the leading cause of construction fatalities. | Fall protection measures incorporate in CSM(Ref 14.12) and arrange boom lifts for rescue while doing the height work and provided tagging system for scaffolding structures. | Site Head - EHS | Closed
4 | No Lockout–Tagout (LOTO) procedure – The plan has a permit-to-work system, but it does not include physical isolation of energy sources (locks, tags, registers) to prevent accidental energization. | Indian Electricity Rules, 1956 (Rule 48–49) and Factories Act, Sec. 38 require safe isolation of electrical / mechanical energy before work. Implement a Lockout–Tagout (LOTO) procedure for all energy sources, integrated with the existing permitto-work system | 1. LOTO SOP available | 1. Site EHS Head | Closed
5 | Emergency Preparedness & Life Safety First aid boxes, mandated under the EHS plan to be placed at key locations, were not available on site,limiting emergency response capability. | Ensure first aid boxes are placed at all key locations | First aid boxes to be placed at all key location | Site EHS head | Closed
6 | Safety mock drills (fire, evacuation, medical emergency) required under the EHS plan had not been conducted recently, and no drill records or reports were available for verification | Conduct all types of safety mock drills (fire, evacuation, and medical emergency) at planned intervals as per the EHS annual plan and statutory requirements. | Mock drills being conducted at regular intervals and maintaining the records and recent mock drill report is enclosed herewith. | Site EHS head | Closed
7 | No documented records of noise level monitoring or provision of hearing protection were available,despite requirements in the EHS plan for noise control. |  | In CSM manual we incorparted noise level control measures,refer 14.17 in CSM manual | Site EHS head | Closed
8 | No records of dust suppression measures, such as regular water spraying, were available, leading to uncontrolled dust emissions during activities. | Water to be sprayed at regular intervals of time | Water sprinkling is now conducted on-site twice daily — in the morning and evening — to control dust emissions. Daily records of water sprinkling activities are maintained and attached as evidence. | Site EHS head | Closed
9 | No water pollution control measures, such as silt traps or sedimentation tanks, were in place, increasing the risk of contaminated runoff into nearby areas. |  | have created earth drain for diverting natural rain water runoff. | Projects Head | Closed
10 | No waste segregation bins were observed at the site, contrary to EHS plan requirements for separating construction debris, domestic waste, and hazardous materials. |  | Provided dust bins for waste collection | Site EHS head | Closed
11 | No evidence of air quality management practices, such as tree plantation or greenbelt development, was observed, although committed under the EHS plan. |  | Air monitoring test conducted and evidence attached | Projects Head | Closed
12 | Noted that a Toolbox Talk (TBT) register was not maintained, indicating that daily safety briefings and awareness sessions were neither systematically conducted nor documented. Furthermore, the absence of daily labor attendance records prevents verification of participation in these sessions. Additionally, records of job-specific safety training for high-risk activities—such as working at height, hot work, electrical work,lifting operations, and confined space entry—were not maintained by the HSE department. | Maintain Toolbox Talk registers or tracker and records of job specific safety training for all high-riskactivities to ensure compliance and awareness | Maintaining TBT records, evidance photos of TBT attached and TBT attendance attahced | Site EHS Head | Closed
13 | PPE Non- compliance: During our site visit, workers were observed performing tasks without proper PPE,including gum boots, goggles, gloves, and safety shoes, which exposes them to preventable injuries. | PPE awarness training sessions to be imparted | Site EHS team to be conducted PPE awarness training sessions to all contract workmen. Safety violation to be raised gainst non compliance and action to be taken as per PCM | Site EHS Head | Closed
14 | Permit-to-Work Non-compliance: 2 instances were observed where work was executed without initiation of a permit-to-work. | PTM awarness training sessions to be imparted | PTW awareness training conducted for all engineers, supervisors, and contractors. No work is allowed without valid permits. Raising violation as per progressive consequences management procedure if anybody is found working without workpermit | Site EHS Head | Closed
15 | Lack of Barricading at Excavation Zones: Excavation areas were not barricaded as per safety standards,increasing the risk of accidental entry and potential fall hazards. | Excavation areas are to be barricated | Dedicated Safety Steward to be recruited for barrication and signages by each contract agency and he has to take care of barrication activity at their respective work places along wioth the display of signage boards | Site EHS Head | Closed
16 | Noncompliance with Excavation Edge Clearance : During our site visit, we noted that the required 1.5 m distance between excavated earth and the pit edge was not maintained, in violation of IS 3764:1992 (Code of Safety for Excavation Work), which mandates adequate measures to prevent cave-ins |  | maintaining the minimum 1.5 m excavation edge clearance per IS 3764:1992 and implement safety measures to prevent cave-ins. | Site EHS Head | Closed
17 | Water logging Hazards on Site: Multiple areas of water logging were noted across the site, leading to unsafe footing, mosquito breeding, and risk of equipment damage. | Drainages to be provided for dewatering of rain water | We will promptly drain all water-logged areas, improve site drainage systems, and conduct regular inspections to prevent water accumulation, ensuring safe footing and reducing health and equipment risks. | Site EHS Head | Closed
18 | Absence of Safety NCR System: No system of issuing and monitoring Safety NCRs was implemented,despite it being a critical requirement for tracking and corrective action on safety violations |  | We will set up a system to issue and track Safety NCRs and ensure timely corrections. | Site EHS Head | Closed
19 | Inadequate Safety Signage and Awareness Displays: Insufficient safety banners, signage, and awarenessboards displayed at site locations, reducing visibility of safety instructions and hazard warnings forworkers | Safety signages to be displayed across the plant | All the Contractors maintaing the signage boards at their respective work locations | Site EHS head | Closed
20 | Lack of Designated Approach Roads: No designated approach roads were planned or constructed at the site, resulting in unsafe and unregulated movement of vehicles, equipment, and workers. |  | Traffic Management plan prepared and provide pedstrain pathways and speed limit signages | Site EHS head | Closed
22 | Exposed Electrical Wiring Hazards: Multiple instances of exposed electrical wiring without rubber insulation or proper grounding were observed, posing a serious risk of electrical shock and potential firehazard |  | We have implemented proper insulation and grounding for all exposed electrical wiring and established routine monitoring to ensure ongoing compliance with electrical safety standards. | Site EHS head | Closed
23 | Absence of Site Fencing / compound wall: As per BOCW Act, 1996 (Sec.32) and BOCW Rules, 1998 (Rule 35), construction sites are required to be properly fenced; however, no compound wall or fencing has been completed at the site. | Fencing to be provided for the compound wall | 90% of boundary wall work completed, only East side work going on | Projects Head | Closed
24 | EHS records (electrical safety, labour camp,vehicle/equipment checks, work permits, JSAs) were only available from August though work began in June. • Out of the 30 sampled vehicle checklists, 16 instances were found with missing information. Additionally,the checklist template did not require an approver’s signature, increasing the risk of incomplete inspections going unverified and unsafe vehicles being released for use. Further there is no designed mechanism to validate the closer remarks or implementation of action plan based on the recommendation. | Vehicle and equipment checklists to be revised | 1.The vehicle and equipment checklist format to be revised by inchuding approver's signature and remarks section 2. Training to be given to EHS team on filling the formats and monthly internal inspection to be carriedout to find out the gaps in the filled formats. 3. Deviation log to be maintained for closure of the recommendations / observations. | Site EHS head | Closed
25 | Out of the 30 sampled Toolbox Talk form, 22 instances did not have trainee signatures, and in 25 instances the meeting information was not recorded. No evidence was available to show that correctiveaction plans for the points discussed were documented or implemented. | Training to be imparted to all EHS team members | 1. Training to be given to EHS team on filling the TBT formats and monthly internal inspection to be carriedout to find out the gaps in the filled formats. 2. Deviation log to be maintained for closure of the recommendations / observations. | Site EHS head | Closed
26 | Labour inspection checklist only prepared for September, moreover, there is no procedure defined to document the remarks and ensure that the findings are closed and accountable entity. | Deviation log sheet to be developed for Labour inspection checklist | Deviation log sheet to be prepared for the labour inspection checklist to ensure that the finding are closed and accountable | Site EHS head | Closed
27 | Improper Operation of Boom Lift : Unauthorized operation of the boom lift was noted, with the equipment being used by someone not identified as the designated licensed operator. | List of authorized operators to be pasted over all boom lifts | Operaters licenses to be checked by site EHS team and the same list to be prepared and pasted over all boom lifts. If unauthorized operation found, violation to be taised by site EHS team | Site EHS head | Closed
28 | Non-Adherence to Safety Protocols : No proper safety protocols were implemented during concrete pouring activities, and safe ladder practices such as maintaining three-point contact were not followed. | This point to be deleted after discussing with Projects Head | Conducted 3point contact awareness training to the concrete team while access the ladder and Monitering strict adherence to safety protocols during concrete pouring and enforce safe ladder practices, including maintaining three-point contact. | Site EHS Head | Closed
29 | Data Security Risk : Most EHS data, including checklists, permits, and records, is shared locally onpersonal phones and communicated over WhatsApp. This practice poses a significant risk of data leaks,loss of critical safety records, and lack of traceability, as there is no secure, centralized system for data storage and sharing | This point to be deleted after discussing with Projects Head | Maintain all EHS data in a secure in system and ensure data transfer and communication are conducted via official email channels instead of personal phones or WhatsApp. | Site EHS Head | Closed
30 | Lack of Designated Pathways at site : There was no designated pathway, where workers could safely move without coming into proximity to the work locations. | To be discussed with Projects head | provided site approch access ares and provided speed limit boards | Site EHS Head | Closed
31 | Lack of Security Training : Security staff had no documented training records on daily operations, emergency response, or visitor management, therefore could not be validated. | Admin Scope | Hand over to admin |  | Closed
32 | Missing Site Layout Display : The site layout plan was not displayed at the entrance, restricting awareness of emergency exits, muster points, and key facilities | To be discussed with Projects head | Plant Layout Displayed at security office, labour camp, project office | Site EHS Head | Closed
33 | Absence of Incident Logbook : No incident logbook was maintained at the site to record security incident,no structured reporting system was established for theft, trespassing, fights, weakening the ability toinvestigate and prevent recurrence. |  | Provided incident logbook | Site EHS Head | Closed
34 | Emergency Contact List Not Displayed : Emergency contact numbers (ambulance, hospital, fire services,police, safety officer, site in-charge) were not displayed prominently at the site. | Emergency contact list to be prepared and displayed | Emergency contact list to be prepared and displayed | Site EHS Head | Closed
35 | Visitor Management System Not Implemented : No formal system was in place for issuing visitor passesor recording details such as name, company, purpose of visit, and in/out times | Admin Scope | Visitor entry process and records are maintained and visitor induction also given to visitors by EHS team |  | Closed
36 | No Verification of Security Staff Credentials : No records were available to confirm verification ofidentity, background, or training credentials of security personnel deployed at the site. | Admin Scope | Hand over to admin |  | Closed
37 | No Access Control for Restricted Areas : Restricted areas such as electrical rooms, fuel storage points,and heavy equipment yards were accessible without locks, passes, or clear signage, as no access control measures were implemented. | This point to be deleted after discussing with Projects Head | identified restricted areas and provided clear signage boards for restricted entry | Site EHS head | Closed

## Sheet2
PREMIER ENERGIES GLOBAL ENVIRONMENTAL PRIVATE LIMITED
CAPEX PROJECT AUDIT REPOERT (NAIDUPET) - ACTION PLAN
S.No | Observation | Existing Law/ Recommendation | Action plan | Responsibility | Target Date | Evidence