## Sheet1
PREMIER ENERGIES GLOBAL ENVIRONMENTAL PRIVATE LIMITED
CAPEX PROJECT AUDIT REPOERT SEETHARAMPUR - ACTION PLAN
S.No | Observation | Existing Law/ Recommendation | Corrective Action | Responsibility | Traget Date | Target Date | Evidence
1 | No occupational health & hygiene program – The plan only mentions first aid/medical rooms but does not include dust/noise/heat/ vibration monitoring or periodic health checks. | Factories Act, 1948 (Sec. 13, 41F, 87) and BOCW Act,1996 (Sec. 32, 40) require ongoing monitoring of harmful exposures and medical surveillance to protect workers from long-term illnesses. | Pre employment medical examination done for contract employees before onboarding, ensure the employee fitness. Updated the plan with dust & noise monitoring plan as per the CPCB | Site Admin /EHS |  | Closed | Workmen medical check up being conducted and recorded.
2 | No traffic & pedestrian safety plan inside site – The plan stops at vehicle entry checks (license, reverse horn) but lacks segregation of people / vehicles, marked walkways, marshals, or speed control systems. | BOCW Rules, 1998 (Rule 36) and Motor Vehicles Act, 1988 mandate precautions for safe transport of materials and protection of workers from vehicle accidents inside sites. | Pedestrain walk way marking done and segrigated from vehicle movement | Site Head - EHS |  | Closed | Photo : Pedestrain seperation pic, Speed limit board
3 | Fall protection measures not detailed – The plan says workers should use PPE at height, but it does not specify rescue arrangements, scaffold tagging, anchor point standards, or inspection systems. | BOCW Act, 1996 (Sec. 32, Part VII Rules) and IS 3696 require detailed safe systems of work at height, as falls are the leading cause of construction fatalities. | EHS plan updated with height work rescue plan refer csm manual 14.17 point | Corporate EHS |  | Closed | EHS plan screen shot & JSA updated with rescue plan
4 | No Lockout–Tagout (LOTO) procedure – The plan has a permit-to-work system, but it does not include physical isolation of energy sources (locks, tags, registers) to prevent accidental energization. | Indian Electricity Rules, 1956 (Rule 48–49) and Factories Act, Sec. 38 require safe isolation of electrical / mechanical energy before work. Implement a Lockout–Tagout (LOTO) procedure for all energy sources, integrated with the existing permitto-work system | SOP is available for LOTO. Will be followed for all energy isolation. | Project head/Site EHS Head |  | Closed | LOTO procedure
5 | Emergency Preparedness & Life Safety First aid boxes, mandated under the EHS plan to be placed at key locations, were not available on site,limiting emergency response capability. | Ensure first aid boxes are placed at all key locations | First aid boxes to be placed at all key location | Respective Contrct agencies |  | Closed |  | List of area provided First aid box
6 | Safety mock drills (fire, evacuation, medical emergency) required under the EHS plan had not been conducted recently, and no drill records or reports were available for verification | Conduct all types of safety mock drills (fire, evacuation, and medical emergency) at planned intervals as per the EHS annual plan and statutory requirements. | Mock drills conducted at regular intervals and maintaining the records and recent mock drill report is enclosed herewith. | Site EHS head |  | Closed |  | Mock drill report to be attached
| No documented records of noise level monitoring or provision of hearing protection were available,despite requirements in the EHS plan for noise control. |  | For all high noise zone area - Contract employees are provided with Ear plug and ear muff. Monthly monitoring conducted with external agency.Report attached | 2025-11-15 |  | Closed
8 | No records of dust suppression measures, such as regular water spraying, were available, leading to uncontrolled dust emissions during activities. | Water to be sprayed at regular intervals of time | Water sprinkling started to suppress the dust at project site- twice daily — in the morning and evening — to control dust emissions. Daily records of water sprinkling activities are maintained and attached as evidence. | Projects Head |  | Closed |  | Record to be attached
9 | No water pollution control measures, such as silt traps or sedimentation tanks, were in place, increasing the risk of contaminated runoff into nearby areas. |  | have created earth drain for diverting natural rain water runoff. |  |  | Closed
10 | No waste segregation bins were observed at the site, contrary to EHS plan requirements for separating construction debris, domestic waste, and hazardous materials. |  | Waste material segrigated and separate storage areas arranged |  |  | Closed
11 | No evidence of air quality management practices, such as tree plantation or greenbelt development, was observed, although committed under the EHS plan. |  | Tree plantation will be planed,The same will be need to be discussed with management.So far we are closing this point |  |  | Closed
12 | Noted that a Toolbox Talk (TBT) register was not maintained, indicating that daily safety briefings and awareness sessions were neither systematically conducted nor documented. Furthermore, the absence of daily labor attendance records prevents verification of participation in these sessions. Additionally, records of job-specific safety training for high-risk activities—such as working at height, hot work, electrical work,lifting operations, and confined space entry—were not maintained by the HSE department. | Maintain Toolbox Talk registers or tracker and records of job specific safety training for all high-riskactivities to ensure compliance and awareness | Maintaining TBT records, evidance photos of TBT attached and TBT attendance attahced | Site EHS Head |  | Closed
13 | PPE Non- compliance: During our site visit, workers were observed performing tasks without proper PPE,including gum boots, goggles, gloves, and safety shoes, which exposes them to preventable injuries. | PPE awarness training sessions to be imparted | PPE awareness training conducted to all the contract employees and will be ensured 100 % compliance of PPE usage. | Site EHS Head |  | Closed
14 | Oversight of site & Standard compliances: This activity falls under the contractor’s scope; however, it issupervised by the entity to ensure that the required work is executed and validated in accordance withapplicable IS standards. |  | PPE awareness training conducted to all the contract employees and will be ensured 100 % compliance of PPE usage. | Site EHS Head |  | Closed
15 | Lack of Barricading at Excavation Zones: Excavation areas were not barricaded as per safety standards,increasing the risk of accidental entry and potential fall hazards. | Excavation areas are to be barricated | Barricaded all the excavation pits. Awareness session conducted to all the contractors to comply with the safety requirements | Project Head |  | Closed
16 | Noncompliance with Excavation Edge Clearance : During our site visit, we noted that the required 1.5 m distance between excavated earth and the pit edge was not maintained, in violation of IS 3764:1992 (Code of Safety for Excavation Work), which mandates adequate measures to prevent cave-ins |  | maintaining the minimum 1.5 m excavation edge clearance per IS 3764:1992 and implement safety measures to prevent cave-ins. |  |  | Closed | #VALUE!
17 | Water logging Hazards on Site: Multiple areas of water logging were noted across the site, leading to unsafe footing, mosquito breeding, and risk of equipment damage. | Drainages to be provided for dewatering of rain water | We will promptly drain all water-logged areas, improve site drainage systems, and conduct regular inspections to prevent water accumulation, ensuring safe footing and reducing health and equipment risks. | Nil |  | Closed
18 | Absence of Safety NCR System: No system of issuing and monitoring Safety NCRs was implemented,despite it being a critical requirement for tracking and corrective action on safety violations |  | NCR are identified and cerculated to all concerned team to close the EHS NCRs. NCR record attached for ref |  |  | Closed | NCR TRACKER IS MAINTAINING
19 | Inadequate Safety Signage and Awareness Displays: Insufficient safety banners, signage, and awarenessboards displayed at site locations, reducing visibility of safety instructions and hazard warnings forworkers | Safety signages to be displayed across the plant | Safety sign boards are arranged at site. Attached pics for ref | Site EHS head |  | Closed | Pics to be attached
20 | Lack of Designated Approach Roads: No designated approach roads were planned or constructed at the site, resulting in unsafe and unregulated movement of vehicles, equipment, and workers. |  | Approach road to reach site office is available and segrigated pedestrain and vehicle. |  |  | Closed
21 | Exposed Electrical Wiring Hazards: Multiple instances of exposed electrical wiring without rubber insulation or proper grounding were observed, posing a serious risk of electrical shock and potential firehazard |  | We have implemented proper insulation and grounding for all exposed electrical wiring and established routine monitoring to ensure ongoing compliance with electrical safety standards. |  |  | Closed
22 | Absence of Site Fencing / compound wall: As per BOCW Act, 1996 (Sec.32) and BOCW Rules, 1998 (Rule 35), construction sites are required to be properly fenced; however, no compound wall or fencing has been completed at the site. | Fencing to be provided for the compound wall | Boundry wall construction work is under progress,However 70 % of work completed.Refer enclosed pics | Projects Head |  | Closed
23 | Non-Adherence to Safety Protocols : No proper safety protocols were implemented during concrete pouring activities, and safe ladder practices such as maintaining three-point contact were not followed. | This point to be deleted after discussing with Projects Head | Lader provided. Awareness training conducted for contract employees. | Site EHS Head |  | Closed |  | Ladder photo Awareness training record
24 | Data Security Risk : Most EHS data, including checklists, permits, and records, is shared locally onpersonal phones and communicated over WhatsApp. This practice poses a significant risk of data leaks,loss of critical safety records, and lack of traceability, as there is no secure, centralized system for data storage and sharing | This point to be deleted after discussing with Projects Head | Maintain all EHS data in a secure in system and ensure data transfer and communication are conducted via official email channels instead of personal phones or WhatsApp. | Site EHS Head |  | Closed
25 | Lack of Designated Pathways at site : There was no designated pathway, where workers could safely move without coming into proximity to the work locations. | To be discussed with Projects head | provided site approch access. |  |  | Closed | Approach road photo to be attached
26 | Lack of Security Training : Security staff had no documented training records on daily operations, emergency response, or visitor management, therefore could not be validated. | Admin Scope | Periodically trainings has been conducted.Attendance sheet attached for reference |  |  | Closed
27 | Missing Site Layout Display : The site layout plan was not displayed at the entrance, restricting awareness of emergency exits, muster points, and key facilities | To be discussed with Projects head | Plant Layout Displayed at security office, labour colony, project office |  |  | Closed
28 | Absence of Incident Logbook : No incident logbook was maintained at the site to record security incident,no structured reporting system was established for theft, trespassing, fights, weakening the ability toinvestigate and prevent recurrence. | Admin Scope | Incident register attached |  |  | Closed
29 | Emergency Contact List Not Displayed : Emergency contact numbers (ambulance, hospital, fire services,police, safety officer, site in-charge) were not displayed prominently at the site. | Emergency contact list to be prepared and displayed | Emergency contact list prepared and displayed | Site EHS Head |  | Closed
30 | Visitor Management System Not Implemented : No formal system was in place for issuing visitor passesor recording details such as name, company, purpose of visit, and in/out times | Admin Scope | Hand over to admin |  |  | Closed
31 | No Verification of Security Staff Credentials : No records were available to confirm verification ofidentity, background, or training credentials of security personnel deployed at the site. | Admin Scope | Hand over to admin |  |  | Closed